## Contract Register Format
MANDERA COUNTY GOVERNMENT
MANDERA MUNICIPALITY CONTRACT REGISTER
| NO. | CONTRACT NO. | PROJECT NAME | CONTRACTOR | METHOD OF PROCUREMENT | FINANCIER | COST OF PROJECT (Ksh.) | CONTRACT START DATE | CONTRACT EXPECTED END DATE | CATEGORY OF CONTRACT | COMPLETION DATE | RETENTION AMOUNT (Ksh.) | PAYMENT OF RETENTION
| 1 | MCG/OT/KUSP/02/2018-2019 | PROPOSED PROTECTION WORKS FOR STORM WATER DRAIN IN MANDERA MUNICIPALITY | MASHO HILL COMPANY LTD | OPEN | KUSP | 124484301.48 | 2019-04-01 | 2020-04-01 | WORKS | 2020-04-01 | 12448430.1 | 2020-04-01
| 2 | MCG/OT/KUSP/01/2018-2019 | PROPSED SUPPLY, DELIVERY AND INSTALLATION OF SOLAR STREET LIGHTS IN SHAFSHAFEY AND BULLA BARWAQO IN MANDERA EAST | INFOSERVE NETWORKS LIMITED | OPEN | KUSP | 49783000 | 2019-04-01 | 2020-04-01 | WORKS | 2020-04-01 | 4978300 | 2020-04-01
| 3 | MCG/OT/KUSP/01/2019-2020 | PROPOSED PROTECTION WORKS FOR STORM WATER DRAIN PHASE II IN MANDERA MUNICIPALITY | AL IMRAN INVESTMENT LIMITED | OPEN | KUSP | 124800055.8 | 20TH APRIL 2020 | 30TH APRIL 2022 | WORKS | 2022-04-01 | 12480005.5 | 2021-04-01
| 4 | MCG/OT/KUSP/02/2019-2020 | PROPSED SUPPLY, DELIVERY AND INSTALLATION OF SOLAR STREET LIGHTS IN KHALALIO AND LIVESTOCK MARKET AREA | DISTON INVESTMENT LIMITED | OPEN | KUSP | 49620395.04 | 16TH APRIL 2020 | 30TH APRIL 2022 | WORKS | 2022-04-01 | 0 | NA
5
6
7
8
9
10