## Supabase Snippet Filter Project
title | description | project_goal | project_output | project_code | budget_item_name | sub_county_name | ward_name | latitude | longitude | sector_vote_name | department_name | directorate_name | implementing_agency_name | date_of_approval | project_start_date | expected_completion_date | actual_completion_date | estimated_project_cost | approved_project_cost | funds_available_specific_year | project_funding_source | development_partner_name | county_government_component | development_partner_component | total_disbursed_funds | percentage_disbursed | expenditure_to_date | pending_bills | project_balance | status | percentage_completion | stalled_completion_percentage | stalled_reasons | year_project_stalled | time_to_complete_months | estimated_cost_to_complete | still_in_budget | stalled_project_recommendation | associated_risks | climate_disaster_screened | climate_mitigation_action | environmental_social_screened | environmental_mitigation_action | technical_viability_screened | viability_mitigation_action | remarks
MCG/194/2013-2014 | Supply & delivery of non-pharmaceuticals to Mandera West and Banissa | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community |  |  | Mandera West | Takaba | 3.3933 | 40.2256 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 11000000 | 10675990 | 10675990 | GOK | N/A | 100 | null | 10675990 | 10675990 | 10675990 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA WEST SUB COUNTY | accessibility and social equity |  |  | public works | Mandera West | Dandu | 3.6 | 39.92 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-05 00:00:00+00 | 5870702 | 5870702 | 5870702 | GOK | N/A | 100 | 0 | 5870702 | null | 5870702 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/199/2013-2014 | Construction of El-wak SME Park | TO promotes the socio?economic development | Job creation & local economic linkages |  |  | Mandera South | Elwak South | null | null | TRADE | TRADE | Trade | TRADE | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 150000000 | 147053440 | null | GOK | N/A | 100 | null | 147053440 | 147053440 | 147053440 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/200/2013-2014 | Refurbishment and Construction of Market Stalls in Wargadud | TO promotes the socio?economic development | Job creation & local economic linkages |  |  | Mandera South | Elwak South | null | null | TRADE | TRADE | Trade | TRADE | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 5500000 | 5139000 | 5139000 | GOK | N/A | 100 | null | 5139000 | 5139000 | 5139000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 44NO HOUSING UNIT AND 44NO TOILET FOR VULNERABLE PERSONS IN MANDERA EAST SUB COUNTY | PROPOSED CONSTRUCTION OF 44NO HOUSING UNIT AND 44NO TOILET FOR VULNERABLE PERSONS IN MANDERA EAST SUB COUNTY | improve access to sanitation | environmental protection |  | Special programme | Mandera East | Township | null | null | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 43421048 | 43421048 | 43421048 | GOK | NA | 100 | 0 | 43421048 | null | 43421048 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 44NO HOUSING UNIT AND 44NO TOILET FOR VULNERABLE PERSONS IN MANDERA EAST SUB COUNTY | PROPOSED CONSTRUCTION OF 44NO HOUSING UNIT AND 44NO TOILET FOR VULNERABLE PERSONS IN MANDERA EAST SUB COUNTY | improve access to sanitation | environmental protection |  | Special programme | Mandera East | Township | null | null | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 43421048 | 43421048 | 43421048 | GOK | NA | 100 | 0 | 43421048 | null | 43421048 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
MCG/194/2013-2014 | Construction of Mandera town Roads to Bitumen Standard lot 1 | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | Tarmacking of roads | null | Mandera East | Township | 3.9486 | 41.8525 | ROADS | ROADS | ROADS | ROADS | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 1300000000 | 1218597587 | null | GOK | N/A | 100 | null | 1218597587 | 1218597587 | 1218597587 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/194/2013-2014 | Construction of Mandera town Roads to Bitumen Standard lot 1 | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | Tarmacking of roads | null | Mandera East | Township | 3.9486 | 41.8525 | ROADS | ROADS | ROADS | ROADS | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 1300000000 | 1218599554 | null | GOK | N/A | 100 | null | 1218599554 | 1218599554 | 1218599554 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA NORTH SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA NORTH SUB COUNTY | accessibility and social equity |  |  | public works | Mandera North | Guticha | 3.484 | 40.749 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-19 00:00:00+00 | 5950000 | 5950000 | 5950000 | GOK | N/A | 100 | 0 | 5950000 | null | 5950000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/207/2013-2014 | Construction of Youth Office in Mandera Town | TO promotes the socio?economic development | Office block |  |  | Mandera East | Township | null | null | EDUCATION | EDUCATION | EDUCATION | EDUCATION | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 15000000 | 14001780 | 14001780 | GOK | N/A | 100 | null | 14001780 | 14001780 | 14001780 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/215/2013-2014 | Construction of LCD Training Center in Mandera East | Improve digital learning | Digital learning |  |  | Mandera East | Township | null | null | EDUCATION | EDUCATION | EDUCATION | EDUCATION | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 10000000 | 9810920 | 9810920 | GOK | N/A | 100 | null | 9810920 | 9810920 | 9810920 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/91/2013-2014 | Improvement of Aresa, kiosks and pipe extension | improve access to water | water infrustructure | null | null | Mandera East | Libihiya | 3.7451 | 41.2886 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 5850000 | 5850000 | 5850000 | GOK | N/A | 100 | null | 5850000 | 5850000 | 5850000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/91/2013-2014 | Improvement of Aresa, kiosks and pipe extension | improve access to water | water infrustructure | null | null | Mandera East | Libihiya | 3.7451 | 41.2886 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 5850000 | 5850000 | 5850000 | GOK | N/A | 100 | null | 5850000 | 5850000 | 5850000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/86/2013-2014 | Fincharo piping and kiosks | improve access to water | water infrustructure | null | null | Mandera South | Elwak South | 2.8929 | 40.8459 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 9176622 | 9176622 | 9176622 | GOK | N/A | 100 | null | 9176622 | 9176622 | 9176622 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/86/2013-2014 | Fincharo piping and kiosks | improve access to water | water infrustructure | null | null | Mandera South | Elwak South | 2.8929 | 40.8459 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 9176622 | 9176622 | 9176622 | GOK | N/A | 100 | null | 9176622 | 9176622 | 9176622 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/81/2013-2014 | Drilling of 3 boreholes in Mandera East (Hareri Hosle, Farey and Koromey) | improve access to water | water infrustructure | null | null | Mandera East | Libihiya | 3.7636 | 41.3584 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 9948500 | 9948500 | 9948500 | GOK | N/A | 100 | null | 9948500 | 9948500 | 9948500 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/81/2013-2014 | Drilling of 3 boreholes in Mandera East (Hareri Hosle, Farey and Koromey) | improve access to water | water infrustructure | null | null | Mandera East | Libihiya | 3.7636 | 41.3584 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 9948500 | 9948500 | 9948500 | GOK | N/A | 100 | null | 9948500 | 9948500 | 9948500 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/258/2013-2014 | Supply & Delivery Of Emergency Obstetric Care Equipment | improve infrustructure | equipment | null | null | Mandera East | Township | 3.9486 | 41.8525 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 14000000 | 13685138 | 13685138 | GOK | N/A | 100 | null | 13685138 | 13685138 | 13685138 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/201/2013-2014 | Refurbishment and Construction of Market Stalls (HNO Block) in Lafey | TO promotes the socio?economic development | Job creation & local economic linkages | null | null | Lafey | Lafey | 3.2104 | 41.1784 | TRADE | TRADE | Trade | TRADE | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 11000000 | 10007900 | 10007900 | GOK | N/A | 100 | null | 10007900 | 10007900 | 10007900 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF KMTC IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF KMTC IN MANDERA EAST SUB-COUNTY | promote quality education | human resources development |  | Education | Mandera East | Township | 3.936 | 41.857 | Education | EDUCATION | EDUCATION | EDUCATION | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-14 00:00:00+00 | 256235085 | 256235085 | 80000000 | GOK | N/A | 100 | 0 | 256235085 | null | 256235085 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/208/2013-2014 | Construction of Twin Workshop in Fino | TO promotes the socio?economic development | Twin workshop |  |  | Lafey | Fino | 3.8933 | 41.8255 | EDUCATION | EDUCATION | EDUCATION | EDUCATION | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 8000000 | 7450000 | 7450000 | GOK | N/A | 100 | null | 7450000 | 7450000 | 7450000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/226/2013-2014 | Construction of 1km concrete canal at Rhamu Dimtu | improve food production | Canal constructed |  |  | Mandera South | Rhamu Dimtu | null | null | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 15000000 | 13238968 | 13238968 | GOK | N/A | 100 | null | 13238968 | 13238968 | 13238968 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/82/2013-2014 | Drilling of 4 boreholes in Mandera South (Nyat Alio, Burmayo, Falama and Shimbir Fatuma) | improve access to water | water infrustructure |  |  | Mandera South | Elwak South | 2.9129 | 40.7366 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 17299500 | 17299500 | 17299500 | GOK | N/A | 100 | null | 17299500 | 17299500 | 17299500 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/82/2013-2014 | Drilling of 4 boreholes in Mandera South (Nyat Alio, Burmayo, Falama and Shimbir Fatuma) | improve access to water | water infrustructure |  |  | Mandera South | Elwak South | 2.9129 | 40.7366 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 17299500 | 17299500 | 17299500 | GOK | N/A | 100 | null | 17299500 | 17299500 | 17299500 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/87/2013-2014 | Shirshir water improvement work | improve access to water | water infrustructure |  |  | Mandera North | Rhamu Dimtu | 3.6552 | 41.1224 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 3527700 | 3527700 | 3527700 | GOK | N/A | 100 | null | 3527700 | 3527700 | 3527700 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/87/2013-2014 | Shirshir water improvement work | improve access to water | water infrustructure |  |  | Mandera North | Rhamu Dimtu | 3.6552 | 41.1224 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 3527700 | 3527700 | 3527700 | GOK | N/A | 100 | null | 3527700 | 3527700 | 3527700 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/92/2013-2014 | Upgrading and improvement of Sala water supply | improve access to water | water infrustructure |  |  | Mandera South | WARGADUD | 3.1219 | 40.6136 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 7996153 | 7996153 | 7996153 | GOK | N/A | 100 | null | 7996153 | 7996153 | 7996153 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/92/2013-2014 | Upgrading and improvement of Sala water supply | improve access to water | water infrustructure |  |  | Mandera South | WARGADUD | 3.1219 | 40.6136 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 7996153 | 7996153 | 7996153 | GOK | N/A | 100 | null | 7996153 | 7996153 | 7996153 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/260/2013-2014 | Supply of Security uniforms | Improve service delivery | uniforms | null | null | Mandera East | Township | 3.9486 | 41.8525 | PUBLIC SERVICE | Public Service | Public Service | Public Service | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 27000000 | 26318890 | 26318890 | GOK | N/A | 100 | null | 26318890 | 26318890 | 26318890 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/202/2013-2014 | Fencing of the El-wak Slaughter House | To protect the safety and security of the property | Enhanced security | null | null | Mandera South | Elwak South | 2.8929 | 40.8459 | LIVESTOCK | Livestock | Livestock | Livestock | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 4000000 | 3906880 | 3906880 | GOK | N/A | 100 | null | 3906880 | 3906880 | 3906880 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED FENCING OF MANDERA TEACHERS TRAINING COLLEGE IN MANDERA EAST SUB COUNTY | PROPOSED FENCING OF MANDERA TEACHERS TRAINING COLLEGE IN MANDERA EAST SUB COUNTY | promote quality education | human resources development |  | Education | Mandera East | Township | 3.936 | 41.857 | Education | EDUCATION | EDUCATION | EDUCATION | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-30 00:00:00+00 | 8000000 | 8000000 | null | GOK | N/A | 100 | 0 | 8000000 | null | 8000000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/209/2013-2014 | Construction of Twin Workshop in Rhamu | TO promotes the socio?economic development | Twin workshop |  |  | Mandera South | Rhamu | 3.9362 | 41.2192 | EDUCATION | EDUCATION | EDUCATION | EDUCATION | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 8000000 | 7604680 | 7604680 | GOK | N/A | 100 | null | 7604680 | 7604680 | 7604680 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/83/2013-2014 | Drilling of 5 boreholes in Mandera North(Quramathow,Gofa,Bur John, Sukela tinfa and Kubi) | improve access to water | water infrustructure |  |  | Mandera North | ASHABITO | 3.9216 | 41.2148 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 18632000 | 18632000 | 18632000 | GOK | N/A | 100 | null | 18632000 | 18632000 | 18632000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/83/2013-2014 | Drilling of 5 boreholes in Mandera North(Quramathow,Gofa,Bur John, Sukela tinfa and Kubi) | improve access to water | water infrustructure |  |  | Mandera North | ASHABITO | 3.9216 | 41.2148 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 18632000 | 18632000 | 18632000 | GOK | N/A | 100 | null | 18632000 | 18632000 | 18632000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/88/2013-2014 | Takaba piping extension from borehole/Troughs | improve access to water | water infrustructure |  |  | Mandera West | Takaba | 3.4074 | 40.2231 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 3322828 | 3322828 | 3322828 | GOK | N/A | 100 | null | 3322828 | 3322828 | 3322828 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/88/2013-2014 | Takaba piping extension from borehole/Troughs | improve access to water | water infrustructure |  |  | Mandera West | Takaba | 3.4074 | 40.2231 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 3322828 | 3322828 | 3322828 | GOK | N/A | 100 | null | 3322828 | 3322828 | 3322828 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/93/2013-2014 | Pipe extension and works(kiosks) at wargadud | improve access to water | water infrustructure |  |  | Mandera West | Gither | 2.9644 | 40.7616 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 5534010 | 5534010 | 5534010 | GOK | N/A | 100 | null | 5534010 | 5534010 | 5534010 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/93/2013-2014 | Pipe extension and works(kiosks) at wargadud | improve access to water | water infrustructure |  |  | Mandera West | Gither | 2.9644 | 40.7616 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 5534010 | 5534010 | 5534010 | GOK | N/A | 100 | null | 5534010 | 5534010 | 5534010 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/98/2013-2014 | Construction of Dam at Ashabito 2 | improve access to water | water infrustructure |  |  | Mandera North | ASHABITO | 3.2106 | 40.9806 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6804157 | 6804157 | 6804157 | GOK | N/A | 100 | null | 6804157 | 6804157 | 6804157 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/98/2013-2014 | Construction of Dam at Ashabito 2 | improve access to water | water infrustructure |  |  | Mandera North | ASHABITO | 3.2106 | 40.9806 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6804157 | 6804157 | 6804157 | GOK | N/A | 100 | null | 6804157 | 6804157 | 6804157 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/263/2013-2014 | Provision of Consultancy Services for Detailed Design and engineering of Mandera Regional Livestock Market | improve infrustructure | consultancy | null | null | Mandera East | Neboi | 3.9621 | 41.7703 | LIVESTOCK | Livestock | Livestock | Livestock | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 12000000 | 11835559 | 11835559 | GOK | N/A | 100 | null | 11835559 | 11835559 | 11835559 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/203/2013-2014 | Fencing of Rhamu Slaughter House | To protect the safety and security of the property | Enhanced security | null | null | Mandera North | Rhamu | 3.8422 | 41.1828 | LIVESTOCK | Livestock | Livestock | Livestock | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 3000000 | 2775900 | 2775900 | GOK | N/A | 100 | null | 2775900 | 2775900 | 2775900 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED FENCING OF ELWAK SUB-COUNTY HEADQAURTER IN MANDERA SOUTH SUB-COUNTY | PROPOSED FENCING OF ELWAK SUB-COUNTY HEADQAURTER IN MANDERA SOUTH SUB-COUNTY | promote infrastructure development |  |  | public works | Mandera South | Elwak South | 2.808 | 40.926 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-28 00:00:00+00 | 25579050 | 25579050 | 7000000 | GOK | N/A | 100 | 0 | 25579050 | null | 25579050 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/210/2013-2014 | Construction of Twin Workshop in Banisa | TO promotes the socio?economic development | Twin workshop |  |  | Banisa | Banisa | 3.932 | 40.3546 | EDUCATION | EDUCATION | EDUCATION | EDUCATION | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 3000000 | 7544220 | 7544220 | GOK | N/A | 100 | null | 7544220 | 7544220 | 7544220 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/234/201 3-2014 | Construction Of Administration Police Housing Units, Abolitions Block And Office Block At Kamor | improve infrustructure | Office blocks |  |  | Mandera East | Township | 3.9264 | 41.7939 | PUBLIC SERVICE | Public Service | Public Service | Public Service | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 25000000 | 24198430 | 24198430 | GOK | N/A | 100 | null | 24198430 | 24198430 | 24198430 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/84/2013-2014 | New water supply at Bulla Haji | improve access to water | water infrustructure |  |  | Banisa | Banisa | 2.7336 | 40.9241 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 9504067 | 9504067 | 9504067 | GOK | N/A | 100 | null | 9504067 | 9504067 | 9504067 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/84/2013-2014 | New water supply at Bulla Haji | improve access to water | water infrustructure |  |  | Banisa | Banisa | 2.7336 | 40.9241 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 9504067 | 9504067 | 9504067 | GOK | N/A | 100 | null | 9504067 | 9504067 | 9504067 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/89/2013-2014 | Masonry Tank 100m3 in Elwak town | improve access to water | water infrustructure |  |  | Mandera South | Elwak South | 2.8022 | 40.925 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 4209430 | 4209430 | 4209430 | GOK | N/A | 100 | null | 4209430 | 4209430 | 4209430 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/89/2013-2014 | Masonry Tank 100m3 in Elwak town | improve access to water | water infrustructure |  |  | Mandera South | Elwak South | 2.8022 | 40.925 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 4209430 | 4209430 | 4209430 | GOK | N/A | 100 | null | 4209430 | 4209430 | 4209430 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/94/2013-2014 | Underground water tank at Harshilmi(250m3) | improve access to water | water infrustructure |  |  | Mandera West | Gither | 3.5884 | 40.7126 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 3370290 | 3370290 | 3370290 | GOK | N/A | 100 | null | 3370290 | 3370290 | 3370290 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/94/2013-2014 | Underground water tank at Harshilmi(250m3) | improve access to water | water infrustructure |  |  | Mandera West | Gither | 3.5884 | 40.7126 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 3370290 | 3370290 | 3370290 | GOK | N/A | 100 | null | 3370290 | 3370290 | 3370290 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/99/2013-2014 | Construction of Dam at Ola 1 | improve access to water | water infrustructure |  |  | Mandera North | Rhamu Dimtu | 3.1986 | 40.9706 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 7298550 | 7298550 | 7298550 | GOK | N/A | 100 | null | 7298550 | 7298550 | 7298550 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/99/2013-2014 | Construction of Dam at Ola 1 | improve access to water | water infrustructure |  |  | Mandera North | Rhamu Dimtu | 3.1986 | 40.9706 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 7298550 | 7298550 | 7298550 | GOK | N/A | 100 | null | 7298550 | 7298550 | 7298550 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/205/2013-2014 | Renovations of Mandera county referral hospital Mandera | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | null | null | Mandera East | Neboi | 3.9621 | 41.7703 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 33000000 | 30507960 | 30507960 | GOK | N/A | 100 | null | 30507960 | 30507960 | 30507960 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED PROVISION OF ASSET TAGGING SOLUTIONS TO MANDERA COUNTY GOVERNMENT | PROPOSED PROVISION OF ASSET TAGGING SOLUTIONS TO MANDERA COUNTY GOVERNMENT | proper management of assets/tracking of assets | reduced theft |  | finance | Mandera East | Township | 3.936 | 41.857 | financial services | FINANCIAL SERVICES | Financial Services | FINANCIAL SERVICES | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-29 00:00:00+00 | 11100000 | 11100000 | 11100000 | GOK | N/A | 100 | 0 | 11100000 | null | 11100000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/211/2013-2014 | Construction of Computer Laboratory at Youth Polytechnic in Mandera Town | Improve digital learning | Digital learning |  |  | Mandera East | Township | 3.9342 | 41.8581 | EDUCATION | EDUCATION | EDUCATION | EDUCATION | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 9000000 | 8833010 | 8833010 | GOK | N/A | 100 | null | 8833010 | 8833010 | 8833010 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20000m3 earth pan at Soroba in Banisa | Construction of 20000m3 earth pan at Soroba in Banisa | improved water access | Soroba earthpan | MCG/OT/39/2019-2020 | null | Banisa | Banisa | 3.8731 | 41.6044 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-11-07 00:00:00+00 | 10000000 | 10000000 | 10000000 | null | N/A | null | null | 10000000 | 100 | 10000000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Construction of 20000m3 earth pan at Soroba in Banisa | Construction of 20000m3 earth pan at Soroba in Banisa | improved water access | Soroba earthpan | MCG/OT/39/2019-2020 | null | Banisa | Banisa | 3.8731 | 41.6044 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-11-07 00:00:00+00 | 10000000 | 10000000 | 10000000 | null | N/A | null | null | 10000000 | 100 | 10000000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Mcg/80/2013-2014 | Drilling of 3 boreholes in Lafey (Lafey, Bambo and Qumbiso) | improve access to water | water infrustructure |  |  | Lafey | WARANQARA | 3.1367 | 40.6021 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 14767000 | 14767000 | 14767000 | GOK | N/A | 100 | null | 14767000 | 14767000 | 14767000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/80/2013-2014 | Drilling of 3 boreholes in Lafey (Lafey, Bambo and Qumbiso) | improve access to water | water infrustructure |  |  | Lafey | WARANQARA | 3.1367 | 40.6021 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 14767000 | 14767000 | 14767000 | GOK | N/A | 100 | null | 14767000 | 14767000 | 14767000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/85/2013-2014 | Water supply and improvement at Qalanqalesa (Piping, Tank and kiosk) | improve access to water | water infrustructure |  |  | Mandera South | Elwak South | 3.8124 | 41.3016 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 4242241 | 4242241 | 4242241 | GOK | N/A | 100 | null | 4242241 | 4242241 | 4242241 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/85/2013-2014 | Water supply and improvement at Qalanqalesa (Piping, Tank and kiosk) | improve access to water | water infrustructure |  |  | Mandera South | Elwak South | 3.8124 | 41.3016 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 4242241 | 4242241 | 4242241 | GOK | N/A | 100 | null | 4242241 | 4242241 | 4242241 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/95/2013-2014 | Rhamu elevated tank repair/Replacement | improve access to water | water infrustructure |  |  | Mandera North | Rhamu | 3.9446 | 41.2298 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 2710000 | 2710000 | 2710000 | GOK | N/A | 100 | null | 2710000 | 2710000 | 2710000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/95/2013-2014 | Rhamu elevated tank repair/Replacement | improve access to water | water infrustructure |  |  | Mandera North | Rhamu | 3.9446 | 41.2298 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 2710000 | 2710000 | 2710000 | GOK | N/A | 100 | null | 2710000 | 2710000 | 2710000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/100/2013-2014 | Construction of Dandu ï¿½ Earth pan | improve access to water | water infrustructure |  |  | Mandera West | Dandu | 3.1856 | 40.9656 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6594682 | 6594682 | 6594682 | GOK | N/A | 100 | null | 6594682 | 6594682 | 6594682 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/100/2013-2014 | Construction of Dandu ï¿½ Earth pan | improve access to water | water infrustructure |  |  | Mandera West | Dandu | 3.1856 | 40.9656 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6594682 | 6594682 | 6594682 | GOK | N/A | 100 | null | 6594682 | 6594682 | 6594682 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/255/2013-2014 | Request For Proposal For *Provision Of Engineering Consultancy Services (Ees) For Construction Supervision Of Mandera County Projects | improve infrustructure | consultancy | null | null | Mandera East | Township | 3.9486 | 41.8525 | PUBLIC WORKS | Public Works | PUBLIC WORKS | Public Works | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 9000000 | 25892495 | 25892495 | GOK | N/A | 100 | null | 25892495 | 25892495 | 25892495 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED AUTOMATION OF MANDERA COUNTY REVENUE SYSTEM | PROPOSED AUTOMATION OF MANDERA COUNTY REVENUE SYSTEM | enhance efficiency and productivity | quality service delivery |  | ICT | Mandera East | Township | 3.936 | 41.857 | ICT | ICT | ICT | ICT | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-10 00:00:00+00 | 24676416 | 24676416 | 11000000 | GOK | N/A | 100 | 0 | 24676416 | null | 24676416 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/106/2013-2014 | Construction of Dam at Kamor liban | improve access to water | water infrustructure |  |  | Lafey | Fino | 3.1256 | 40.9056 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6932933 | 6932933 | 6932933 | GOK | N/A | 100 | null | 6932933 | 6932933 | 6932933 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/106/2013-2014 | Construction of Dam at Kamor liban | improve access to water | water infrustructure |  |  | Lafey | Fino | 3.1256 | 40.9056 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6932933 | 6932933 | 6932933 | GOK | N/A | 100 | null | 6932933 | 6932933 | 6932933 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply and Delivery of Funiture for ECD Centres in Banisa Sub- County | Supply and Delivery of Funiture for ECD Centres in Banisa Sub- County | Equiping ECD centres for learning puporses | Facilitates availability of learning equipment | MCG/OT/87/2017-2018 | Operationalization of 13 Wards Offices (Furnitures and Solar) | Banisa | Banisa | null | null | Education | EDUCATION | EDUCATION | EDUCATION | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 24997140 | 24997140 | 9000000 | GOK | N/A | 100 | null | 24997140 | 24997140 | 24997140 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF LAG DIMA DRIFT AT DERKHALE IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF LAG DIMA DRIFT AT DERKHALE IN BANISA SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/052/2023-2024 | null | Banisa | DERKALE | 3.8238 | 40.274 | ROADS | ROADS | ROADS | ROADS | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 9987530 | 9987530 | 8236000 | GOK | N/A | null | null | null | null | 8236000 | null | 1751530 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of Box Culvert at Duse-A3 Road | Construction of Box Culvert at Duse-A3 Road | For drainage purposes and creating water path for the raining seasons | Reduced floodings in the roads during the raining | MCG/OT/076/2017-2018 | null | Mandera East | Khalalio | 3.9038 | 41.6239 | Roads | ROADS | ROADS | ROADS | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 61995040 | 61995040 | 30000000 | GOK | N/A | 100 | null | 61995040 | 61995040 | 61995040 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Desilting Of Aliya Dera Earthpan, Arda Boji Earthpan, Did Kuro Earthpan Damasa Earthpan, Garale Earthpan, Kobadadi South Earthpan | Desilting Of Aliya Dera Earthpan, Arda Boji Earthpan, Did Kuro Earthpan Damasa Earthpan, Garale Earthpan, Kobadadi South Earthpan | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | null | null | Lafey | Lafey | 3.2104 | 41.1784 | WATER SERVICES | Water Services | Water Services | Water Services | 2022-07-13 21:00:00+00 | 2023-03-09 21:00:00+00 | 2023-08-22 21:00:00+00 | 2023-08-22 21:00:00+00 | 13500000 | 13500000 | 13500000 | GOK | N/A | null | null | null | null | 13500000 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Desilting Of Aliya Dera Earthpan, Arda Boji Earthpan, Did Kuro Earthpan Damasa Earthpan, Garale Earthpan, Kobadadi South Earthpan | Desilting Of Aliya Dera Earthpan, Arda Boji Earthpan, Did Kuro Earthpan Damasa Earthpan, Garale Earthpan, Kobadadi South Earthpan | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | null | null | Lafey | Lafey | 3.2104 | 41.1784 | WATER SERVICES | Water Services | Water Services | Water Services | 2022-07-13 21:00:00+00 | 2023-03-09 21:00:00+00 | 2023-08-22 21:00:00+00 | 2023-08-22 21:00:00+00 | 13500000 | 13500000 | 13500000 | GOK | N/A | null | null | null | null | 13500000 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of Earthpan in Lagsure in Mandera west sub county | Proposed construction of Earthpan in Lagsure in Mandera west sub county | improve access to water | water infrustructure | null | null | Mandera West | LAGSURE | 3.1756 | 40.9556 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6838597 | 6838597 | 6838597 | GOK | N/A | 100 | null | 6838597 | 6838597 | 6838597 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of Earthpan in Lagsure in Mandera west sub county | Proposed construction of Earthpan in Lagsure in Mandera west sub county | improve access to water | water infrustructure | null | null | Mandera West | LAGSURE | 3.1756 | 40.9556 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6838597 | 6838597 | 6838597 | GOK | N/A | 100 | null | 6838597 | 6838597 | 6838597 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED FENCING AND SELVING OF SALA MARKET IN LAFEY SUB-COUNTY | PROPOSED FENCING AND SELVING OF SALA MARKET IN LAFEY SUB-COUNTY | boost trade | economic development |  | public works | Mandera East | Lafey | 3.077 | 41.083 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-15 00:00:00+00 | 9095850 | 9095850 | null | GOK | N/A | 100 | 0 | 9095850 | null | 9095850 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/107/2013-2014 | Construction of Dam at Fino | improve access to water | water infrustructure |  |  | Lafey | Fino | 3.1156 | 40.8956 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 7285058 | 7285058 | 7285058 | GOK | N/A | 100 | null | 7285058 | 7285058 | 7285058 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/107/2013-2014 | Construction of Dam at Fino | improve access to water | water infrustructure |  |  | Lafey | Fino | 3.1156 | 40.8956 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 7285058 | 7285058 | 7285058 | GOK | N/A | 100 | null | 7285058 | 7285058 | 7285058 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED DIGITIZATION OF LANDS RECORDS IN MANDERA COUNTY | PROPOSED DIGITIZATION OF LANDS RECORDS IN MANDERA COUNTY | enhance public service | accessibility and social equity |  | lands | Mandera East | Township | 3.936 | 41.857 | Lands | Lands | Lands | Lands | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-26 00:00:00+00 | 9699535 | 9699535 | 10000000 | GOK | N/A | 100 | 0 | 9699535 | null | 9699535 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED RENOVATION WORKS AT ESP RHAMU MARKET STALLS, KITCHEN AND TOILET BLOCK IN MANDERA NORTH SUB-COUNTY. | PROPOSED RENOVATION WORKS AT ESP RHAMU MARKET STALLS, KITCHEN AND TOILET BLOCK IN MANDERA NORTH SUB-COUNTY. | boost trade | economic development |  | public works | Mandera North | Rhamu | 3.935 | 41.222 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-11 00:00:00+00 | 6005951 | 6005951 | 1181264 | GOK | N/A | 100 | 0 | 6005951 | null | 6005951 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF MUNICIPALITY OFFICE BLOCK IN MANDERA EAST | PROPOSED CONSTRUCTION OF MUNICIPALITY OFFICE BLOCK IN MANDERA EAST | enhance public service | accessibility and social equity |  | public works | Mandera East | Township | 3.936 | 41.857 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-09 00:00:00+00 | 59021552 | 59021552 | 40000000 | GOK | N/A | 100 | 0 | 59021552 | null | 59021552 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED DINNING BLOCK AT MANDERA TECHNICAL TRAINING INSTITUTE IN MANDERA EAST SUB COUNTY | PROPOSED DINNING BLOCK AT MANDERA TECHNICAL TRAINING INSTITUTE IN MANDERA EAST SUB COUNTY | promote quality education | human resources development |  | Education | Mandera East | Township | 3.9396 | 41.8612 | Education | EDUCATION | EDUCATION | EDUCATION | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-23 00:00:00+00 | 28979955 | 28979955 | 20000000 | GOK | N/A | 100 | 0 | 28979955 | null | 28979955 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/102/2013-2014 | Construction of Dam at Burmayo | improve access to water | water infrustructure | null | null | Mandera West | Takaba | 3.4911 | 40.1095 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 7445445 | 7445445 | 7445445 | GOK | N/A | 100 | null | 7445445 | 7445445 | 7445445 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/102/2013-2014 | Construction of Dam at Burmayo | improve access to water | water infrustructure | null | null | Mandera West | Takaba | 3.4911 | 40.1095 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 7445445 | 7445445 | 7445445 | GOK | N/A | 100 | null | 7445445 | 7445445 | 7445445 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF WARD OFFICE AND RELATED WORKS AT ASHABITO IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WARD OFFICE AND RELATED WORKS AT ASHABITO IN MANDERA NORTH SUB-COUNTY | improve infrastructure and economic development | QUALITY CONTROL |  | Road/public works | Mandera North | ASHABITO | 3.768 | 41.134 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-09 00:00:00+00 | 7950000 | 7950000 | 7950000 | GOK | N/A | 100 | 0 | 7950000 | null | 7950000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/108/2013-2014 | Construction of Dam at Harbuyo | improve access to water | water infrustructure |  |  | Mandera West | Dandu | 3.1056 | 40.8856 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 7520100 | 7520100 | 7520100 | GOK | N/A | 100 | null | 7520100 | 7520100 | 7520100 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/108/2013-2014 | Construction of Dam at Harbuyo | improve access to water | water infrustructure |  |  | Mandera West | Dandu | 3.1056 | 40.8856 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 7520100 | 7520100 | 7520100 | GOK | N/A | 100 | null | 7520100 | 7520100 | 7520100 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED EXPANSION OF ARDA BOJI EARTHPAN BY 60,000 CUBIC METRE IN MANDERA SOUTH SUB-COUNTY | PROPOSED EXPANSION OF ARDA BOJI EARTHPAN BY 60,000 CUBIC METRE IN MANDERA SOUTH SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera South | null | 4.1165 | 40.3925 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-15 00:00:00+00 | 40004387 | 40004387 | 14000000 | GOK | N/A | 100 | 0 | 40004387 | null | 40004387 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED EXPANSION OF ARDA BOJI EARTHPAN BY 60,000 CUBIC METRE IN MANDERA SOUTH SUB-COUNTY | PROPOSED EXPANSION OF ARDA BOJI EARTHPAN BY 60,000 CUBIC METRE IN MANDERA SOUTH SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera South | null | 4.1165 | 40.3925 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-15 00:00:00+00 | 40004387 | 40004387 | 14000000 | GOK | N/A | 100 | 0 | 40004387 | null | 40004387 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 15,000 CUBIC METRE EARTH PAN AT HARBATE IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF 15,000 CUBIC METRE EARTH PAN AT HARBATE IN MANDERA SOUTH SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera South | WARGADUD | 2.9797 | 40.63 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-08 00:00:00+00 | 9978675 | 9978675 | 9978675 | GOK | N/A | 100 | 0 | 9978675 | null | 9978675 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 15,000 CUBIC METRE EARTH PAN AT HARBATE IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF 15,000 CUBIC METRE EARTH PAN AT HARBATE IN MANDERA SOUTH SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera South | WARGADUD | 2.9797 | 40.63 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-08 00:00:00+00 | 9978675 | 9978675 | 9978675 | GOK | N/A | 100 | 0 | 9978675 | null | 9978675 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSRUCTION OF SECURITY CAMP AT THE NEW COUNTY HEAD QUARTERS IN MANDERA EAST | PROPOSED CONSRUCTION OF SECURITY CAMP AT THE NEW COUNTY HEAD QUARTERS IN MANDERA EAST | Promote security | increased safety |  | Road/public works | Mandera East | Khalalio | 3.936 | 41.857 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-06 00:00:00+00 | 43006826 | 43006826 | 35000000 | GOK | N/A | 100 | 0 | 43006826 | null | 43006826 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT OMAR JILLAOW IN MANDERA EAST SUB-COUNTY WEST | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT OMAR JILLAOW IN MANDERA EAST SUB-COUNTY WEST | promote sustainable water management | clean water |  | water | Mandera East | ARABIA | 3.56 | 41.5 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-02 00:00:00+00 | 14929425 | 14929425 | 15500000 | GOK | N/A | 100 | 0 | 14929425 | null | 14929425 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT OMAR JILLAOW IN MANDERA EAST SUB-COUNTY WEST | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT OMAR JILLAOW IN MANDERA EAST SUB-COUNTY WEST | promote sustainable water management | clean water |  | water | Mandera East | ARABIA | 3.56 | 41.5 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-02 00:00:00+00 | 14929425 | 14929425 | 15500000 | GOK | N/A | 100 | 0 | 14929425 | null | 14929425 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed construction of Earthpan in Kiliweheri in Banisa Sub county | Proposed construction of Earthpan in Kiliweheri in Banisa Sub county | improve access to water | Improve ground infrastructure | null | null | Banisa | Kiliweheri | 3.1556 | 40.9356 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6750000 | 6750000 | 6750000 | GOK | N/A | 100 | null | 6750000 | 6750000 | 6750000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of Earthpan in Kiliweheri in Banisa Sub county | Proposed construction of Earthpan in Kiliweheri in Banisa Sub county | improve access to water | Improve ground infrastructure | null | null | Banisa | Kiliweheri | 3.1556 | 40.9356 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6750000 | 6750000 | 6750000 | GOK | N/A | 100 | null | 6750000 | 6750000 | 6750000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/104/2013-2014 | Construction of Guba Dam | improve access to water | water infrustructure |  |  | Mandera North | Guba | 3.1456 | 40.9256 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 16186432 | 16186432 | 16186432 | GOK | N/A | 100 | null | 16186432 | 16186432 | 16186432 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/104/2013-2014 | Construction of Guba Dam | improve access to water | water infrustructure |  |  | Mandera North | Guba | 3.1456 | 40.9256 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 16186432 | 16186432 | 16186432 | GOK | N/A | 100 | null | 16186432 | 16186432 | 16186432 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/109/2013-2014 | Construction of Dam at Dimu | improve access to water | water infrustructure |  |  | Mandera South | Kutulo | 3.0956 | 40.8756 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6909997 | 6909997 | 6909997 | GOK | N/A | 100 | null | 6909997 | 6909997 | 6909997 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/109/2013-2014 | Construction of Dam at Dimu | improve access to water | water infrustructure |  |  | Mandera South | Kutulo | 3.0956 | 40.8756 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6909997 | 6909997 | 6909997 | GOK | N/A | 100 | null | 6909997 | 6909997 | 6909997 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED MUSEUM HALL AT MANDERA EAST SUB COUNTY | PROPOSED MUSEUM HALL AT MANDERA EAST SUB COUNTY | promote heritage and culture | promote investment |  | heritage | Mandera East | Township | 3.936 | 41.857 | Heritage and culture | Heritage And Culture | Heritage And Culture | Heritage And Culture | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-31 00:00:00+00 | 6000000 | 6000000 | null | GOK | N/A | 100 | 0 | 6000000 | null | 6000000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Supply And Delivery Of Office Furniture For Mandera County Lot2 | Supply And Delivery Of Office Furniture For Mandera County Lot2 | ensure service delivery | effective service delivery |  | finance | Mandera East | Township | 3.936 | 41.857 | financial services | FINANCIAL SERVICES | Financial Services | FINANCIAL SERVICES | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-16 00:00:00+00 | 14853800 | 14853800 | 7000000 | GOK | N/A | 100 | 0 | 14853800 | null | 14853800 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED COMPLETION OF ESP MARKET IN MANDERA TOWN IN MANDERA EAST | PROPOSED COMPLETION OF ESP MARKET IN MANDERA TOWN IN MANDERA EAST | boost trade | economic development |  | public works | Mandera East | Township | 3.936 | 41.857 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-02 00:00:00+00 | 46640923 | 46640923 | 10048096 | GOK | N/A | 100 | 0 | 46640923 | null | 46640923 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Supply And Delivery Of Office Furniture To Office Of The Deputy Governor | Supply And Delivery Of Office Furniture To Office Of The Deputy Governor | to promotequality service delivery |  |  | finance | Mandera East | Township | 3.9361 | 41.86 | financial services | FINANCIAL SERVICES | Financial Services | FINANCIAL SERVICES | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-21 00:00:00+00 | 9936738 | 9936738 | 8000000 | GOK | N/A | 100 | 0 | 9936738 | null | 9936738 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED UPGRADE OF HARSHILMI PRIMARY SCHOOL IN MANDERA WEST SUB COUNTY | PROPOSED UPGRADE OF HARSHILMI PRIMARY SCHOOL IN MANDERA WEST SUB COUNTY | promote quality education | human resources development |  | Education | Mandera West | Dandu | 3.6 | 39.7422 | Education | EDUCATION | EDUCATION | EDUCATION | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-26 00:00:00+00 | 48758616 | 48758616 | null | GOK | N/A | 100 | 0 | 48758616 | null | 48758616 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/105/2013-2014 | Construction of Dam at Alungu | improve access to water | water infrustructure |  |  | Lafey | Alungu | 3.1356 | 40.9156 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6817125 | 6817125 | 6817125 | GOK | N/A | 100 | null | 6817125 | 6817125 | 6817125 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/105/2013-2014 | Construction of Dam at Alungu | improve access to water | water infrustructure |  |  | Lafey | Alungu | 3.1356 | 40.9156 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 6817125 | 6817125 | 6817125 | GOK | N/A | 100 | null | 6817125 | 6817125 | 6817125 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/50/2014-2015 | CONSTRUCTION OF KUTULO DABASITY ROAD | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods |  | Construction of Inter-Ward Roads | Mandera South | Kutulo | 2.8042 | 40.9281 | ROADS | ROADS | ROADS | ROADS | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 280000000 | 274800229.5 | 489029387 | GOK | N/A | 100 | null | 274800230 | 274800230 | 274800230 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/52/2014-2015 | CONSTRUCTION OF DABASITY - ELWAK ROAD | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods |  | Construction of Inter-Ward Roads | Mandera South | Elwak South | 3.0206 | 40.5406 | ROADS | ROADS | ROADS | ROADS | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 145000000 | 144973688 | 100000000 | GOK | N/A | 100 | null | 144973688 | 144973688 | 144973688 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/54/2014-2015 | INSTALLATION OF MOTOR VEHICLE TRACKING AND FLEET MANAGEMENT SYSTEMS - MANDERA TOWN | enhance mobility, operational efficiency, and service delivery | Enhanced operation effeciency |  |  | Mandera East | Township | 3.2006 | 40.9006 | TRASNPORT | TRANSPORT | TRANSPORT | TRANSPORT | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12000000 | 11939401 | 11939401 | GOK | N/A | 100 | null | 11939401 | 11939401 | 11939401 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Executive Office Block At Public Works Compound In Mandera East Sub-County | Proposed Executive Office Block At Public Works Compound In Mandera East Sub-County | providing extra spaces for the executive functions | provides office spaces | MCG/OT/077/2017-2018 | Construction of office block at Works office | Mandera East | Township | 3.9486 | 41.8525 | Public Works | Public Works | PUBLIC WORKS | Public Works | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 53987058 | 53987058 | 12000000 | GOK | N/A | 100 | null | 53987058 | 53987058 | 53987058 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/510/2014-2015 | EQUIPPING AND COMMISSIONING OF BOREHOLES IN DANDU | ï¿½To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | null | Drilling and equiping of Boreholes rehabilited civil works | Mandera West | Dandu | 3.4907 | 39.943 | WATER SERVICES | TRADE | Trade | TRADE | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 35000000 | 34948273 | 95000000 | GOK | N/A | 100 | null | 34948273 | 34948273 | 34948273 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/56/2014-2015 | CONSTRUCTION OF 60,000Mï¿½ EARTH PAN AT DANYERE | ï¿½To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | null | Construction/De-silting of earth Dams and pans | Mandera East | Khalalio | 3.9038 | 41.6239 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 38000000 | 37986583.5 | 47500000 | GOK | N/A | 100 | null | 37986584 | 37986584 | 37986584 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/56/2014-2015 | CONSTRUCTION OF 60,000Mï¿½ EARTH PAN AT DANYERE | ï¿½To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | null | Construction/De-silting of earth Dams and pans | Mandera East | Khalalio | 3.9038 | 41.6239 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 38000000 | 37986583.5 | 47500000 | GOK | N/A | 100 | null | 37986584 | 37986584 | 37986584 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/512/2014-2015 | SUPPLY, INSTALL AND COMMISSIONING OF REVERSE OSMOSIS DESALINATION PLANT FOR ELWAK |  |  |  | Man made lakes and mega dams development Feasibility studies | Mandera South | Elwak South | 3.2506 | 40.9506 | WATER SERVICES | TRADE | Trade | TRADE | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11000000 | 10721530 | 19000000 | GOK | N/A | 100 | null | 10721530 | 10721530 | 10721530 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/524/2014-2015 | RFP FOR PHYSICAL PLANNING AND SURVEYING OF ELWAK AND KUTULO TOWN | improve infrustructure | consultancy |  |  | Mandera South | Kutulo | 2.4063 | 40.596 | LANDS | EDUCATION | EDUCATION | EDUCATION | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 78000000 | 76065540 | 50000000 | GOK | N/A | 100 | null | 76065540 | 76065540 | 76065540 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/530/2014-2015 | CONSTRUCTION OF GARIS DISPENSARY AT GARIS | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community |  | Construction of 6 new dispensaries | Lafey | WARANQARA | 3.4371 | 40.9998 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 13000000 | 11223845.63 | 11223845.63 | GOK | N/A | 100 | null | 11223845.63 | 11223845.63 | 11223845.63 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/279/2014-2015 | Drilling of boreholes in Mandera East Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera East | Township | 3.7813 | 41.3529 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 17899500 | 17899500 | 17899500 | GOK | N/A | 100 | null | 17899500 | 17899500 | 17899500 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/279/2014-2015 | Drilling of boreholes in Mandera East Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera East | Township | 3.7813 | 41.3529 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 17899500 | 17899500 | 17899500 | GOK | N/A | 100 | null | 17899500 | 17899500 | 17899500 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/284/2014-2015 | Construction of 20,000m3 earth pan at Qotqot in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | Guba | 3.0217 | 40.2299 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12540020 | 12540020 | 12540020 | GOK | N/A | 100 | null | 12540020 | 12540020 | 12540020 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/284/2014-2015 | Construction of 20,000m3 earth pan at Qotqot in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | Guba | 3.0217 | 40.2299 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12540020 | 12540020 | 12540020 | GOK | N/A | 100 | null | 12540020 | 12540020 | 12540020 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/294/2014-2015 | Construction of 30,000m3 at Waranqara in Lafey Sub ï¿½ County | improve water access | water infrustructure |  |  | Lafey | WARANQARA | 3.1419 | 40.6084 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 17455429 | 17455428.9 | 17455429 | GOK | N/A | 100 | null | 17455429 | 17455429 | 17455429 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/294/2014-2015 | Construction of 30,000m3 at Waranqara in Lafey Sub ï¿½ County | improve water access | water infrustructure |  |  | Lafey | WARANQARA | 3.1419 | 40.6084 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 17455429 | 17455428.9 | 17455429 | GOK | N/A | 100 | null | 17455429 | 17455429 | 17455429 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/520/2014-2015 | HARDWARE AND SOFTWARE DEVELOPMENT OF COMPUTER AIDED DESIGN AND SOFTWARE | null | software | null | null | Mandera East | Township | 3.9486 | 41.8525 | EDUCATION | EDUCATION | EDUCATION | EDUCATION | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 230000000 | 228591560 | 130000000 | GOK | N/A | 100 | null | 228591560 | 228591560 | 228591560 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED MAINTENANCE OF KILIWEHIRI-BURDURAS ROAD IN KILIWEHIRI SUB COUNTY | PROPOSED MAINTENANCE OF KILIWEHIRI-BURDURAS ROAD IN KILIWEHIRI SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/035/2023-2024 | null | Banisa | Kiliweheri | 3.8602 | 40.2472 | ROADS | ROADS | ROADS | ROADS | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 35052938 | 35052938 | 19052938 | GOK | N/A | null | null | null | null | 19052938 | null | 16000000 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF WARD OFFICE AND RELATED WORKS AT GUBA IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WARD OFFICE AND RELATED WORKS AT GUBA IN MANDERA NORTH SUB-COUNTY | promote infrastructure development |  |  | Road/public works | Mandera North | Rhamu Dimtu | 3.921 | 40.121 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-13 00:00:00+00 | 7995000 | 7995000 | 7995000 | GOK | N/A | 100 | 0 | 7995000 | null | 7995000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/521/2014-2015 | CONSTRUCTION OF KUTULO MARKET | TO promotes the socio?economic development | Job creation & local economic linkages |  |  | Mandera South | Kutulo | 2.4084 | 40.5954 | TRADE | EDUCATION | EDUCATION | EDUCATION | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 19000000 | 17035702 | 17035702 | GOK | N/A | 100 | null | 17035702 | 17035702 | 17035702 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/522/2014-2015 | RFP FOR THE PHYSICAL PLANNING AND SURVEYING OF MANDERA TOWN | improve infrustructure | consultancy |  |  | Mandera East | Township | 3.9254 | 41.8341 | LANDS | EDUCATION | EDUCATION | EDUCATION | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 13000000 | 12000000 | 12000000 | GOK | N/A | 100 | null | 12000000 | 12000000 | 12000000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/275/2014-2015 | Drilling of boreholes in Mandera North Sub ï¿½ County | improve water access | boreholes |  |  | Mandera North | Rhamu | 3.9418 | 41.2321 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 17187700 | 17187700 | 17187700 | GOK | N/A | 100 | null | 17187700 | 17187700 | 17187700 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/275/2014-2015 | Drilling of boreholes in Mandera North Sub ï¿½ County | improve water access | boreholes |  |  | Mandera North | Rhamu | 3.9418 | 41.2321 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 17187700 | 17187700 | 17187700 | GOK | N/A | 100 | null | 17187700 | 17187700 | 17187700 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/276/2014-2015 | Drilling of boreholes in Mandera Sorth Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera South | Elwak South | 2.9053 | 40.7265 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 24996000 | 24996000 | 24996000 | GOK | N/A | 100 | null | 24996000 | 24996000 | 24996000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/276/2014-2015 | Drilling of boreholes in Mandera Sorth Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera South | Elwak South | 2.9053 | 40.7265 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 24996000 | 24996000 | 24996000 | GOK | N/A | 100 | null | 24996000 | 24996000 | 24996000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/516/2014-2015 | RFP FOR ENGINEERING CONSULTANCY FOR DESIGN OF WATER TREATMENT PLANT | TO promotes the socio?economic development | Job creation & local economic linkages | null | Man made lakes and mega dams development Feasibility studies | Mandera East | Township | 3.9486 | 41.8525 | WATER SERVICES | Livestock | Livestock | Livestock | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 32000000 | 31237315.2 | 31237315 | GOK | N/A | 100 | null | 31237315 | 31237315 | 31237315 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/282/2014-2015 | Construction of 30,000m3 earth pan at Kotkoto in Mandera west Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera West | LAGSURE | 3.6124 | 40.3341 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 15057981 | 15057980.7 | 15057981 | GOK | N/A | 100 | null | 15057981 | 15057981 | 15057981 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/282/2014-2015 | Construction of 30,000m3 earth pan at Kotkoto in Mandera west Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera West | LAGSURE | 3.6124 | 40.3341 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 15057981 | 15057980.7 | 15057981 | GOK | N/A | 100 | null | 15057981 | 15057981 | 15057981 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/287/2014-2015 | Construction of 20,000m3 earth pan at Donkhay in Mandera west Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.6289 | 40.3395 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11650341 | 11650340.73 | 11650341 | GOK | N/A | 100 | null | 11650341 | 11650341 | 11650341 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/287/2014-2015 | Construction of 20,000m3 earth pan at Donkhay in Mandera west Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.6289 | 40.3395 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11650341 | 11650340.73 | 11650341 | GOK | N/A | 100 | null | 11650341 | 11650341 | 11650341 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/292/2014-2015 | Construction of 20,000m3 at Diribor pan in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0238 | 40.2335 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12043681 | 12043680.6 | 12043681 | GOK | N/A | 100 | null | 12043681 | 12043681 | 12043681 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/292/2014-2015 | Construction of 20,000m3 at Diribor pan in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0238 | 40.2335 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12043681 | 12043680.6 | 12043681 | GOK | N/A | 100 | null | 12043681 | 12043681 | 12043681 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/297/2014-2015 | Construction of 20,000m3 earth pan at Masho in Mandera west Sub-county | improve water access | water infrustructure |  |  | Mandera West | Gither | 3.6028 | 40.371 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12332715 | 12332715.15 | 12332715 | GOK | N/A | 100 | null | 12332715 | 12332715 | 12332715 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/297/2014-2015 | Construction of 20,000m3 earth pan at Masho in Mandera west Sub-county | improve water access | water infrustructure |  |  | Mandera West | Gither | 3.6028 | 40.371 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12332715 | 12332715.15 | 12332715 | GOK | N/A | 100 | null | 12332715 | 12332715 | 12332715 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/528/2014-2015 | CONSTRUCTION OF OFFICE BLOCK FOR DEPARTMENT OF LIVESTOCK | TO promotes the socio?economic development | Job creation & local economic linkages | null | null | Mandera East | Township | 3.9486 | 41.8525 | LIVESTOCK | Livestock | Livestock | Livestock | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 10000000 | 8490921.6 | 8490922 | GOK | N/A | 100 | null | 8490922 | 8490922 | 8490922 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/523/2014-2015 | RFP FOR PHYSICAL PLANNING AND SURVEYING OF ELWAK AND KUTULO TOWN | improve infrustructure | consultancy | null | null | Mandera South | Elwak South | 2.8929 | 40.8459 | LANDS | EDUCATION | EDUCATION | EDUCATION | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 145000000 | 142957820 | 90000000 | GOK | N/A | 100 | null | 142957820 | 142957820 | 142957820 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/518/2014-2015 | RFP FOR ENGINEERING CONSULTANCY FOR DESIGN AND DEVELOPMENT OF SOLID WASTE | null | null | null | null | Mandera East | Township | 3.9486 | 41.8525 | SOCIAL SERVICES | Social Services | Social Services | Social Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 45000000 | 40916045 | 40916045 | GOK | N/A | 100 | null | 40916045 | 40916045 | 40916045 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/519/2014-2015 | CONSTRUCTION OF 60,000CM EARTH PAN AT FINO IN LAFEY SUB COUNTY | ï¿½To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water |  | Rehabilitation and construction of rural water supplies | Lafey | Fino | null | null | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 16000000 | 14535146.4 | 47000000 | GOK | N/A | 100 | null | 14535146 | 14535146 | 14535146 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/519/2014-2015 | CONSTRUCTION OF 60,000CM EARTH PAN AT FINO IN LAFEY SUB COUNTY | ï¿½To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water |  | Rehabilitation and construction of rural water supplies | Lafey | Fino | null | null | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 16000000 | 14535146.4 | 47000000 | GOK | N/A | 100 | null | 14535146 | 14535146 | 14535146 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/529/2014-2015 | CONSTRUCTION OF DISPENSARY IN GUBA | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community |  | Construction of 6 new dispensaries | Mandera North | Banisa | 3.8624 | 40.4999 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 10000000 | 8490921.6 | 34200000 | GOK | N/A | 100 | null | 8490922 | 8490922 | 8490922 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/278/2014-2015 | Drilling of boreholes in Mandera Lafey Sub ï¿½ County | improve water access | water infrustructure |  |  | Lafey | Lafey | 3.1367 | 40.6021 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 22570500 | 22570500 | 22570500 | GOK | N/A | 100 | null | 22570500 | 22570500 | 22570500 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/278/2014-2015 | Drilling of boreholes in Mandera Lafey Sub ï¿½ County | improve water access | water infrustructure |  |  | Lafey | Lafey | 3.1367 | 40.6021 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 22570500 | 22570500 | 22570500 | GOK | N/A | 100 | null | 22570500 | 22570500 | 22570500 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/283/2014-2015 | Construction of 20,000m3 earth pan at Tarbey in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | DERKALE | 3.0183 | 40.2236 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11662785 | 11662785 | 11662785 | GOK | N/A | 100 | null | 11662785 | 11662785 | 11662785 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/283/2014-2015 | Construction of 20,000m3 earth pan at Tarbey in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | DERKALE | 3.0183 | 40.2236 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11662785 | 11662785 | 11662785 | GOK | N/A | 100 | null | 11662785 | 11662785 | 11662785 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/288/2014-2015 | Construction of 20,0003 at lanqura in Mandera north Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera North | Rhamu | 3.8842 | 41.2053 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12749013 | 12749012.85 | 12749013 | GOK | N/A | 100 | null | 12749013 | 12749013 | 12749013 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/288/2014-2015 | Construction of 20,0003 at lanqura in Mandera north Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera North | Rhamu | 3.8842 | 41.2053 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12749013 | 12749012.85 | 12749013 | GOK | N/A | 100 | null | 12749013 | 12749013 | 12749013 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/293/2014-2015 | Construction of 20,000m3 at Awachosambur pan in Mandera west Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.6337 | 40.3528 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12595989 | 12595989 | 12595989 | GOK | N/A | 100 | null | 12595989 | 12595989 | 12595989 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/293/2014-2015 | Construction of 20,000m3 at Awachosambur pan in Mandera west Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.6337 | 40.3528 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12595989 | 12595989 | 12595989 | GOK | N/A | 100 | null | 12595989 | 12595989 | 12595989 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/298/2014-2015 | Construction of 20,000m3 earth pan at Dobu in Mandera west Sub-county | improve water access | water infrustructure |  |  | Mandera West | Dandu | 3.5944 | 40.3791 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12758786 | 12758786 | 12758786 | GOK | N/A | 100 | null | 12758786 | 12758786 | 12758786 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/298/2014-2015 | Construction of 20,000m3 earth pan at Dobu in Mandera west Sub-county | improve water access | water infrustructure |  |  | Mandera West | Dandu | 3.5944 | 40.3791 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12758786 | 12758786 | 12758786 | GOK | N/A | 100 | null | 12758786 | 12758786 | 12758786 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/280/2014-2015 | Construction of 30,000m3 earth pan at Kabo ii in lafey Sub ï¿½ County | improve water access | water infrustructure |  |  | Lafey | Lafey | 3.1676 | 40.6214 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 22185742 | 22185741.9 | 22185742 | GOK | N/A | 100 | null | 22185742 | 22185742 | 22185742 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/280/2014-2015 | Construction of 30,000m3 earth pan at Kabo ii in lafey Sub ï¿½ County | improve water access | water infrustructure |  |  | Lafey | Lafey | 3.1676 | 40.6214 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 22185742 | 22185741.9 | 22185742 | GOK | N/A | 100 | null | 22185742 | 22185742 | 22185742 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/285/2014-2015 | Construction of 60,000m3 earth pan in Derhkale in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | DERKALE | 3.0461 | 40.2479 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 31671669 | 31671669 | 31671669 | GOK | N/A | 100 | null | 31671669 | 31671669 | 31671669 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/285/2014-2015 | Construction of 60,000m3 earth pan in Derhkale in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | DERKALE | 3.0461 | 40.2479 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 31671669 | 31671669 | 31671669 | GOK | N/A | 100 | null | 31671669 | 31671669 | 31671669 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/290/2014-2015 | Construction of 60,000m3 earth pan at Dandu 4 in Mandera west Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera West | Dandu | 3.6419 | 40.3471 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 34995400 | 34995400 | 34995400 | GOK | N/A | 100 | null | 34995400 | 34995400 | 34995400 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/290/2014-2015 | Construction of 60,000m3 earth pan at Dandu 4 in Mandera west Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera West | Dandu | 3.6419 | 40.3471 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 34995400 | 34995400 | 34995400 | GOK | N/A | 100 | null | 34995400 | 34995400 | 34995400 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/295/2014-2015 | Construction of 20,000m3 earth pan at dayday in Mandera north Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.8726 | 41.196 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 13502654 | 13502654 | 13502654 | GOK | N/A | 100 | null | 13502654 | 13502654 | 13502654 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/295/2014-2015 | Construction of 20,000m3 earth pan at dayday in Mandera north Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.8726 | 41.196 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 13502654 | 13502654 | 13502654 | GOK | N/A | 100 | null | 13502654 | 13502654 | 13502654 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/300/2014-2015 | Construction of 20,000m3 earth pan at Qarsa dima Mandera west- Sub-county | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.5839 | 40.3882 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11870000 | 11870000 | 11870000 | GOK | N/A | 100 | null | 11870000 | 11870000 | 11870000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/300/2014-2015 | Construction of 20,000m3 earth pan at Qarsa dima Mandera west- Sub-county | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.5839 | 40.3882 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11870000 | 11870000 | 11870000 | GOK | N/A | 100 | null | 11870000 | 11870000 | 11870000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/305/2014-2015 | Rehabilitation of Gadudia / banane water supply in Mandera east Sub-County | improve water access | water infrustructure |  |  | Mandera East | Khalalio | 3.7728 | 41.3436 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 5759195 | 5759195 | 5759195 | GOK | N/A | 100 | null | 5759195 | 5759195 | 5759195 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/305/2014-2015 | Rehabilitation of Gadudia / banane water supply in Mandera east Sub-County | improve water access | water infrustructure |  |  | Mandera East | Khalalio | 3.7728 | 41.3436 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 5759195 | 5759195 | 5759195 | GOK | N/A | 100 | null | 5759195 | 5759195 | 5759195 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED REFURBISHMENT AND ADDITIONAL RELATED WORKS TO OLD RHAMU MARKET STALLS IN MANDERA NORTH | PROPOSED REFURBISHMENT AND ADDITIONAL RELATED WORKS TO OLD RHAMU MARKET STALLS IN MANDERA NORTH | boost trade | economic development |  | public works | Mandera North | Rhamu | 3.935 | 41.222 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-07 00:00:00+00 | 7100000 | 7100000 | 6000000 | GOK | N/A | 100 | 0 | 7100000 | null | 7100000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/281/2014-2015 | Construction of 20,000m3 earth pan at Hardawa in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0128 | 40.2148 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11375108 | 11375108 | 11375108 | GOK | N/A | 100 | null | 11375108 | 11375108 | 11375108 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/281/2014-2015 | Construction of 20,000m3 earth pan at Hardawa in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0128 | 40.2148 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11375108 | 11375108 | 11375108 | GOK | N/A | 100 | null | 11375108 | 11375108 | 11375108 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/286/2014-2015 | Construction of 60,000m3 earth pan in Gither in Mandera west Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera West | Gither | 3.6533 | 40.3612 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 31799632 | 31799632 | 31799632 | GOK | N/A | 100 | null | 31799632 | 31799632 | 31799632 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/286/2014-2015 | Construction of 60,000m3 earth pan in Gither in Mandera west Sub ï¿½ County | improve water access | water infrustructure |  |  | Mandera West | Gither | 3.6533 | 40.3612 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 31799632 | 31799632 | 31799632 | GOK | N/A | 100 | null | 31799632 | 31799632 | 31799632 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/291/2014-2015 | Construction of 20,000m3 pan at Ardagarse in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0291 | 40.2419 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 16483037 | 16483036.6 | 16483037 | GOK | N/A | 100 | null | 16483037 | 16483037 | 16483037 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/291/2014-2015 | Construction of 20,000m3 pan at Ardagarse in Banisa Sub ï¿½ County | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0291 | 40.2419 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 16483037 | 16483036.6 | 16483037 | GOK | N/A | 100 | null | 16483037 | 16483037 | 16483037 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/306/2014-2015 | Rehabilitation of Khalaliyo water supply in Mandera east Sub-County | improve water access | water infrustructure |  |  | Mandera East | Khalalio | 3.7851 | 41.3368 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 13838179 | 13838178.5 | 13838179 | GOK | N/A | 100 | null | 13838179 | 13838179 | 13838179 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/306/2014-2015 | Rehabilitation of Khalaliyo water supply in Mandera east Sub-County | improve water access | water infrustructure |  |  | Mandera East | Khalalio | 3.7851 | 41.3368 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 13838179 | 13838178.5 | 13838179 | GOK | N/A | 100 | null | 13838179 | 13838179 | 13838179 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/311/2014-2015 | Rehabilitation of Kutulo water supply in Mandera south Sub-County | improve water access | water infrustructure |  |  | Mandera South | Kutulo | 3.9384 | 40.3329 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 18310011 | 18310011 | 18310011 | GOK | N/A | 100 | null | 18310011 | 18310011 | 18310011 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/311/2014-2015 | Rehabilitation of Kutulo water supply in Mandera south Sub-County | improve water access | water infrustructure |  |  | Mandera South | Kutulo | 3.9384 | 40.3329 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 18310011 | 18310011 | 18310011 | GOK | N/A | 100 | null | 18310011 | 18310011 | 18310011 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/296/2014-2015 | Construction of 20,000m3 earth pan at sukeladhodhay in Mandera west Sub ï¿½ County | improve water access | water infrustructure | null | null | Mandera West | Gither | 3.7055 | 39.954 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12076151 | 12076150.8 | 12076151 | GOK | N/A | 100 | null | 12076151 | 12076151 | 12076151 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/296/2014-2015 | Construction of 20,000m3 earth pan at sukeladhodhay in Mandera west Sub ï¿½ County | improve water access | water infrustructure | null | null | Mandera West | Gither | 3.7055 | 39.954 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12076151 | 12076150.8 | 12076151 | GOK | N/A | 100 | null | 12076151 | 12076151 | 12076151 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/301/2014-2015 | Construction of 20,000m3 earth pan at Gololbia Mandera north- Sub-county | improve water access | water infrustructure | null | null | Mandera North | Guticha | 3.6884 | 40.5974 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12583300 | 12583300 | 12583300 | GOK | N/A | 100 | null | 12583300 | 12583300 | 12583300 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/301/2014-2015 | Construction of 20,000m3 earth pan at Gololbia Mandera north- Sub-county | improve water access | water infrustructure | null | null | Mandera North | Guticha | 3.6884 | 40.5974 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12583300 | 12583300 | 12583300 | GOK | N/A | 100 | null | 12583300 | 12583300 | 12583300 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/299/2014-2015 | Construction of 20,000m3 earth pan at Sheikh barrow lafey Sub-county | improve water access | water infrustructure |  |  | Lafey | Fino | 3.1592 | 40.6298 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12298886 | 12298886 | 12298886 | GOK | N/A | 100 | null | 12298886 | 12298886 | 12298886 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/299/2014-2015 | Construction of 20,000m3 earth pan at Sheikh barrow lafey Sub-county | improve water access | water infrustructure |  |  | Lafey | Fino | 3.1592 | 40.6298 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12298886 | 12298886 | 12298886 | GOK | N/A | 100 | null | 12298886 | 12298886 | 12298886 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF BP1 BORDER PATROL BASE IN MANDERA EAST SUB COUNTY. | PROPOSED CONSTRUCTION OF BP1 BORDER PATROL BASE IN MANDERA EAST SUB COUNTY. | community welfare and icreased safety |  |  | Road/public works | Mandera East | Township | 3.936 | 41.857 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-19 00:00:00+00 | 17208650 | 17208650 | null | GOK | N/A | 100 | 0 | 17208650 | null | 17208650 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/314/2014-2015 | Rehabilitation of Rhamu water supply in Mandera north Sub-County | improve water access | water infrustructure |  |  | Mandera North | Rhamu | 3.9446 | 41.2298 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 21581752 | 21581752 | 21581752 | GOK | N/A | 100 | null | 21581752 | 21581752 | 21581752 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/314/2014-2015 | Rehabilitation of Rhamu water supply in Mandera north Sub-County | improve water access | water infrustructure |  |  | Mandera North | Rhamu | 3.9446 | 41.2298 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 21581752 | 21581752 | 21581752 | GOK | N/A | 100 | null | 21581752 | 21581752 | 21581752 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/319/2014-2015 | Rehabilitation of Arabia water supply in Mandera east Sub-County | improve water access | water infrustructure |  |  | Mandera East | ARABIA | 3.7481 | 41.3746 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12314887 | 12314887 | 12314887 | GOK | N/A | 100 | null | 12314887 | 12314887 | 12314887 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/319/2014-2015 | Rehabilitation of Arabia water supply in Mandera east Sub-County | improve water access | water infrustructure |  |  | Mandera East | ARABIA | 3.7481 | 41.3746 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12314887 | 12314887 | 12314887 | GOK | N/A | 100 | null | 12314887 | 12314887 | 12314887 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/324/2014-2015 | Rehabilitation and upgrading of Alungo water supply, Lafey Sub-County | improve water access | water infrustructure |  |  | Lafey | Fino | 3.1332 | 40.5984 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 9614100 | 9614100 | 9614100 | GOK | N/A | 100 | null | 9614100 | 9614100 | 9614100 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/324/2014-2015 | Rehabilitation and upgrading of Alungo water supply, Lafey Sub-County | improve water access | water infrustructure |  |  | Lafey | Fino | 3.1332 | 40.5984 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 9614100 | 9614100 | 9614100 | GOK | N/A | 100 | null | 9614100 | 9614100 | 9614100 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/331/2014-2015 | Installation of solar powered street lighting ï¿½Rhamu town | improve water access | water infrustructure |  |  | Mandera North | Rhamu | 3.9446 | 41.2298 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 73219000 | 73219000 | 73219000 | GOK | N/A | 100 | null | 73219000 | 73219000 | 73219000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/331/2014-2015 | Installation of solar powered street lighting ï¿½Rhamu town | improve water access | water infrustructure |  |  | Mandera North | Rhamu | 3.9446 | 41.2298 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 73219000 | 73219000 | 73219000 | GOK | N/A | 100 | null | 73219000 | 73219000 | 73219000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/508/2014-2015 | Construction of Darwed Water Supply infrastructure | improve water access | water infrustructure |  |  | Mandera West | LAGSURE | 3.4561 | 40.2586 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 17167608 | 17167608 | 17167608 | GOK | N/A | 100 | null | 17167608 | 17167608 | 17167608 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/508/2014-2015 | Construction of Darwed Water Supply infrastructure | improve water access | water infrustructure |  |  | Mandera West | LAGSURE | 3.4561 | 40.2586 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 17167608 | 17167608 | 17167608 | GOK | N/A | 100 | null | 17167608 | 17167608 | 17167608 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/309/2014-2015 | Rehabilitation of Elele water supply in Mandera south Sub-County | improve water access | water infrustructure | null | null | Mandera South | Elwak South | 2.8929 | 40.8459 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 1260000 | 1260000 | 1260000 | GOK | N/A | 100 | null | 12600 | 12600 | 12600 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/309/2014-2015 | Rehabilitation of Elele water supply in Mandera south Sub-County | improve water access | water infrustructure | null | null | Mandera South | Elwak South | 2.8929 | 40.8459 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 1260000 | 1260000 | 1260000 | GOK | N/A | 100 | null | 12600 | 12600 | 12600 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/307/2014-2015 | Rehabilitation of Kobadadi water supply in Mandera south Sub-County | improve water access | water infrustructure |  |  | Mandera South | Elwak South | 2.9157 | 40.7357 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 6928385 | 6928385 | 6928385 | GOK | N/A | 100 | null | 6928385 | 6928385 | 6928385 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/307/2014-2015 | Rehabilitation of Kobadadi water supply in Mandera south Sub-County | improve water access | water infrustructure |  |  | Mandera South | Elwak South | 2.9157 | 40.7357 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 6928385 | 6928385 | 6928385 | GOK | N/A | 100 | null | 6928385 | 6928385 | 6928385 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/312/2014-2015 | Rehabilitation of Lafey water supply in lafey Sub-County | improve water access | water infrustructure |  |  | Lafey | Lafey | 3.1367 | 40.6021 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 23496160 | 23496160 | 23496160 | GOK | N/A | 100 | null | 23496160 | 23496160 | 23496160 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/312/2014-2015 | Rehabilitation of Lafey water supply in lafey Sub-County | improve water access | water infrustructure |  |  | Lafey | Lafey | 3.1367 | 40.6021 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 23496160 | 23496160 | 23496160 | GOK | N/A | 100 | null | 23496160 | 23496160 | 23496160 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/302/2014-2015 | Rehabilitation of Dadabadadi borehole in Mandera north Sub-County | improve water access | water infrustructure | null | null | Mandera North | Guticha | 3.6884 | 40.5974 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 6521932 | 6521931.9 | 6521932 | GOK | N/A | 100 | null | 6521932 | 6521932 | 6521932 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/302/2014-2015 | Rehabilitation of Dadabadadi borehole in Mandera north Sub-County | improve water access | water infrustructure | null | null | Mandera North | Guticha | 3.6884 | 40.5974 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 6521932 | 6521931.9 | 6521932 | GOK | N/A | 100 | null | 6521932 | 6521932 | 6521932 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/327/2014-2015 | Construction of Sala 11 water supply, Lafey sub county | improve water access | water infrustructure |  |  | Lafey | SALA | 3.1219 | 40.6136 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 16038000 | 16038000 | 16038000 | GOK | N/A | 100 | null | 16038000 | 16038000 | 16038000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/327/2014-2015 | Construction of Sala 11 water supply, Lafey sub county | improve water access | water infrustructure |  |  | Lafey | SALA | 3.1219 | 40.6136 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 16038000 | 16038000 | 16038000 | GOK | N/A | 100 | null | 16038000 | 16038000 | 16038000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/506/2014-2015 | Construction of 60,000m3 earth pan at Merrille in Banisa sub-county | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0196 | 40.2184 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 37896835 | 37896834.5 | 37896835 | GOK | N/A | 100 | null | 37896835 | 37896835 | 37896835 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/506/2014-2015 | Construction of 60,000m3 earth pan at Merrille in Banisa sub-county | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0196 | 40.2184 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 37896835 | 37896834.5 | 37896835 | GOK | N/A | 100 | null | 37896835 | 37896835 | 37896835 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/518/2014-2015 | RFP for Engineering Consultancy Services (ECS) for the Design and Development of Solid Waste Treatment (separations, recycling and Disposal) System for Mandera Town | improve water access | water infrustructure |  |  | Mandera East | Township | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 27000000 | 27000000 | 27000000 | GOK | N/A | 100 | null | 27000000 | 27000000 | 27000000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/518/2014-2015 | RFP for Engineering Consultancy Services (ECS) for the Design and Development of Solid Waste Treatment (separations, recycling and Disposal) System for Mandera Town | improve water access | water infrustructure |  |  | Mandera East | Township | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 27000000 | 27000000 | 27000000 | GOK | N/A | 100 | null | 27000000 | 27000000 | 27000000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/317/2014-2015 | Rehabilitation of Qarsadamu water supply in Mandera south Sub-County | improve water access | water infrustructure | null | null | Mandera South | Shimpir Fatuma | 2.9531 | 40.7521 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 4291000 | 4291000 | 4291000 | GOK | N/A | 100 | null | 4291000 | 4291000 | 4291000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/317/2014-2015 | Rehabilitation of Qarsadamu water supply in Mandera south Sub-County | improve water access | water infrustructure | null | null | Mandera South | Shimpir Fatuma | 2.9531 | 40.7521 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 4291000 | 4291000 | 4291000 | GOK | N/A | 100 | null | 4291000 | 4291000 | 4291000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/303/2014-2015 | Rehabilitation of Banisa water supply in Banisa Sub-County | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0104 | 40.2249 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 27524760 | 27524760 | 27524760 | GOK | N/A | 100 | null | 27524760 | 27524760 | 27524760 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/303/2014-2015 | Rehabilitation of Banisa water supply in Banisa Sub-County | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0104 | 40.2249 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 27524760 | 27524760 | 27524760 | GOK | N/A | 100 | null | 27524760 | 27524760 | 27524760 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
TENDER FOR SUPPLY AND DELIVERY OF ECDE DESKS TO ALL SCHOOLS IN SHIMBIR FATUMA WARD IN MANDERA SOUTH SUB-COUNTY | TENDER FOR SUPPLY AND DELIVERY OF ECDE DESKS TO ALL SCHOOLS IN SHIMBIR FATUMA WARD IN MANDERA SOUTH SUB-COUNTY | promote quality education | human resources development | null | Education | Mandera South | Shimpir Fatuma | 2.381 | 40.907 | Education | EDUCATION | EDUCATION | EDUCATION | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-07 00:00:00+00 | 9938880 | 9938880 | null | GOK | N/A | 100 | null | 9938880 | null | 9938880 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/323/2014-2015 | Improvement of water supply in Warankara, Lafey Sub-County | improve water access | water infrustructure |  |  | Lafey | Alungu | 3.1419 | 40.6084 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11131740 | 11131740 | 11131740 | GOK | N/A | 100 | null | 11131740 | 11131740 | 11131740 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/323/2014-2015 | Improvement of water supply in Warankara, Lafey Sub-County | improve water access | water infrustructure |  |  | Lafey | Alungu | 3.1419 | 40.6084 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11131740 | 11131740 | 11131740 | GOK | N/A | 100 | null | 11131740 | 11131740 | 11131740 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/330/2014-2015 | Installation of solar powered street lighting -Takaba | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.4074 | 40.2231 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 89563992 | 89563992 | 89563992 | GOK | N/A | 100 | null | 89563992 | 89563992 | 89563992 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/330/2014-2015 | Installation of solar powered street lighting -Takaba | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.4074 | 40.2231 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 89563992 | 89563992 | 89563992 | GOK | N/A | 100 | null | 89563992 | 89563992 | 89563992 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/507/2014-2015 | Construction of Water Piping from Darwed to Takaba town | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.4512 | 40.2514 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 20519196 | 20519196 | 20519196 | GOK | N/A | 100 | null | 20519196 | 20519196 | 20519196 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/507/2014-2015 | Construction of Water Piping from Darwed to Takaba town | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.4512 | 40.2514 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 20519196 | 20519196 | 20519196 | GOK | N/A | 100 | null | 20519196 | 20519196 | 20519196 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/511/2014-2015 | Equipping& Commissioning of Darwed Borehole | improve water access | water infrustructure |  |  | Mandera West | LAGSURE | 3.4561 | 40.2586 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 10712520 | 10712520 | 10712520 | GOK | N/A | 100 | null | 10712520 | 10712520 | 10712520 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/511/2014-2015 | Equipping& Commissioning of Darwed Borehole | improve water access | water infrustructure |  |  | Mandera West | LAGSURE | 3.4561 | 40.2586 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 10712520 | 10712520 | 10712520 | GOK | N/A | 100 | null | 10712520 | 10712520 | 10712520 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/313/2014-2015 | Rehabilitation of Libihiya water supply in lafey Sub-County | improve water access | water infrustructure | null | null | Mandera East | Libihiya | 3.1296 | 40.5942 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11600000 | 11600000 | 11600000 | GOK | N/A | 100 | null | 11600000 | 11600000 | 11600000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/313/2014-2015 | Rehabilitation of Libihiya water supply in lafey Sub-County | improve water access | water infrustructure | null | null | Mandera East | Libihiya | 3.1296 | 40.5942 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11600000 | 11600000 | 11600000 | GOK | N/A | 100 | null | 11600000 | 11600000 | 11600000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/308/2014-2015 | Rehabilitation of El-Golicha shallow wells in Mandera south Sub-County | improve water access | water infrustructure | null | null | Mandera South | Elwak South | 2.8929 | 40.8459 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 7450626 | 7450626 | 7450626 | GOK | N/A | 100 | null | 7450626 | 7450626 | 7450626 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/308/2014-2015 | Rehabilitation of El-Golicha shallow wells in Mandera south Sub-County | improve water access | water infrustructure | null | null | Mandera South | Elwak South | 2.8929 | 40.8459 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 7450626 | 7450626 | 7450626 | GOK | N/A | 100 | null | 7450626 | 7450626 | 7450626 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/320/2014-2015 | Rehabilitation of Rhamudimtu water supply in Mandera north Sub-County | improve water access | water infrustructure |  |  | Mandera North | Rhamu Dimtu | 3.9321 | 41.219 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 14174000 | 14174000 | 14174000 | GOK | N/A | 100 | null | 14174000 | 14174000 | 14174000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/320/2014-2015 | Rehabilitation of Rhamudimtu water supply in Mandera north Sub-County | improve water access | water infrustructure |  |  | Mandera North | Rhamu Dimtu | 3.9321 | 41.219 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 14174000 | 14174000 | 14174000 | GOK | N/A | 100 | null | 14174000 | 14174000 | 14174000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/325/2014-2015 | Rhabilitation of Fino water supply, Lafey Sub-County | improve water access | water infrustructure |  |  | Mandera South | WARGADUD | 3.1496 | 40.5794 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 13358775 | 13358775 | 13358775 | GOK | N/A | 100 | null | 13358775 | 13358775 | 13358775 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/325/2014-2015 | Rhabilitation of Fino water supply, Lafey Sub-County | improve water access | water infrustructure |  |  | Mandera South | WARGADUD | 3.1496 | 40.5794 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 13358775 | 13358775 | 13358775 | GOK | N/A | 100 | null | 13358775 | 13358775 | 13358775 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/332/2014-2015 | Installation of solar powered street lighting ï¿½Lafey | improve water access | water infrustructure |  |  | Lafey | Lafey | 3.1367 | 40.6021 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 86502970 | 86502970 | 86502970 | GOK | N/A | 100 | null | 86502970 | 86502970 | 86502970 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/332/2014-2015 | Installation of solar powered street lighting ï¿½Lafey | improve water access | water infrustructure |  |  | Lafey | Lafey | 3.1367 | 40.6021 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 86502970 | 86502970 | 86502970 | GOK | N/A | 100 | null | 86502970 | 86502970 | 86502970 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/509/2014-2015 | Extension of Water from Darwed to Afalo | improve water access | water infrustructure |  |  | null | LAGSURE | 3.4684 | 40.2699 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 14404750 | 14404750 | 14404750 | GOK | N/A | 100 | null | 14404750 | 14404750 | 14404750 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/509/2014-2015 | Extension of Water from Darwed to Afalo | improve water access | water infrustructure |  |  | null | LAGSURE | 3.4684 | 40.2699 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 14404750 | 14404750 | 14404750 | GOK | N/A | 100 | null | 14404750 | 14404750 | 14404750 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/516/2014-2015 | RFP for Engineering Consultancy Services (ECS) for the Design and Development of modern Water Treatment Plant and water quality analysis laboratory for Mandera Urban Water Supply | improve water access | water infrustructure |  |  | Mandera East | Township | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 31237315 | 31237315.2 | 31237315 | GOK | N/A | 100 | null | 31237315 | 31237315 | 31237315 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/516/2014-2015 | RFP for Engineering Consultancy Services (ECS) for the Design and Development of modern Water Treatment Plant and water quality analysis laboratory for Mandera Urban Water Supply | improve water access | water infrustructure |  |  | Mandera East | Township | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 31237315 | 31237315.2 | 31237315 | GOK | N/A | 100 | null | 31237315 | 31237315 | 31237315 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
CONSTRUCTION OF 3NO ECDE CLASSROOMS AND SUPPLY AND DELIVERY OF ECDE MATERIALS FOR MANDERA ECDE TEACHERS TRAINING COLLEGE IN MANDERA EAST | CONSTRUCTION OF 3NO ECDE CLASSROOMS AND SUPPLY AND DELIVERY OF ECDE MATERIALS FOR MANDERA ECDE TEACHERS TRAINING COLLEGE IN MANDERA EAST | null | null | null | Education | Mandera East | Neboi | 3.9621 | 41.7703 | Education | EDUCATION | EDUCATION | EDUCATION | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-09 00:00:00+00 | 15526716 | 15526716 | null | GOK | N/A | 100 | null | 15526716 | null | 15526716 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Equiping Of 3no. Borehole At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | Proposed Equiping Of 3no. Borehole At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | promote sustainable water management | clean water |  | water | Mandera South | Takaba | 3.403 | 40.186 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-22 00:00:00+00 | 30036825 | 30036825 | null | GOK | N/A | 100 | 0 | 30036825 | null | 30036825 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Equiping Of 3no. Borehole At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | Proposed Equiping Of 3no. Borehole At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | promote sustainable water management | clean water |  | water | Mandera South | Takaba | 3.403 | 40.186 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-22 00:00:00+00 | 30036825 | 30036825 | null | GOK | N/A | 100 | 0 | 30036825 | null | 30036825 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/321/2014-2015 | Improvement of water supply system in Shaf-Shafey and Kamor in Mandera East Sub-County | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.7394 | 41.3816 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 39600000 | 39600000 | 39600000 | GOK | N/A | 100 | null | 39600000 | 39600000 | 39600000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/321/2014-2015 | Improvement of water supply system in Shaf-Shafey and Kamor in Mandera East Sub-County | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.7394 | 41.3816 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 39600000 | 39600000 | 39600000 | GOK | N/A | 100 | null | 39600000 | 39600000 | 39600000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/326/2014-2015 | Rehabilitation of Wargadud water supply, Mandera South Sub-County | improve water access | water infrustructure |  |  | Mandera South | WARGADUD | 2.9644 | 40.7616 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 10229971 | 10229971 | 10229971 | GOK | N/A | 100 | null | 10229971 | 10229971 | 10229971 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/326/2014-2015 | Rehabilitation of Wargadud water supply, Mandera South Sub-County | improve water access | water infrustructure |  |  | Mandera South | WARGADUD | 2.9644 | 40.7616 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 10229971 | 10229971 | 10229971 | GOK | N/A | 100 | null | 10229971 | 10229971 | 10229971 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/333/2014-2015 | Installation of solar powered street lighting ï¿½Banisa town | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0104 | 40.2249 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 71150000 | 71150000 | 71150000 | GOK | N/A | 100 | null | 71150000 | 71150000 | 71150000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/333/2014-2015 | Installation of solar powered street lighting ï¿½Banisa town | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0104 | 40.2249 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 71150000 | 71150000 | 71150000 | GOK | N/A | 100 | null | 71150000 | 71150000 | 71150000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/510/2014-2015 | Extension of Water from Darwed to Bulla Mpya in Lagsure Ward | improve water access | water infrustructure |  |  | Mandera West | LAGSURE | 3.4796 | 40.2811 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 34948273 | 34948273 | 34948273 | GOK | N/A | 100 | null | 34948273 | 34948273 | 34948273 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/510/2014-2015 | Extension of Water from Darwed to Bulla Mpya in Lagsure Ward | improve water access | water infrustructure |  |  | Mandera West | LAGSURE | 3.4796 | 40.2811 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 34948273 | 34948273 | 34948273 | GOK | N/A | 100 | null | 34948273 | 34948273 | 34948273 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/517/2014-2015 | RFP for Engineering Consultancy Services (ECS) for the Design and Development of modern Water supply reticulation, automated leak detection &electronic metering and Billing systems for Mandera Urban Water Supply | improve water access | water infrustructure |  |  | Mandera East | Township | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 50887122 | 50887122 | 50887122 | GOK | N/A | 100 | null | 50887122 | 50887122 | 50887122 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/517/2014-2015 | RFP for Engineering Consultancy Services (ECS) for the Design and Development of modern Water supply reticulation, automated leak detection &electronic metering and Billing systems for Mandera Urban Water Supply | improve water access | water infrustructure |  |  | Mandera East | Township | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 50887122 | 50887122 | 50887122 | GOK | N/A | 100 | null | 50887122 | 50887122 | 50887122 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT ALUNGU IN LAFEY SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT ALUNGU IN LAFEY SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Lafey | Lafey | 3.05 | 41.3 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-03 00:00:00+00 | 9998566 | 9998566 | 9998566 | GOK | N/A | 100 | 0 | 9998566 | null | 9998566 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT ALUNGU IN LAFEY SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT ALUNGU IN LAFEY SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Lafey | Lafey | 3.05 | 41.3 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-03 00:00:00+00 | 9998566 | 9998566 | 9998566 | GOK | N/A | 100 | 0 | 9998566 | null | 9998566 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/515/2014-2015 | RFP for Engineering Consultancy Services (ECS) for the Design and Development of modern Sewerage and Drainage Systems for Mandera Town | improve water access | water infrustructure |  |  | Mandera East | Township | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 58800000 | 58800000 | 58800000 | GOK | N/A | 100 | null | 58800000 | 58800000 | 58800000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/515/2014-2015 | RFP for Engineering Consultancy Services (ECS) for the Design and Development of modern Sewerage and Drainage Systems for Mandera Town | improve water access | water infrustructure |  |  | Mandera East | Township | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 58800000 | 58800000 | 58800000 | GOK | N/A | 100 | null | 58800000 | 58800000 | 58800000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Civil Works At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | Proposed Civil Works At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | improve water quality and sanitation | sustainable water management practices |  | water | Mandera South | Takaba | 3.403 | 40.186 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-15 00:00:00+00 | 22945996 | 22945996 | null | GOK | N/A | 100 | 0 | 22945996 | null | 22945996 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Civil Works At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | Proposed Civil Works At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | improve water quality and sanitation | sustainable water management practices |  | water | Mandera South | Takaba | 3.403 | 40.186 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-15 00:00:00+00 | 22945996 | 22945996 | null | GOK | N/A | 100 | 0 | 22945996 | null | 22945996 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Desilting And Expansion Of Qarsa Dima Eath Pan From 20,000m3 ï¿½ 40,000m3 To Mandera West Sub-County | Proposed Desilting And Expansion Of Qarsa Dima Eath Pan From 20,000m3 ï¿½ 40,000m3 To Mandera West Sub-County | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | Dandu | 3.6532 | 39.9773 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-11 00:00:00+00 | 19887462 | 19887462 | null | GOK | N/A | 100 | 0 | 19887462 | null | 19887462 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Desilting And Expansion Of Qarsa Dima Eath Pan From 20,000m3 ï¿½ 40,000m3 To Mandera West Sub-County | Proposed Desilting And Expansion Of Qarsa Dima Eath Pan From 20,000m3 ï¿½ 40,000m3 To Mandera West Sub-County | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | Dandu | 3.6532 | 39.9773 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-11 00:00:00+00 | 19887462 | 19887462 | null | GOK | N/A | 100 | 0 | 19887462 | null | 19887462 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT HAIGURACH IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT HAIGURACH IN BANISA SUB-COUNTY | promote sustainable water management | clean water |  | water | null | null | 3.9403 | 40.4281 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-17 00:00:00+00 | 15450660 | 15450660 | 15500000 | GOK | N/A | 100 | 0 | 15450660 | null | 15450660 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT HAIGURACH IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT HAIGURACH IN BANISA SUB-COUNTY | promote sustainable water management | clean water |  | water | null | null | 3.9403 | 40.4281 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-17 00:00:00+00 | 15450660 | 15450660 | 15500000 | GOK | N/A | 100 | 0 | 15450660 | null | 15450660 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED EXPANSION OF WAKO DADACHA EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF WAKO DADACHA EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | null | water | Mandera South | Kutulo | 2.5481 | 40.7047 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-28 00:00:00+00 | 9686625 | 9686625 | 9686625 | GOK | N/A | 100 | null | 9686625 | null | 9686625 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED EXPANSION OF WAKO DADACHA EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF WAKO DADACHA EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | null | water | Mandera South | Kutulo | 2.5481 | 40.7047 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-28 00:00:00+00 | 9686625 | 9686625 | 9686625 | GOK | N/A | 100 | null | 9686625 | null | 9686625 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT KILIWEHIRI IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT KILIWEHIRI IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | null | water | Banisa | Kiliweheri | 3.876 | 40.533 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-29 00:00:00+00 | 18709801 | 18709801 | 18000000 | GOK | N/A | 100 | null | 18709801 | null | 18709801 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT KILIWEHIRI IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT KILIWEHIRI IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | null | water | Banisa | Kiliweheri | 3.876 | 40.533 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-29 00:00:00+00 | 18709801 | 18709801 | 18000000 | GOK | N/A | 100 | null | 18709801 | null | 18709801 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT KUBDISHAN IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT KUBDISHAN IN MANDERA WEST SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | Mandera West | Takaba | 3.4052 | 40.1034 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-06 00:00:00+00 | 14980140 | 14980140 | 14980140 | GOK | N/A | 100 | 0 | 14980140 | null | 14980140 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT KUBDISHAN IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT KUBDISHAN IN MANDERA WEST SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | Mandera West | Takaba | 3.4052 | 40.1034 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-06 00:00:00+00 | 14980140 | 14980140 | 14980140 | GOK | N/A | 100 | 0 | 14980140 | null | 14980140 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/519/2014-2015 | Construction of 60,000m3 earth pan at Fino in Lafey sub-county | improve water access | water infrustructure |  |  | Lafey | Lafey | 3.1496 | 40.5794 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 40916045 | 40916045 | 40916045 | GOK | N/A | 100 | null | 40916045 | 40916045 | 40916045 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/519/2014-2015 | Construction of 60,000m3 earth pan at Fino in Lafey sub-county | improve water access | water infrustructure |  |  | Lafey | Lafey | 3.1496 | 40.5794 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 40916045 | 40916045 | 40916045 | GOK | N/A | 100 | null | 40916045 | 40916045 | 40916045 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/18/2015-2016 | Proposed Constructions of Road Mandera ï¿½ Khalalio Road to all weather ï¿½murrum standard (28 KM) | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods |  | construction of new inter-constituency and interward Roads | Mandera East | Khalalio | null | null | Roads | ROADS | ROADS | ROADS | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 124178858.6 | 124178859 | 241888000 | GOK | N/A | 100 | null | 124178859 | 124178859 | 124178859 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED MAINTENANCE OF ELWAK-SHIMPIR FATUMA ROAD IN MANDERA SOUTH SUB COUNTY | PROPOSED MAINTENANCE OF ELWAK-SHIMPIR FATUMA ROAD IN MANDERA SOUTH SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/037/2023-2024 | null | Mandera South | Shimpir Fatuma | 2.783 | 40.583 | ROADS | ROADS | ROADS | ROADS | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 39932768 | 39932768 | 25000000 | GOK | N/A | null | null | null | null | 25000000 | null | 14932768 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED EXPANSION OF DHARKEN SADEN EARTH PAN BY 15,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF DHARKEN SADEN EARTH PAN BY 15,000 CUBIC METRE IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | null | water | Banisa | DERKALE | 4.062 | 40.2602 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-03 00:00:00+00 | 9991275 | 9991275 | 9991275 | GOK | N/A | 100 | null | 9991275 | null | 9991275 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED EXPANSION OF DHARKEN SADEN EARTH PAN BY 15,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF DHARKEN SADEN EARTH PAN BY 15,000 CUBIC METRE IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | null | water | Banisa | DERKALE | 4.062 | 40.2602 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-03 00:00:00+00 | 9991275 | 9991275 | 9991275 | GOK | N/A | 100 | null | 9991275 | null | 9991275 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/T/21/2015-2016 | Proposed construction of social Hall in Khalalio, Mandera East | improve infrustructure | Social Hall |  |  | Mandera East | Khalalio | 3.7851 | 41.3368 | Social services | Social Services | Social Services | Social Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 7999398 | 7999398 | 7999398 | GOK | N/A | 100 | null | 7999398 | 7999398 | 7999398 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF MARKET STALLS AT BANISA IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF MARKET STALLS AT BANISA IN BANISA SUB COUNTY | to create retail space and increase sales | low cost entry point and improve spaces for vendors |  | Trade | Banisa | Banisa | null | null | trade | TRADE | Trade | TRADE | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 34932994 | 34932994 | 34932994 | GOK | NA | 100 | 0 | 34932994 | null | 34932994 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
MCG/T/20/2015-2016 | Proposed Construction of Female Hostel at Mandera ECDE college in Mandera East Sub-county | null | Female Hostel built | null | construction of female hostel at MTTC | Mandera East | Neboi | 3.9621 | 41.7703 | Education | EDUCATION | EDUCATION | EDUCATION | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 23750000 | 23750000 | 17644273 | GOK | N/A | 100 | null | 23750000 | 23750000 | 23750000 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Purchase of motor vehicle | Purchase of motor vehicle | To comply with laws, risk managements and financial protections | enhanced well maintained vehicles in the county | null | Purchase of motor Vehicle | Mandera East | Township | 3.9486 | 41.8525 | Public Service | Public Service | Public Service | Public Service | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 10700000 | 10700000 | 18670831 | GOK | N/A | 100 | null | 10700000 | 10700000 | 10700000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/149/2015-2016 | Construction of 20,000M3 Earth Pan at Bidale | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera West | Dandu | 3.2984 | 40.7126 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12240424 | 12240424 | 12240424 | GOK | N/A | 100 | null | 12240424 | 12240424 | 12240424 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/149/2015-2016 | Construction of 20,000M3 Earth Pan at Bidale | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera West | Dandu | 3.2984 | 40.7126 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12240424 | 12240424 | 12240424 | GOK | N/A | 100 | null | 12240424 | 12240424 | 12240424 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/41/2015-2016 | Proposed Construction of Rhamu Dimtu Market, Mandera North | Improvement to social economic of the inhabitant | Sme access to market |  | Construction of Rhamu Dimtu market | Mandera North | Rhamu Dimtu | 3.9521 | 41.2386 | Social services | EDUCATION | EDUCATION | EDUCATION | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 15399410 | 15399410 | 10976000 | GOK | N/A | 100 | null | 15399410 | 15399410 | 15399410 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/27/2015-2016 | Construction of new 60,000m3 Earth Pan at Oda, Mandera East | improve water access | water infrustructure |  |  | Mandera East | ARABIA | 3.5214 | 40.8421 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33384120 | 33384120 | 28000000 | GOK | N/A | 100 | null | 33384120 | 33384120 | 33384120 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/27/2015-2016 | Construction of new 60,000m3 Earth Pan at Oda, Mandera East | improve water access | water infrustructure |  |  | Mandera East | ARABIA | 3.5214 | 40.8421 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33384120 | 33384120 | 28000000 | GOK | N/A | 100 | null | 33384120 | 33384120 | 33384120 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/35/2015-2016 | Construction of new 60,000m3 Earth Pan at Domal, Banisa Sub-County | improve water access | water infrustructure |  |  | Banisa | Malkamari | 3.0286 | 40.2316 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32842950 | 32842950 | 32842950 | GOK | N/A | 100 | null | 32842950 | 32842950 | 32842950 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/35/2015-2016 | Construction of new 60,000m3 Earth Pan at Domal, Banisa Sub-County | improve water access | water infrustructure |  |  | Banisa | Malkamari | 3.0286 | 40.2316 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32842950 | 32842950 | 32842950 | GOK | N/A | 100 | null | 32842950 | 32842950 | 32842950 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/39/2015-2016 | Extension of Water Supply to Morothile | improve water access | water infrustructure |  |  | Mandera North | MOROTHILE | 3.9552 | 41.2451 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10501558 | 10501558 | 10501558 | GOK | N/A | 100 | null | 10501558 | 10501558 | 10501558 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/39/2015-2016 | Extension of Water Supply to Morothile | improve water access | water infrustructure |  |  | Mandera North | MOROTHILE | 3.9552 | 41.2451 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10501558 | 10501558 | 10501558 | GOK | N/A | 100 | null | 10501558 | 10501558 | 10501558 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/47/2015-2016 | Construction of new 60,000m3 Earth Pam at Harshilmi, Mandera West | improve water access | water infrustructure |  |  | Mandera West | Gither | 3.5884 | 40.7126 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11794000 | 11794000 | 11794000 | GOK | N/A | 100 | null | 11794000 | 11794000 | 11794000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/47/2015-2016 | Construction of new 60,000m3 Earth Pam at Harshilmi, Mandera West | improve water access | water infrustructure |  |  | Mandera West | Gither | 3.5884 | 40.7126 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11794000 | 11794000 | 11794000 | GOK | N/A | 100 | null | 11794000 | 11794000 | 11794000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED RENOVATION AND ALTERATION WORKS TO SPECIALIST CLINICS AT MCRH IN MANDERA EAST | PROPOSED RENOVATION AND ALTERATION WORKS TO SPECIALIST CLINICS AT MCRH IN MANDERA EAST | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/027/2023-2024 | null | Mandera East | Neboi | 3.9621 | 41.7703 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 7799156 | 7799156 | 7799156 | GOK | N/A | null | null | null | null | 7799156 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/27/2015-2016 | onstruction of new 60,000m3 Earth Pan at Oda, Mandera East | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera East | ARABIA | 3.5214 | 40.8421 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33384120 | 33384120 | 33384120 | GOK | N/A | 100 | null | 33384120 | 33384120 | 33384120 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/27/2015-2016 | onstruction of new 60,000m3 Earth Pan at Oda, Mandera East | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera East | ARABIA | 3.5214 | 40.8421 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33384120 | 33384120 | 33384120 | GOK | N/A | 100 | null | 33384120 | 33384120 | 33384120 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/37/2015-2016 | Construction of new 60,000m3 Earth Pan in Saikala Tainfa, Mandera North | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | ASHABITO | 3.9246 | 41.2051 | WATER | EDUCATION | EDUCATION | EDUCATION | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32706660 | 32706660 | 25000000 | GOK | N/A | 100 | null | 32706660 | 32706660 | 32706660 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/38/2015-2016 | Construction of 20,000M3 Earth Pan at Domog Ashabito | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | ASHABITO | 3.9196 | 41.2108 | WATER | EDUCATION | EDUCATION | EDUCATION | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10497217.5 | 10497218 | 10497218 | GOK | N/A | 100 | null | 10497218 | 10497218 | 10497218 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/108/2015-2016 | Proposed Construction of Rhamu IDPs Housing Unit 25 No Lot 1 (Re-advertised) | Provision of shelter to displaced internally displaced people | Improveroved living standard |  |  | Mandera North | Rhamu | 3.9446 | 41.2298 | Social services | EDUCATION | EDUCATION | EDUCATION | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 15813750 | 15813750 | 150000000 | GOK | N/A | 100 | null | 15813750 | 15813750 | 15813750 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/114/2015-2016 | Proposed Construction of Rhamu IDPs Housing Unit 25 No Lot 7 (Re-advertised) | Provision of shelter to displaced internally displaced people | Improveroved living standard |  |  | Mandera North | Rhamu | 3.9446 | 41.2298 | Social services | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 16646000 | 16646000 | 16646000 | GOK | N/A | 100 | null | 16646000 | 16646000 | 16646000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/28/2015-2016 | Rehabilitation ,expansion and disilting of Arabia Earth Pan, Mandera East | improve water access | water infrustructure |  |  | Mandera East | ARABIA | 3.7481 | 41.3746 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12800000 | 12800000 | 12800000 | GOK | N/A | 100 | null | 12800000 | 12800000 | 12800000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/28/2015-2016 | Rehabilitation ,expansion and disilting of Arabia Earth Pan, Mandera East | improve water access | water infrustructure |  |  | Mandera East | ARABIA | 3.7481 | 41.3746 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12800000 | 12800000 | 12800000 | GOK | N/A | 100 | null | 12800000 | 12800000 | 12800000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED PAVED PARKING, WALL FINISHING AND GRADING OF MANDERA MOI STADIUM IN MANDERA EAST SUB COUNTY | PROPOSED PAVED PARKING, WALL FINISHING AND GRADING OF MANDERA MOI STADIUM IN MANDERA EAST SUB COUNTY | providing safe and covienent storage to support economic development | reduce vehicles jam and enhance economic | null | Public Works | Mandera East | Township | 3.9486 | 41.8525 | Public Works | Public Works | PUBLIC WORKS | Public Works | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 9700000 | 9700000 | 9700000 | GOK | NA | 100 | null | 9700000 | null | 9700000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
MCG/T/39/2015-2016 | Extension of Water Supply to Morothile | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | MOROTHILE | 3.9552 | 41.2451 | WATER | EDUCATION | EDUCATION | EDUCATION | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10301557.6 | 10301558 | 10301558 | GOK | N/A | 100 | null | 10301558 | 10301558 | 10301558 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/142/2015-2016 | Proposed construction of Gabions measuring 150m x2m x2m at Buno Farm of Shantoley, Mandera North Sub-County | improve water access | water infrustructure |  | Shantoley farming infrustructure | Mandera North | Rhamu | 3.9324 | 41.2226 | AGRICULTURE | Public Service | Public Service | Public Service | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 9504344 | 9504344 | 6860000 | GOK | N/A | 100 | null | 9504344 | 9504344 | 9504344 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/33/2015-2016 | Construction of 20,000M3 Earth Pan at Ban Qayam-Banisa | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0128 | 40.2148 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10453590 | 10453590 | 10453590 | GOK | N/A | 100 | null | 10453590 | 10453590 | 10453590 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/33/2015-2016 | Construction of 20,000M3 Earth Pan at Ban Qayam-Banisa | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.0128 | 40.2148 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10453590 | 10453590 | 10453590 | GOK | N/A | 100 | null | 10453590 | 10453590 | 10453590 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/37/2015-2016 | Construction of new 60,000m3 Earth Pan in SukelaTinfa, Mandera North | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.9186 | 41.1984 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32706660 | 32706660 | 32706660 | GOK | N/A | 100 | null | 32706660 | 32706660 | 32706660 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/37/2015-2016 | Construction of new 60,000m3 Earth Pan in SukelaTinfa, Mandera North | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.9186 | 41.1984 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32706660 | 32706660 | 32706660 | GOK | N/A | 100 | null | 32706660 | 32706660 | 32706660 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/45/2015-2016 | installation of open drip kits with water tank tower and supply of 5000litres plastic water tank at Alati, Mandera West | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.5884 | 40.7126 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33839904 | 33839904 | 33839904 | GOK | N/A | 100 | null | 33839904 | 33839904 | 33839904 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/45/2015-2016 | installation of open drip kits with water tank tower and supply of 5000litres plastic water tank at Alati, Mandera West | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.5884 | 40.7126 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33839904 | 33839904 | 33839904 | GOK | N/A | 100 | null | 33839904 | 33839904 | 33839904 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/50/2015-2016 | Construction of 20,000M3HarrDimtu Earth Pan | improve water access | water infrustructure |  |  | null | Rhamu Dimtu | 3.9484 | 41.2356 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500000 | 10500000 | 10500000 | GOK | N/A | 100 | null | 10500000 | 10500000 | 10500000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/50/2015-2016 | Construction of 20,000M3HarrDimtu Earth Pan | improve water access | water infrustructure |  |  | null | Rhamu Dimtu | 3.9484 | 41.2356 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500000 | 10500000 | 10500000 | GOK | N/A | 100 | null | 10500000 | 10500000 | 10500000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT MURATHELOW IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT MURATHELOW IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | null | null | 4.0426 | 40.4539 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-03 00:00:00+00 | 9999830 | 9999830 | null | GOK | N/A | 100 | 0 | 9999830 | null | 9999830 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT MURATHELOW IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT MURATHELOW IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | null | null | 4.0426 | 40.4539 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-03 00:00:00+00 | 9999830 | 9999830 | null | GOK | N/A | 100 | 0 | 9999830 | null | 9999830 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/T/150/2015-2016 | Construction of 20,000M3 Earth Pan at Damicha | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera West | Takaba | 3.3324 | 40.7421 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500000 | 10500000 | 10500000 | GOK | N/A | 100 | null | 10500000 | 10500000 | 10500000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/150/2015-2016 | Construction of 20,000M3 Earth Pan at Damicha | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera West | Takaba | 3.3324 | 40.7421 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500000 | 10500000 | 10500000 | GOK | N/A | 100 | null | 10500000 | 10500000 | 10500000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/40/2015-2016 | Proposed construction of Dispensary at Kubi, Mandera North | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community |  |  | Mandera North | Rhamu Dimtu | 3.9054 | 41.1986 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 8096800 | 8096800 | 8096800 | GOK | N/A | 100 | null | 8096800 | 8096800 | 8096800 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/26/2015-2016 | Water infrastructure improvement at Bulla Geneva and Tawakal , Mandera East | improve water access | water infrustructure |  |  | Mandera East | Township | 3.7986 | 41.3216 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 13028000 | 13028000 | 13028000 | GOK | N/A | 100 | null | 13028000 | 13028000 | 13028000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/26/2015-2016 | Water infrastructure improvement at Bulla Geneva and Tawakal , Mandera East | improve water access | water infrustructure |  |  | Mandera East | Township | 3.7986 | 41.3216 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 13028000 | 13028000 | 13028000 | GOK | N/A | 100 | null | 13028000 | 13028000 | 13028000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/34/2015-2016 | Construction of 20,000M3 at Urile Earth Pan, Eymole | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.2651 | 40.6624 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10558590 | 10558590 | 10558590 | GOK | N/A | 100 | null | 10558590 | 10558590 | 10558590 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/34/2015-2016 | Construction of 20,000M3 at Urile Earth Pan, Eymole | improve water access | water infrustructure |  |  | Banisa | Banisa | 3.2651 | 40.6624 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10558590 | 10558590 | 10558590 | GOK | N/A | 100 | null | 10558590 | 10558590 | 10558590 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/38/2015-2016 | Construction of 20,000M3 Earth Pan at DomogAshabito | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.9196 | 41.2108 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10497218 | 10497218 | 10497218 | GOK | N/A | 100 | null | 10497218 | 10497218 | 10497218 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/38/2015-2016 | Construction of 20,000M3 Earth Pan at DomogAshabito | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.9196 | 41.2108 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10497218 | 10497218 | 10497218 | GOK | N/A | 100 | null | 10497218 | 10497218 | 10497218 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/46/2015-2016 | Piping of Water Supply to Duduble, Mandera West | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.5712 | 40.6896 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11219040 | 11219040 | 11219040 | GOK | N/A | 100 | null | 11219040 | 11219040 | 11219040 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/46/2015-2016 | Piping of Water Supply to Duduble, Mandera West | improve water access | water infrustructure |  |  | Mandera West | Takaba | 3.5712 | 40.6896 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11219040 | 11219040 | 11219040 | GOK | N/A | 100 | null | 11219040 | 11219040 | 11219040 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/52/2015-2016 | Construction of 20,000M3 Earth Pan at Itlale | improve water access | water infrustructure |  |  | Banisa | Guba | 3.5024 | 40.6726 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33863340 | 33863340 | 33863340 | GOK | N/A | 100 | null | 33863340 | 33863340 | 33863340 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/52/2015-2016 | Construction of 20,000M3 Earth Pan at Itlale | improve water access | water infrustructure |  |  | Banisa | Guba | 3.5024 | 40.6726 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33863340 | 33863340 | 33863340 | GOK | N/A | 100 | null | 33863340 | 33863340 | 33863340 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED COMPLETION OF OPD AT HARSHILMI IN MANDERA WEST SUB COUNTY | PROPOSED COMPLETION OF OPD AT HARSHILMI IN MANDERA WEST SUB COUNTY | provide high accessible, high quality diagonistic, curative service | improve patient flow and reduce wait times |  | Health Services | Mandera West | Dandu | null | null | Health Services | Health Services | Health Services | Health Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 48360306.5 | 48360306.5 | 5000000 | GOK | NA | 100 | 0 | 48360307 | null | 48360307 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
Proposed Completion of Mirra Market in Mandera East Constituency | Proposed Completion of Mirra Market in Mandera East Constituency | Boosting mirra tradings and provinding modern market | Boost mirra business | MCG/OT/73/2017-2018 | Construction of Proposed Miraa Market In Mandera Town | Mandera East | Township | 3.9486 | 41.8525 | Trade | TRADE | Trade | TRADE | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 39032886 | 39032886 | 20161407 | GOK | N/A | 100 | null | 39032886 | 39032886 | 39032886 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT MOROTHILE IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT MOROTHILE IN MANDERA NORTH SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera North | MOROTHILE | 3.798 | 40.982 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-28 00:00:00+00 | 10692750 | 10692750 | 10692750 | GOK | N/A | 100 | 0 | 10692750 | null | 10692750 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT MOROTHILE IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT MOROTHILE IN MANDERA NORTH SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera North | MOROTHILE | 3.798 | 40.982 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-28 00:00:00+00 | 10692750 | 10692750 | 10692750 | GOK | N/A | 100 | 0 | 10692750 | null | 10692750 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/T/49/2015-2016 | Construction of 20,000M3 Earth Pan at Busle, Burduras | improve water access | water infrustructure |  |  | Mandera West | Gither | 3.5224 | 40.6826 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12240424 | 12240424 | 12240424 | GOK | N/A | 100 | null | 12240424 | 12240424 | 12240424 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/49/2015-2016 | Construction of 20,000M3 Earth Pan at Busle, Burduras | improve water access | water infrustructure |  |  | Mandera West | Gither | 3.5224 | 40.6826 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12240424 | 12240424 | 12240424 | GOK | N/A | 100 | null | 12240424 | 12240424 | 12240424 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 13 | Proposed construction of rhamu IDP Phase ll 25NO LOT 13 | enhancing social inclusivity and reducing inequalities within the society | enhanced the overrall well being of the beneficieries | MCG/OT/03/2017/2018 | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18430500 | 18430500 | 18430500 | GOK | N/A | 100 | null | 18430500 | 18430500 | 18430500 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 18 | Proposed construction of rhamu IDP Phase ll 25NO LOT 18 | roviding shelter to the poor and promoting social reintegration and self-belief | enhanced the overrall well being of the beneficieries |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18916207 | 18916207 | 18916207 | GOK | N/A | 100 | null | 18916207 | 18916207 | 18916207 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 23 | Proposed construction of rhamu IDP Phase ll 25NO LOT 23 | promoting sustainable development | it facilitates reintegration of IDPS with other communities |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18270000 | 18270000 | 18270000 | GOK | N/A | 100 | null | 18270000 | 18270000 | 18270000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/32/2015-2016 | Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | improve water access | water infrustructure | null | null | Banisa | DERKALE | 3.0461 | 40.2479 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10881045 | 10881045 | 10881045 | GOK | N/A | 100 | null | 10881045 | 10881045 | 10881045 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/32/2015-2016 | Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | improve water access | water infrustructure | null | null | Banisa | DERKALE | 3.0461 | 40.2479 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10881045 | 10881045 | 10881045 | GOK | N/A | 100 | null | 10881045 | 10881045 | 10881045 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/32/2015-2016 | Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | improve water access | water infrustructure |  |  | Banisa | DERKALE | 3.0461 | 40.2479 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10881045 | 10881045 | 10881045 | GOK | N/A | 100 | null | 10881045 | 10881045 | 10881045 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/32/2015-2016 | Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | improve water access | water infrustructure |  |  | Banisa | DERKALE | 3.0461 | 40.2479 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10881045 | 10881045 | 10881045 | GOK | N/A | 100 | null | 10881045 | 10881045 | 10881045 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/43/2015-2016 | Proposed construction of | improve water access | water infrustructure |  |  | Mandera North | MOROTHILE | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 15871073 | 15871073 | 15871073 | GOK | N/A | 100 | null | 15871073 | 15871073 | 15871073 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/43/2015-2016 | Proposed construction of | improve water access | water infrustructure |  |  | Mandera North | MOROTHILE | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 15871073 | 15871073 | 15871073 | GOK | N/A | 100 | null | 15871073 | 15871073 | 15871073 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/48/2015-2016 | Construction of 20,000M3 in HardaAllo, Mandera West | improve water access | water infrustructure |  |  | Mandera West | Dandu | 3.5624 | 40.6986 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 9999885 | 9999885 | 9999885 | GOK | N/A | 100 | null | 9999885 | 9999885 | 9999885 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/48/2015-2016 | Construction of 20,000M3 in HardaAllo, Mandera West | improve water access | water infrustructure |  |  | Mandera West | Dandu | 3.5624 | 40.6986 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 9999885 | 9999885 | 9999885 | GOK | N/A | 100 | null | 9999885 | 9999885 | 9999885 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/54/2015-2016 | Construction of new 60,000m3 Earth Pan Bambo, Lafey Sub-county | improve water access | water infrustructure |  |  | Lafey | WARANQARA | 3.1186 | 40.5924 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 9851000 | 9851000 | 9851000 | GOK | N/A | 100 | null | 9851000 | 9851000 | 9851000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/54/2015-2016 | Construction of new 60,000m3 Earth Pan Bambo, Lafey Sub-county | improve water access | water infrustructure |  |  | Lafey | WARANQARA | 3.1186 | 40.5924 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 9851000 | 9851000 | 9851000 | GOK | N/A | 100 | null | 9851000 | 9851000 | 9851000 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/61/2015-2016 | Fencing of Waranqara, Bambo&Gari Boreholes | improve water access | water infrustructure |  |  | Lafey | WARANQARA | 3.1419 | 40.6084 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500126 | 10500126 | 10500126 | GOK | N/A | 100 | null | 10500126 | 10500126 | 10500126 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/61/2015-2016 | Fencing of Waranqara, Bambo&Gari Boreholes | improve water access | water infrustructure |  |  | Lafey | WARANQARA | 3.1419 | 40.6084 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500126 | 10500126 | 10500126 | GOK | N/A | 100 | null | 10500126 | 10500126 | 10500126 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT ADA BURUDHI IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT ADA BURUDHI IN MANDERA WEST SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | null | 3.3281 | 40.2727 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-08 00:00:00+00 | 14927588 | 14927588 | 14927588 | GOK | N/A | 100 | 0 | 14927588 | null | 14927588 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT ADA BURUDHI IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT ADA BURUDHI IN MANDERA WEST SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | null | 3.3281 | 40.2727 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-08 00:00:00+00 | 14927588 | 14927588 | 14927588 | GOK | N/A | 100 | 0 | 14927588 | null | 14927588 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed construction of rhamu IDP Phase ll 25NO LOT 12 | Proposed construction of rhamu IDP Phase ll 25NO LOT 12 | promoting sustainable development | Reduce crowding | MCG/OT/04/2017-2018 | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18483575 | 18483575 | 18483575 | GOK | N/A | 100 | null | 18483575 | 18483575 | 18483575 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 14 | Proposed construction of rhamu IDP Phase ll 25NO LOT 14 | To provide affordable housing for the vulnerable people affected by the internal conflicts | improve living conditions by providing shelter | MCG/0T/06/2017-2018 | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18464875 | 18464875 | 300000000 | GOK | N/A | 100 | null | 18464875 | 18464875 | 18464875 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 16 | Proposed construction of rhamu IDP Phase ll 25NO LOT 16 | promoting sustainable development | promote social cohesion and integrity |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18450375 | 18450375 | 18450375 | GOK | N/A | 100 | null | 18450375 | 18450375 | 18450375 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 21 | Proposed construction of rhamu IDP Phase ll 25NO LOT 21 | roviding shelter to the poor and promoting social reintegration and self-belief | promote social cohesion and integrity |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18673750 | 18673750 | 18673750 | GOK | N/A | 100 | null | 18673750 | 18673750 | 18673750 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 26 | Proposed construction of rhamu IDP Phase ll 25NO LOT 26 | roviding shelter to the poor and promoting social reintegration and self-belief | enhanced the overrall well being of the beneficieries |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 11223000 | 11223000 | 11223000 | GOK | N/A | 100 | null | 11223000 | 11223000 | 11223000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of hardimtu dispensary block in mandera west subcounty | Proposed construction of hardimtu dispensary block in mandera west subcounty | Improve Access to Primary Healthcare Services | increased immunizat+F23+E23:K23+E2+E23:O24 | MCG/OT/23/2017-2018 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) | Mandera West | Gither | 3.595 | 40.0693 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 7900296 | 7900296 | 7900296 | GOK | N/A | 100 | null | 7900296 | 7900296 | 7900296 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of irestino dispensary block in irestino | Proposed construction of irestino dispensary block in irestino subcounty | Reduce delays in seeking care (for minor ailments, emergencies). | lowered the number of referals | MCG/OT/28/2017-2018 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) | Mandera West | Dandu | 3.3421 | 39.795 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 7806162 | 7806162 | 7806162 | GOK | N/A | 100 | null | 7806162 | 7806162 | 7806162 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/60/2015-2016 | Water infrastructure improvement in Fino | improve water access | water infrustructure |  |  | Lafey | Fino | 3.1496 | 40.5794 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11900232 | 11900232 | 11900232 | GOK | N/A | 100 | null | 11900232 | 11900232 | 11900232 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/60/2015-2016 | Water infrastructure improvement in Fino | improve water access | water infrustructure |  |  | Lafey | Fino | 3.1496 | 40.5794 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11900232 | 11900232 | 11900232 | GOK | N/A | 100 | null | 11900232 | 11900232 | 11900232 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/64/2015-2016 | Kutulo water supply rehabilitation, Mandera South | improve water access | water infrustructure |  |  | Mandera South | Kutulo | 3.9384 | 40.3329 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33434940 | 33434940 | 33434940 | GOK | N/A | 100 | null | 33434940 | 33434940 | 33434940 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/64/2015-2016 | Kutulo water supply rehabilitation, Mandera South | improve water access | water infrustructure |  |  | Mandera South | Kutulo | 3.9384 | 40.3329 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33434940 | 33434940 | 33434940 | GOK | N/A | 100 | null | 33434940 | 33434940 | 33434940 | null | null | completed | 100 | 0 | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
SUPPLY AND DELIVERY OF DENTAL EQUIPMENT FOR MANDERA COUNTY GOVERNMENT | SUPPLY AND DELIVERY OF DENTAL EQUIPMENT FOR MANDERA COUNTY GOVERNMENT | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/031/2023-2024 | Procurement of Dental/ ENT and Eyes equipment | Mandera East | Neboi | 3.9621 | 41.7703 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 17075853 | 17075853 | 10000000 | GOK | N/A | null | null | null | null | 7537927 | null | 9537926 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 15 | Proposed construction of rhamu IDP Phase ll 25NO LOT 15 | To provide affordable housing for the vulnerable people affected by the internal conflicts | it facilitates reintegration of IDPS with other communities | MCG/OT/07/2017-2018 | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18435010 | 18435010 | 18435010 | GOK | N/A | 100 | null | 18435010 | 18435010 | 18435010 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 20 | Proposed construction of rhamu IDP Phase ll 25NO LOT 20 | enhancing social inclusivity and reducing inequalities within the society | it facilitates reintegration of IDPS with other communities | MCG/OT/12/2017-2018 | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18636879 | 18636879 | 18636879 | GOK | N/A | 100 | null | 18636879 | 18636879 | 18636879 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 25 | Proposed construction of rhamu IDP Phase ll 25NO LOT 25 | roviding shelter to the poor and promoting social reintegration and self-belief | promote sustainable development |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 11173671 | 11173671 | 11173671 | GOK | N/A | 100 | null | 11173671 | 11173671 | 11173671 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of Dandu theatre in mandera west | Proposed construction of Dandu theatre in mandera west | Reduce travel distance/time for residents, especially in remote/nomadic communities. | improved sanitation standard and good well being | MCG/22/2017-2018 | Construction of theater in Dandu | Mandera West | Dandu | 3.4214 | 39.8823 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 36048260 | 36048260 | 23000000 | GOK | N/A | 100 | null | 36048260 | 36048260 | 36048260 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 11 | Proposed construction of rhamu IDP Phase ll 25NO LOT 11 | roviding shelter to the poor and promoting social reintegration and self-belief | promte better neighbourhood and safety |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18742700 | 18742700 | 18742700 | GOK | N/A | 100 | null | 18742700 | 18742700 | 18742700 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 19 | Proposed construction of rhamu IDP Phase ll 25NO LOT 19 | promoting sustainable development | promte better neighbourhood and safety |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18519975 | 18519975 | 18519975 | GOK | N/A | 100 | null | 18519975 | 18519975 | 18519975 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 24 | Proposed construction of rhamu IDP Phase ll 25NO LOT 24 | enhancing social inclusivity and reducing inequalities within the society | promote social cohesion and integrity |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18600020 | 18600020 | 18600020 | GOK | N/A | 100 | null | 18600020 | 18600020 | 18600020 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of bachile dispensary block in mandera east subcounty | Proposed construction of bachile dispensary block in mandera east subcounty | Reduce delays in seeking care (for minor ailments, emergencies). | provide deep healthcare awareness | MCG/OT/21/2017-2018 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) | Mandera West | Takaba | 3.399 | 40.8696 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 7922162 | 7922162 | 35000000 | GOK | N/A | 100 | null | 7922162 | 7922162 | 7922162 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of hullow dispensary block in banisa subcounty | Proposed construction of hullow dispensary block in banisa subcounty | Reduce delays in seeking care (for minor ailments, emergencies). | reduce disease outbreak | MCG/0T/26/2017/2018 |  | Banisa | Malkamari | 4.1836 | 40.803 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 7795200 | 7795200 | 7795200 | GOK | N/A | 100 | null | 7795200 | 7795200 | 7795200 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of fresh water system for mandera refferal hospital in mandera east | Proposed construction of fresh water system for mandera refferal hospital in mandera east | To improve hygienity and cleaniness | improved sanitation standard and good well being | MCG/OT/31/2017-2018 | Drilling of new borehole, piping to MCRH, underground water tank, elavated metalic tank and water reticulation with MCRH | Mandera West | Township | null | null | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 29784386 | 29784386 | 30000000 | GOK | N/A | 100 | null | 29784386 | 29784386 | 29784386 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT OGODE IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT OGODE IN MANDERA WEST SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | Gither | 3.7003 | 40.0804 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-06 00:00:00+00 | 9680475 | 9680475 | 9680475 | GOK | N/A | 100 | 0 | 9680475 | null | 9680475 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT OGODE IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT OGODE IN MANDERA WEST SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | Gither | 3.7003 | 40.0804 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-06 00:00:00+00 | 9680475 | 9680475 | 9680475 | GOK | N/A | 100 | 0 | 9680475 | null | 9680475 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed construction of rhamu IDP Phase ll 25NO LOT 17 | Proposed construction of rhamu IDP Phase ll 25NO LOT 17 | enhancing social inclusivity and reducing inequalities within the society | promote sustainable development |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18441375 | 18441375 | 18441375 | GOK | N/A | 100 | null | 18441375 | 18441375 | 18441375 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 12 | Proposed construction of rhamu IDP Phase ll 25NO LOT 12 | To provide affordable housing for the vulnerable people affected by the internal conflicts | promote sustainable development |  | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18701056 | 18701056 | 18701056 | GOK | N/A | 100 | null | 18701056 | 18701056 | 18701056 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 27 | Proposed construction of rhamu IDP Phase ll 25NO LOT 27 | To provide affordable housing for the vulnerable people affected by the internal conflicts | improve living conditions by providing shelter | MCG/OT/2017-2018 | IDP Housing Programs | Mandera North | Rhamu | 3.9322 | 41.2211 | SPECIAL PROGRAME | special programme | special programme | null | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 13705695 | 13705695 | 13705695 | GOK | N/A | 100 | null | 13705695 | 13705695 | 13705695 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of harwale dispensary block in mandera south subcounty | Proposed construction of harwale dispensary block in mandera south subcounty | Ensure essential services (maternal/child health, immunization,) are available locally. | community engagement | MCG/OT/24/2017-2018 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) | Mandera South | Kutulo | 2.4914 | 40.7762 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 7851599 | 7851599 | 7851599 | GOK | N/A | 100 | null | 7851599 | 7851599 | 7851599 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of elwak sub-county headquarters | Construction of elwak sub-county headquarters | provide centralized locations for subcounty andministrations | provides closer government services | null | Sub-County Headquarter for Elwak Sub-County | Mandera South | Elwak South | 2.8929 | 40.8459 | Devolved unit | Devolved Unit | Devolved Unit | Devolved Unit | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 50172731 | 50172731 | 30000000 | GOK | N/A | 100 | null | 50172731 | 50172731 | 50172731 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT FINCHARO IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT FINCHARO IN MANDERA SOUTH SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera South | Elwak South | 2.93 | 40.5015 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-23 00:00:00+00 | 21961990 | 21961990 | 21961990 | GOK | N/A | 100 | 0 | 21961990 | null | 21961990 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT FINCHARO IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT FINCHARO IN MANDERA SOUTH SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera South | Elwak South | 2.93 | 40.5015 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-23 00:00:00+00 | 21961990 | 21961990 | 21961990 | GOK | N/A | 100 | 0 | 21961990 | null | 21961990 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
proposed construction of 20,000m3 earth pan at chiracha in banisa sub-county | proposed construction of 20,000m3 earth pan at chiracha in banisa sub-county | Providing Water for Domestic Use | Long trekking for water reduced | MCG/OT/40/2017-2018 | construction of 20,000m3 earth pan at Chiracha in Banisa -Sub county | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 9683680 | 9683680 | 10000000 | GOK | N/A | 100 | null | 9683680 | 9683680 | 9683680 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 20,000m3 earth pan at chiracha in banisa sub-county | proposed construction of 20,000m3 earth pan at chiracha in banisa sub-county | Providing Water for Domestic Use | Long trekking for water reduced | MCG/OT/40/2017-2018 | construction of 20,000m3 earth pan at Chiracha in Banisa -Sub county | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 9683680 | 9683680 | 10000000 | GOK | N/A | 100 | null | 9683680 | 9683680 | 9683680 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF KARO AIRPORT (RUN-WAY)IN MANDERA EAST | PROPOSED CONSTRUCTION OF KARO AIRPORT (RUN-WAY)IN MANDERA EAST | Improve Air transport | Air transport infrastrature | null | Road/public works | Mandera East | Township | 3.9486 | 41.8525 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-25 00:00:00+00 | 77175525 | 77175525 | 69000000 | GOK | N/A | 100 | null | null | null | null | null | null | stalled | null | null | null | null | null | null | null | null | null | null | null | null | null | null | null | stalled
Proposed Construction Of Maternity/Delivery Block, Solar Installation, Twin Toiletn At Kutayu Health Centre In Mandera South | Proposed Construction Of Maternity/Delivery Block, Solar Installation, Twin Toiletn At Kutayu Health Centre In Mandera South | Ensure essential services (maternal/child health, immunization, ) are available locally. | provide deep healthcare awareness | MCG/OT/30/2017/2018 | Construction of Kutayu Marternity wing | Mandera West | Takaba | 2.6581 | 40.6861 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 19663879 | 19663879 | 4000000 | GOK | N/A | 100 | null | 19663879 | 19663879 | 19663879 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction of 30,000m3 Earth Pan At Daka Qaresa In Banisa Sub-County | Proposed Construction of 30,000m3 Earth Pan At Daka Qaresa In Banisa Sub-County | Animal Watering , Supplying water for livestock | provides fresh water for domestic use |  | Construction of 30,000m3 earthpan at Daka Qaresa (Banisa Sub-County) | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 16500120 | 16500120 | 15000000 | GOK | N/A | 100 | null | 16500120 | 16500120 | 16500120 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction of 30,000m3 Earth Pan At Daka Qaresa In Banisa Sub-County | Proposed Construction of 30,000m3 Earth Pan At Daka Qaresa In Banisa Sub-County | Animal Watering , Supplying water for livestock | provides fresh water for domestic use |  | Construction of 30,000m3 earthpan at Daka Qaresa (Banisa Sub-County) | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 16500120 | 16500120 | 15000000 | GOK | N/A | 100 | null | 16500120 | 16500120 | 16500120 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed de-silting and expansion of qarsa hama earth pan from 20,000m3 to 50,000m3 in mandera west sub-county | proposed de-silting and expansion of qarsa hama earth pan from 20,000m3 to 50,000m3 in mandera west sub-county | promoting food security and sustainable development | Long trekking for water reduced |  | Construction of 20,000m3 earthpan at Karsa Hama | Mandera West | Dandu | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 14114310 | 14114310 | 10000000 | GOK | N/A | 100 | null | 14114310 | 14114310 | 14114310 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed de-silting and expansion of qarsa hama earth pan from 20,000m3 to 50,000m3 in mandera west sub-county | proposed de-silting and expansion of qarsa hama earth pan from 20,000m3 to 50,000m3 in mandera west sub-county | promoting food security and sustainable development | Long trekking for water reduced |  | Construction of 20,000m3 earthpan at Karsa Hama | Mandera West | Dandu | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 14114310 | 14114310 | 10000000 | GOK | N/A | 100 | null | 14114310 | 14114310 | 14114310 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 20,000m3 earth pan at duse in banisa sub-county | proposed construction of 20,000m3 earth pan at duse in banisa sub-county | Irrigation, Supporting agricultural activities through water harvesting and storage . | Reductions of livestocks movement for water | MCG/OT/51/2017-2018 |  | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 14165760 | 14165760 | 14165760 | GOK | N/A | 100 | null | 14165760 | 14165760 | 14165760 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 20,000m3 earth pan at duse in banisa sub-county | proposed construction of 20,000m3 earth pan at duse in banisa sub-county | Irrigation, Supporting agricultural activities through water harvesting and storage . | Reductions of livestocks movement for water | MCG/OT/51/2017-2018 |  | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 14165760 | 14165760 | 14165760 | GOK | N/A | 100 | null | 14165760 | 14165760 | 14165760 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Banisa | Lafey | null | null | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Banisa | Lafey | null | null | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
Construction of kutulow sub-county headquarters | Construction of kutulow sub-county headquarters | ensuring governance and service delivery to the residents | promote tracking of new infectious disease | MCG/OT/036/2017/2018 | Sub-County Headquarter for kutulo Sub-County | Mandera South | Kutulo | 2.5481 | 40.7047 | Devolved unit | Devolved Unit | Devolved Unit | Devolved Unit | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 40000000 | 40000000 | 30000000 | GOK | N/A | 100 | null | 40000000 | 40000000 | 40000000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed mandera KMTC ( former rest house) boundary wall in mandera east | Proposed mandera KMTC ( former rest house) boundary wall in mandera east | To enhance security of the learners and the entire institution | promote tracking of new infectious disease | MCG/OT/27/2017-2018 | Proposed fencing of Mandera Rest House( Enforcement Office block) | Mandera East | Township | 3.9314 | 41.8478 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 25913646 | 25913646 | 15000000 | GOK | N/A | 100 | null | 25913646 | 25913646 | 25913646 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED EXPANSION OF HARBUYO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | PROPOSED EXPANSION OF HARBUYO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera West | null | 3.4153 | 39.9625 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-07 00:00:00+00 | 9999570 | 9999570 | 9999570 | GOK | N/A | 100 | 0 | 9999570 | null | 9999570 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED EXPANSION OF HARBUYO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | PROPOSED EXPANSION OF HARBUYO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera West | null | 3.4153 | 39.9625 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-07 00:00:00+00 | 9999570 | 9999570 | 9999570 | GOK | N/A | 100 | 0 | 9999570 | null | 9999570 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
proposed construction of hardimtu earth pan of 20,000m3 in mandera west sub-county | proposed construction of hardimtu earth pan of 20,000m3 in mandera west sub-county | reducing the risk of waterborne diseases. | generates revenue to the government | MCG/0T/48/2017-2018 | Construction of 20,000M3 Earth Pna at Hardimtu dams | Mandera West | Gither | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 14128485 | 14128485 | 10000000 | GOK | N/A | 100 | null | 14128485 | 14128485 | 14128485 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of hardimtu earth pan of 20,000m3 in mandera west sub-county | proposed construction of hardimtu earth pan of 20,000m3 in mandera west sub-county | reducing the risk of waterborne diseases. | generates revenue to the government | MCG/0T/48/2017-2018 | Construction of 20,000M3 Earth Pna at Hardimtu dams | Mandera West | Gither | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 14128485 | 14128485 | 10000000 | GOK | N/A | 100 | null | 14128485 | 14128485 | 14128485 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Rehabilitation And Expansion Of Sake Earth Pan From 25,000m3 To 60,000m3 In Mandera West Sub-County | Proposed Rehabilitation And Expansion Of Sake Earth Pan From 25,000m3 To 60,000m3 In Mandera West Sub-County | Improving Livelihoods, by addressing water scarcity challenges. | boost business locally |  | Expansion of the current Sake dam to 60,000M3 (mandera West) | Mandera West | Takaba | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 16755990 | 16755990 | 15000000 | GOK | N/A | 100 | null | 16755990 | 16755990 | 16755990 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Rehabilitation And Expansion Of Sake Earth Pan From 25,000m3 To 60,000m3 In Mandera West Sub-County | Proposed Rehabilitation And Expansion Of Sake Earth Pan From 25,000m3 To 60,000m3 In Mandera West Sub-County | Improving Livelihoods, by addressing water scarcity challenges. | boost business locally |  | Expansion of the current Sake dam to 60,000M3 (mandera West) | Mandera West | Takaba | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 16755990 | 16755990 | 15000000 | GOK | N/A | 100 | null | 16755990 | 16755990 | 16755990 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Banisa | Rhamu | null | null | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Banisa | Rhamu | null | null | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
proposed Mandera nature park current mirra market boundary wall | proposed Mandera nature park current mirra market boundary wall | To prevent intruders, encroachment and enhancing security | Reduced encroachmen+F38+E38:K39+E38:M39+E38:M38 | MCG/OT/38/2017-2018 | null | Mandera East | Township | 3.9486 | 41.8525 | TRADE | TRADE | Trade | TRADE | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 15000000 | 15000000 | 15000000 | GOK | N/A | 100 | null | 15000000 | 15000000 | 15000000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction dispensary block at towfiq in mandera north subcounty | Proposed construction dispensary block at towfiq in mandera north subcounty | Ensure essential services (maternal/child health, immunization) are available locally. | community engagement | MCG/OT/033/2017-2018 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) | Mandera North | Rhamu | 3.8855 | 41.1956 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 7800000 | 7800000 | 7800000 | GOK | N/A | 100 | null | 7800000 | 7800000 | 7800000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed de-silting and expansion of bachile earth pan from 20,000m3 to 50,000m3 | proposed de-silting and expansion of bachile earth pan from 20,000m3 to 50,000m3 | increase water harvestation during the raining seasons | increased the availablility of water | MCG/OT/039/2017-2018 | Expansion of the Current Bachile Dam to 50,000M3 in Mandera West | Mandera West | Takaba | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 16886940 | 16886940 | 17000000 | GOK | N/A | 100 | null | 16886940 | 16886940 | 16886940 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed de-silting and expansion of bachile earth pan from 20,000m3 to 50,000m3 | proposed de-silting and expansion of bachile earth pan from 20,000m3 to 50,000m3 | increase water harvestation during the raining seasons | increased the availablility of water | MCG/OT/039/2017-2018 | Expansion of the Current Bachile Dam to 50,000M3 in Mandera West | Mandera West | Takaba | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 16886940 | 16886940 | 17000000 | GOK | N/A | 100 | null | 16886940 | 16886940 | 16886940 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 30,000m3 earth pan at arda boji in mandera west sub-county | proposed construction of 30,000m3 earth pan at arda boji in mandera west sub-county | Improving Livelihoods, Contributing to the overall wellbeing by addressing water scarcity. | Reduces clan conflict for water | MCG/OT/44/2017-2018 | construction of 30,000M3 at ardha boji (mandera west ) | Mandera West | Takaba | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 16844940 | 16844940 | 15000000 | GOK | N/A | 100 | null | 16844940 | 16844940 | 16844940 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 30,000m3 earth pan at arda boji in mandera west sub-county | proposed construction of 30,000m3 earth pan at arda boji in mandera west sub-county | Improving Livelihoods, Contributing to the overall wellbeing by addressing water scarcity. | Reduces clan conflict for water | MCG/OT/44/2017-2018 | construction of 30,000M3 at ardha boji (mandera west ) | Mandera West | Takaba | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 16844940 | 16844940 | 15000000 | GOK | N/A | 100 | null | 16844940 | 16844940 | 16844940 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED REHABILITATION OF KHALALIO WATER SUPPLY IN MANDERA EAST SUB-COUNTY | PROPOSED REHABILITATION OF KHALALIO WATER SUPPLY IN MANDERA EAST SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera East | Khalalio | 3.933 | 41.828 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-24 00:00:00+00 | 6241484 | 6241484 | 6241484 | GOK | N/A | 100 | 0 | 6241484 | null | 6241484 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED REHABILITATION OF KHALALIO WATER SUPPLY IN MANDERA EAST SUB-COUNTY | PROPOSED REHABILITATION OF KHALALIO WATER SUPPLY IN MANDERA EAST SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera East | Khalalio | 3.933 | 41.828 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-24 00:00:00+00 | 6241484 | 6241484 | 6241484 | GOK | N/A | 100 | 0 | 6241484 | null | 6241484 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
proposed drilling and equiping at towfiq village in mandera north sub-county | proposed drilling and equiping at towfiq village in mandera north sub-county | providing a reliable water source during dry periods | enhances social integrations among communities | MCG/OT/54/2017-2018 | drilling and equiping of a borehole at Towfiq village in Rhamu | Mandera North | Rhamu | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 10088626 | 10088626 | 10111122 | GOK | N/A | 100 | null | 10088626 | 10088626 | 10088626 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed drilling and equiping at towfiq village in mandera north sub-county | proposed drilling and equiping at towfiq village in mandera north sub-county | providing a reliable water source during dry periods | enhances social integrations among communities | MCG/OT/54/2017-2018 | drilling and equiping of a borehole at Towfiq village in Rhamu | Mandera North | Rhamu | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 10088626 | 10088626 | 10111122 | GOK | N/A | 100 | null | 10088626 | 10088626 | 10088626 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of maternity wing at Takaba Hospital in Mandera West | Proposed construction of maternity wing at Takaba Hospital in Mandera West | Ensure essential services (maternal/child health, immunization, nutrition) are available. | increased immunization coverage |  | Construction of maternity in Takaba sub county hospital. | Mandera West | Takaba | 3.3933 | 40.2256 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 65384577 | 65384577 | 23000000 | GOK | N/A | 100 | null | 65384577 | 65384577 | 65384577 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Banisa | Banisa | null | null | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Banisa | Banisa | null | null | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
proposed construction of 30,000m3 earth pan at Didkobain in mandera west sub-county | proposed construction of 30,000m3 earth pan at Didkobain in mandera west sub-county | Irrigation, Supporting agricultural activities through water harvesting and storage . | generates revenue to the government | MCG/OT/42/2017/2018 | construction of 30,000m3 at Diid Kooba (mandera West) | Mandera West | Takaba | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 14900000 | 14900000 | 15500000 | GOK | N/A | 100 | null | 14900000 | 14900000 | 14900000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 30,000m3 earth pan at Didkobain in mandera west sub-county | proposed construction of 30,000m3 earth pan at Didkobain in mandera west sub-county | Irrigation, Supporting agricultural activities through water harvesting and storage . | generates revenue to the government | MCG/OT/42/2017/2018 | construction of 30,000m3 at Diid Kooba (mandera West) | Mandera West | Takaba | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 14900000 | 14900000 | 15500000 | GOK | N/A | 100 | null | 14900000 | 14900000 | 14900000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of arges awara earth pan from 20,000m3 to in mandera west sub-county | proposed construction of arges awara earth pan from 20,000m3 to in mandera west sub-county | Ensuring households have access to safe drinking water | provides fresh water for domestic use | MCG/OT/47/2017-2018 | construction of 20,000m3 earth pan at Argesa Awara in mandera west-Sub county | Mandera West | Dandu | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 13996080 | 13996080 | 10000000 | GOK | N/A | 100 | null | 13996080 | 13996080 | 13996080 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of arges awara earth pan from 20,000m3 to in mandera west sub-county | proposed construction of arges awara earth pan from 20,000m3 to in mandera west sub-county | Ensuring households have access to safe drinking water | provides fresh water for domestic use | MCG/OT/47/2017-2018 | construction of 20,000m3 earth pan at Argesa Awara in mandera west-Sub county | Mandera West | Dandu | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 13996080 | 13996080 | 10000000 | GOK | N/A | 100 | null | 13996080 | 13996080 | 13996080 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 15,000m3 Earth Pan At Sigirso Idda In Mandera West Sub-County | Proposed Construction Of 15,000m3 Earth Pan At Sigirso Idda In Mandera West Sub-County | Climate Resilience by enhancing the county's resilience to climate change. | provides reliable source of income | MCG/OT/52/2017-2018 | Expansion of Sigirso Idda dam | Mandera West | Gither | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 12423390 | 12423390 | 12000000 | GOK | N/A | 100 | null | 12423390 | 12423390 | 12423390 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 15,000m3 Earth Pan At Sigirso Idda In Mandera West Sub-County | Proposed Construction Of 15,000m3 Earth Pan At Sigirso Idda In Mandera West Sub-County | Climate Resilience by enhancing the county's resilience to climate change. | provides reliable source of income | MCG/OT/52/2017-2018 | Expansion of Sigirso Idda dam | Mandera West | Gither | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 12423390 | 12423390 | 12000000 | GOK | N/A | 100 | null | 12423390 | 12423390 | 12423390 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed of Fire station in Mnadera East Sub county | Proposed of Fire station in Mnadera East Sub county | Providing quick and standby services for fire emergency | quick fire extinguish services and available personel |  | Construction of Fire station | Mandera East | Township | 3.9344 | 41.8617 | Public works | Public Works | PUBLIC WORKS | Public Works | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 24359576 | 24359576 | 15000000 | GOK | N/A | 100 | null | 24359576 | 24359576 | 24359576 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 25,000 CUBIC METRE EARTH PAN AT BULLA DIMTU IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 25,000 CUBIC METRE EARTH PAN AT BULLA DIMTU IN MANDERA WEST SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | Mandera West | Dandu | 3.6906 | 39.921 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-12 00:00:00+00 | 14997728 | 14997728 | 14997728 | GOK | N/A | 100 | 0 | 14997728 | null | 14997728 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 25,000 CUBIC METRE EARTH PAN AT BULLA DIMTU IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 25,000 CUBIC METRE EARTH PAN AT BULLA DIMTU IN MANDERA WEST SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | Mandera West | Dandu | 3.6906 | 39.921 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-12 00:00:00+00 | 14997728 | 14997728 | 14997728 | GOK | N/A | 100 | 0 | 14997728 | null | 14997728 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Construction of Takaba - Shimbir Fatuma Road | Construction of Takaba - Shimbir Fatuma Road | Ease transport in the area | Promote business locally | MCG/OT/070/2017-2018 | null | Mandera West | Takaba | 3.4911 | 40.1095 | Roads | ROADS | ROADS | ROADS | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 220141682 | 220141682 | 89000000 | GOK | N/A | 100 | null | 220141682 | 220141682 | 220141682 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Completion Of County Headquarters | Proposed Completion Of County Headquarters | By provinding more spaces and ease accessibility of the county services | creates easy access to government offices | MCG/0T/58/2017-2018 | Completion of County Headquarter | Mandera East | Neboi | 3.9621 | 41.7703 | Devolved unit | Devolved Unit | Devolved Unit | Devolved Unit | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 455354521 | 455354521 | 40000000 | GOK | N/A | 100 | null | 455354521 | 455354521 | 455354521 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed rehabilitation of qolfole earth pan from 30,000m3 to 60,000m3 in mandera west | Proposed rehabilitation of qolfole earth pan from 30,000m3 to 60,000m3 in mandera west | providing a reliable water source during dry periods | increased the availablility of water | MCG/OT/45/2017-2018 | Expansion of the current Qofole Dam to 60,000M3 (mandera West) | Mandera West | Dandu | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 16542960 | 16542960 | 15000000 | GOK | N/A | 100 | null | 16542960 | 16542960 | 16542960 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed rehabilitation of qolfole earth pan from 30,000m3 to 60,000m3 in mandera west | Proposed rehabilitation of qolfole earth pan from 30,000m3 to 60,000m3 in mandera west | providing a reliable water source during dry periods | increased the availablility of water | MCG/OT/45/2017-2018 | Expansion of the current Qofole Dam to 60,000M3 (mandera West) | Mandera West | Dandu | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 16542960 | 16542960 | 15000000 | GOK | N/A | 100 | null | 16542960 | 16542960 | 16542960 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed extension of distribution main for water supply in mandera south sub - county | proposed extension of distribution main for water supply in mandera south sub - county | Animal Watering , Supplying water for livestock. | Reduces clan conflict for water | MCG/OT/50/2017-2018 | construction of 20,000m3 earth pan at Duse in Kutulo-Sub county | Mandera South | Kutulo | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 19703640 | 19703640 | 10000000 | GOK | N/A | 100 | null | 19703640 | 19703640 | 19703640 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed extension of distribution main for water supply in mandera south sub - county | proposed extension of distribution main for water supply in mandera south sub - county | Animal Watering , Supplying water for livestock. | Reduces clan conflict for water | MCG/OT/50/2017-2018 | construction of 20,000m3 earth pan at Duse in Kutulo-Sub county | Mandera South | Kutulo | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 19703640 | 19703640 | 10000000 | GOK | N/A | 100 | null | 19703640 | 19703640 | 19703640 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 60,000m3 Earth Pan At Waranqara In Lafey Sub-County | Proposed Construction Of 60,000m3 Earth Pan At Waranqara In Lafey Sub-County | Irrigation, Supporting agricultural activities through water harvesting and storage . | Reduces clan conflict for water | MCG/OT/55/2017-2018 | construction of 60,000m3 at waranqara (lafey-sub-county) | Lafey | WARANQARA | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 30997890 | 30997890 | 31000000 | GOK | N/A | 100 | null | 30997890 | 30997890 | 30997890 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 60,000m3 Earth Pan At Waranqara In Lafey Sub-County | Proposed Construction Of 60,000m3 Earth Pan At Waranqara In Lafey Sub-County | Irrigation, Supporting agricultural activities through water harvesting and storage . | Reduces clan conflict for water | MCG/OT/55/2017-2018 | construction of 60,000m3 at waranqara (lafey-sub-county) | Lafey | WARANQARA | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 30997890 | 30997890 | 31000000 | GOK | N/A | 100 | null | 30997890 | 30997890 | 30997890 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 30,000m3 Eath Pan At Khalafow In Mandera West Sub-County | Proposed Construction Of 30,000m3 Eath Pan At Khalafow In Mandera West Sub-County | promote sustainable water management | clean water |  | water | Mandera West | Gither | 3.7296 | 39.9202 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-19 00:00:00+00 | 19854629 | 19854629 | null | GOK | N/A | 100 | 0 | 19854629 | null | 19854629 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of 30,000m3 Eath Pan At Khalafow In Mandera West Sub-County | Proposed Construction Of 30,000m3 Eath Pan At Khalafow In Mandera West Sub-County | promote sustainable water management | clean water |  | water | Mandera West | Gither | 3.7296 | 39.9202 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-19 00:00:00+00 | 19854629 | 19854629 | null | GOK | N/A | 100 | 0 | 19854629 | null | 19854629 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
proposed construction of 20,000m3 earth pan at Gagaba in Mandera west sub-county | proposed construction of 20,000m3 earth pan at Gagaba in Mandera west sub-county | Providing Water for Domestic Use | generates revenue to the government |  | Rehabilitation of Gagaba Water pan | Mandera West | Gither | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 12873080 | 12873080 | 12000000 | GOK | N/A | 100 | null | 12873080 | 12873080 | 12873080 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 20,000m3 earth pan at Gagaba in Mandera west sub-county | proposed construction of 20,000m3 earth pan at Gagaba in Mandera west sub-county | Providing Water for Domestic Use | generates revenue to the government |  | Rehabilitation of Gagaba Water pan | Mandera West | Gither | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 12873080 | 12873080 | 12000000 | GOK | N/A | 100 | null | 12873080 | 12873080 | 12873080 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply, Delivery installation testing and commissioning of oxygen plant in at Mandera Refferral Hospital | Supply, Delivery installation testing and commissioning of oxygen plant in at Mandera Refferral Hospital | ensuring consistent supply of oxygen in the hospital | Reduced demands for oxygen from neighbouring counties | null | Oxygen at Mandera County Referral Hospitak | Mandera East | Neboi | 3.9621 | 41.7703 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 23995000 | 23995000 | 8650000 | GOK | N/A | 100 | null | 23995000 | 23995000 | 23995000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT AWAL BANDIRA IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT AWAL BANDIRA IN MANDERA SOUTH SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | Mandera South | null | 3.1125 | 40.8805 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-26 00:00:00+00 | 14949375 | 14949375 | 14949375 | GOK | N/A | 100 | 0 | 14949375 | null | 14949375 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT AWAL BANDIRA IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT AWAL BANDIRA IN MANDERA SOUTH SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | Mandera South | null | 3.1125 | 40.8805 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-26 00:00:00+00 | 14949375 | 14949375 | 14949375 | GOK | N/A | 100 | 0 | 14949375 | null | 14949375 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | For defining proper bounderies and creating cadestral map | provides proper planning | MCG/84/2017/2018 | Land Survey in Mandera Town, Elwak and Kutulo | Mandera South | Kutulo | 3.9254 | 41.8341 | Lands | Lands | Lands | Lands | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 104000000 | 104000000 | 33848655 | GOK | N/A | 100 | null | 104000000 | 104000000 | 104000000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply and Delivery of Enforcement Equipment | Supply and Delivery of Enforcement Equipment | helps enforcements officers to enforce county laws | Helps enforcement officers to performed their duties | MCG/OT/82/2017-2018 | enforcement band equipment | Mandera East | Township | 3.9486 | 41.8525 | Devolved unit | Devolved Unit | Devolved Unit | Devolved Unit | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 22809776 | 22809776 | 2458347 | GOK | N/A | 100 | null | 22809776 | 22809776 | 22809776 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Land Registry Block At Elwak Town In Mandera South Constituency | Proposed Land Registry Block At Elwak Town In Mandera South Constituency | providing storage for land registry | facilitates well stored books and files | MCG/OT/74/2017-2018 | null | Mandera South | Elwak South | 2.8929 | 40.8459 | Lands | Lands | Lands | Lands | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 20500000 | 20500000 | 20500000 | GOK | N/A | 100 | null | 20500000 | 20500000 | 20500000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Routine Maintenance of Warqadud Qoqaqaye Road | Proposed Routine Maintenance of Warqadud Qoqaqaye Road | For easy movement of the residents | Reduced long travelling hours | null | Qoqaye - Wargadud Road | Mandera South | WARGADUD | null | null | Roads | ROADS | ROADS | ROADS | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 19930499 | 19930499 | 2590000 | GOK | N/A | 100 | null | 19930499 | 19930499 | 19930499 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply and Delivery installation testing and commissioning of oxygen plant in at Elwak Refferral Hospital | Supply and Delivery installation testing and commissioning of oxygen plant in at Elwak Refferral Hospital | provision of emergency services by providing suffient oxygen in the hospital | provides available oxygen supply | null | Oxygen plant at Elwak | Mandera South | Elwak South | 2.8929 | 40.8459 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 24269470 | 24269470 | 8650000 | GOK | N/A | 100 | null | 24269470 | 24269470 | 24269470 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of water supply system for mandera technical training institute in mandera east | Proposed construction of water supply system for mandera technical training institute in mandera east | Giving water to the institution for various usage | enhance hygiene and clealinesss | MCG/OT/57/2017-2018 | Extension of water supply system from Neboi to Mandera TTI | Mandera East | Neboi | 3.9621 | 41.7703 | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 19985312 | 19985312 | 20000000 | GOK | N/A | 100 | null | 19985312 | 19985312 | 19985312 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of water supply system for mandera technical training institute in mandera east | Proposed construction of water supply system for mandera technical training institute in mandera east | Giving water to the institution for various usage | enhance hygiene and clealinesss | MCG/OT/57/2017-2018 | Extension of water supply system from Neboi to Mandera TTI | Mandera East | Neboi | 3.9621 | 41.7703 | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 19985312 | 19985312 | 20000000 | GOK | N/A | 100 | null | 19985312 | 19985312 | 19985312 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED DESILTING AND EXPANSION OF BULLA PANGA EARTH PAN TO 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | PROPOSED DESILTING AND EXPANSION OF BULLA PANGA EARTH PAN TO 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water | null | water | Mandera West | Takaba | 3.4911 | 40.1095 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-14 00:00:00+00 | 9992955 | 9992955 | 9992955 | GOK | N/A | 100 | null | 9992955 | null | 9992955 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED DESILTING AND EXPANSION OF BULLA PANGA EARTH PAN TO 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | PROPOSED DESILTING AND EXPANSION OF BULLA PANGA EARTH PAN TO 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water | null | water | Mandera West | Takaba | 3.4911 | 40.1095 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-14 00:00:00+00 | 9992955 | 9992955 | 9992955 | GOK | N/A | 100 | null | 9992955 | null | 9992955 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Mandera Disability Source Centre In Mandera East County | Proposed Mandera Disability Source Centre In Mandera East County | Empowering persons with disabilities and promotig inclusive development | promote social cohesion and integrity | MCG/0T/71/2017-2018 | Persons with disabilities' resource centre | Mandera East | Township | null | null | Social services | Social Services | Social Services | Social Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 24998580 | 24998580 | 12000000 | GOK | N/A | 100 | null | 24998580 | 24998580 | 24998580 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | For defining proper bounderies and creating cadestral map | provides proper planning | MCG/84/2017/2018 | Land Survey in Mandera Town, Elwak and Kutulo | Mandera East | Kutulo | 3.9254 | 41.8341 | Lands | Lands | Lands | Lands | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 104000000 | 104000000 | 33848655 | GOK | N/A | 100 | null | 104000000 | 104000000 | 104000000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | For defining proper bounderies and creating cadestral map | provides proper planning | MCG/84/2017/2018 | Land Survey in Mandera Town, Elwak and Kutulo | Mandera South | Elwak South | 3.9254 | 41.8341 | Lands | Lands | Lands | Lands | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 104000000 | 104000000 | 33848655 | GOK | N/A | 100 | null | 104000000 | 104000000 | 104000000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of mechanical workshop at MTTI | proposed construction of mechanical workshop at MTTI | for learning purposes | well trained mechanical students graduates | null | Mandera Technical Training Institutes 2 workshops | Mandera East | Neboi | 3.9621 | 41.7703 | Education | EDUCATION | EDUCATION | EDUCATION | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 29117814 | 29117814 | 60000000 | GOK | N/A | 100 | null | 29117814 | 29117814 | 29117814 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Completion Of County Guest House | Proposed Completion Of County Guest House | giving accomodations and providing lodging to visitors,offiials and travellers | provides safety,lodging and other related services | MCG/OT/059/20217-2018 | null | Mandera East | Township | 3.9486 | 41.8525 | SPECIAL PROGRAMME | special programme | special programme | special programme | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 308671300 | 308671300 | 140000000 | GOK | N/A | 100 | null | 308671300 | 308671300 | 308671300 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Completion Of County Guest House | Proposed Completion Of County Guest House | giving accomodations and providing lodging to visitors,offiials and travellers | provides safety,lodging and other related services | MCG/OT/059/20217-2018 | null | Mandera East | Township | 3.9486 | 41.8525 | SPECIAL PROGRAMME | special programme | special programme | SPECIAL PROGRAMME | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 308671300 | 308671300 | 140000000 | GOK | N/A | 100 | null | 308671300 | 308671300 | 308671300 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED EXPANSION OF HARCHINI EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF HARCHINI EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | null | null | 3.9442 | 40.3256 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-28 00:00:00+00 | 9991800 | 9991800 | 9991800 | GOK | N/A | 100 | 0 | 9991800 | null | 9991800 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED EXPANSION OF HARCHINI EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF HARCHINI EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | null | null | 3.9442 | 40.3256 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-28 00:00:00+00 | 9991800 | 9991800 | 9991800 | GOK | N/A | 100 | 0 | 9991800 | null | 9991800 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | For defining proper bounderies and creating cadestral map | provides proper planning | MCG/84/2017/2018 | Land Survey in Mandera Town, Elwak and Kutulo | Mandera East | Township | 3.9254 | 41.8341 | Lands | Lands | Lands | Lands | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 104000000 | 104000000 | 33848655 | GOK | N/A | 100 | null | 104000000 | 104000000 | 104000000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply, Delivery installation of solar streets lights in Morrothile Town in Mandera North Sub-county | Supply, Delivery installation of solar streets lights in Morrothile Town in Mandera North Sub-county | enhance security and ease movement during the night | Promote security during the night | MCG/OT/79/2017-2018 | null | Mandera North | MOROTHILE | null | null | Energy | Energy | Energy | Energy | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 19781097 | 19781097 | 19781097 | GOK | N/A | 100 | null | 19781097 | 19781097 | 19781097 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 25,000 CUBIC METRE EARTH PAN AT CHARI FUDA IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF 25,000 CUBIC METRE EARTH PAN AT CHARI FUDA IN MANDERA SOUTH SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera South | Elwak South | 2.8501 | 40.6295 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-10 00:00:00+00 | 13475233 | 13475233 | 13475233 | GOK | N/A | 100 | 0 | 13475233 | null | 13475233 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 25,000 CUBIC METRE EARTH PAN AT CHARI FUDA IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF 25,000 CUBIC METRE EARTH PAN AT CHARI FUDA IN MANDERA SOUTH SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera South | Elwak South | 2.8501 | 40.6295 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-10 00:00:00+00 | 13475233 | 13475233 | 13475233 | GOK | N/A | 100 | 0 | 13475233 | null | 13475233 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT DHARKEN GABA IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT DHARKEN GABA IN MANDERA WEST SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | null | 3.569 | 39.7114 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-26 00:00:00+00 | 19807988 | 19807988 | 19807988 | GOK | N/A | 100 | 0 | 19807988 | null | 19807988 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT DHARKEN GABA IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT DHARKEN GABA IN MANDERA WEST SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | null | 3.569 | 39.7114 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-26 00:00:00+00 | 19807988 | 19807988 | 19807988 | GOK | N/A | 100 | 0 | 19807988 | null | 19807988 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Mandera Rehabilitation Centre in Mandera East Constituency | Proposed Mandera Rehabilitation Centre in Mandera East Constituency | providing person centered care by providing rehab interventions to each individals needs | Reduced meltal health problems | null | null | Mandera East | Township | 3.9486 | 41.8525 | Social services | Social Services | Social Services | Social Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 44582615 | 44582615 | 20000000 | GOK | N/A | 100 | null | 44582615 | 44582615 | 44582615 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF RENAL UNITS AT ELWAK SUB COUNTY HOSPITAL IN MANDERA SOUTH | PROPOSED CONSTRUCTION OF RENAL UNITS AT ELWAK SUB COUNTY HOSPITAL IN MANDERA SOUTH | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/029/2023-2024 | Proposed Construction Of Renal Units at Elwak Sub County Hospital In Mandera South | Mandera South | Elwak South | 2.8929 | 40.8459 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 12416812 | 12416812 | 5000000 | GOK | N/A | null | null | null | null | 12416812 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Alteration and Demolitions for Kutulo Hospital and Anciliary Works In Kutulo Sub-County | Proposed Alteration and Demolitions for Kutulo Hospital and Anciliary Works In Kutulo Sub-County | for structural modifications | promote safety and modernization of the building | MCG/OT/83/2017-2018 | Repair and Renovation of Kutulo District Hospital | Mandera South | Kutulo | 2.4453 | 40.6522 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 7906525 | 7906525 | 12000000 | GOK | N/A | 100 | null | 7906525 | 7906525 | 7906525 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | For defining proper bounderies and creating cadestral map | provides proper planning | MCG/84/2017/2018 | Land Survey in Mandera Town, Elwak and Kutulo | Mandera South | Township | 3.9254 | 41.8341 | Lands | Lands | Lands | Lands | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 104000000 | 104000000 | 33848655 | GOK | N/A | 100 | null | 104000000 | 104000000 | 104000000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT SACHGODOM IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT SACHGODOM IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | null | null | 3.9442 | 40.3256 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-07 00:00:00+00 | 14860440 | 14860440 | 14860440 | GOK | N/A | 100 | 0 | 14860440 | null | 14860440 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT SACHGODOM IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT SACHGODOM IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | water | null | null | 3.9442 | 40.3256 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-07 00:00:00+00 | 14860440 | 14860440 | 14860440 | GOK | N/A | 100 | 0 | 14860440 | null | 14860440 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT HAMASA IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT HAMASA IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera West | null | 3.2968 | 40.4344 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-23 00:00:00+00 | 10097640 | 10097640 | 10097640 | GOK | N/A | 100 | 0 | 10097640 | null | 10097640 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT HAMASA IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT HAMASA IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera West | null | 3.2968 | 40.4344 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-23 00:00:00+00 | 10097640 | 10097640 | 10097640 | GOK | N/A | 100 | 0 | 10097640 | null | 10097640 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN BANISA SUB COUNTY | accessibility and social equity | null | null | public works | Banisa | Banisa | 3.944 | 40.326 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-03 00:00:00+00 | 5250000 | 5250000 | 5250000 | GOK | N/A | 100 | null | 5250000 | null | 5250000 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Design, construct, supply, deliver, installation and commisioning of Radiology unit at Takaba referral hospital in mandera west | Design, construct, supply, deliver, installation and commisioning of Radiology unit at Takaba referral hospital in mandera west | improving health and preventing diseases | healthy lifestyle |  | health | Mandera West | Takaba | 3.403 | 40.186 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-22 00:00:00+00 | 29744968 | 29744968 | 29000000 | GOK | N/A | 100 | 0 | 29744968 | null | 29744968 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | For defining proper bounderies and creating cadestral map | provides proper planning | MCG/84/2017/2018 | Land Survey in Mandera Town, Elwak and Kutulo | Mandera East | Elwak South | 3.9254 | 41.8341 | Lands | Lands | Lands | Lands | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 104000000 | 104000000 | 33848655 | GOK | N/A | 100 | null | 104000000 | 104000000 | 104000000 | null | null | completed | null | null | N/A | N/A | null | null | FALSE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of Electrical workshop at MTTI | Proposed construction of Electrical workshop at MTTI | for learning purposes | productions of local electrical technicians | null | Mandera Technical Training Institutes 2 workshops | Mandera East | Neboi | 3.9621 | 41.7703 | Education | EDUCATION | EDUCATION | EDUCATION | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 29064716 | 29064716 | 29064716 | GOK | N/A | 100 | null | 29064716 | 29064716 | 29064716 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Lafey | Lafey | null | null | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Lafey | Lafey | null | null | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Lafey | Rhamu | null | null | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Lafey | Rhamu | null | null | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Lafey | Banisa | null | null | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Lafey | Banisa | null | null | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Mandera North | Lafey | null | null | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Mandera North | Lafey | null | null | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Mandera North | Rhamu | null | null | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Mandera North | Rhamu | null | null | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Mandera North | Banisa | null | null | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Special programme | Mandera North | Banisa | null | null | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31578912 | 31578912 | 31578912 | GOK | NA | 100 | 0 | 31578912 | null | 31578912 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED COMPLETION OF HARSHILMI MORDERN PRIMARY SCHOOL IN MANDERA WEST SUB COUNTY | PROPOSED COMPLETION OF HARSHILMI MORDERN PRIMARY SCHOOL IN MANDERA WEST SUB COUNTY | improve access to quality education | increase enrolment and ensure universal education |  | Education | Mandera West | Dandu | null | null | Education | EDUCATION | EDUCATION | EDUCATION | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 38846312 | 38846312 | 5000000 | GOK | NA | 100 | 0 | 38846312 | null | 38846312 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED REPAIR AND MAINTENANCE OF ACCIDENT AND EMERGENCY CENTRES AND MATERNITY CENTRES AT MCRH AND ELWAK REFERRAL HOSPITALS IN MANDERA COUNTY | PROPOSED REPAIR AND MAINTENANCE OF ACCIDENT AND EMERGENCY CENTRES AND MATERNITY CENTRES AT MCRH AND ELWAK REFERRAL HOSPITALS IN MANDERA COUNTY | preventing harm and maintaining safe environment for both patient and hospital staff | maximizing longativity and reducing unplanned cost |  | Health | Mandera East | Elwak South | null | null | Health Services | Health Services | Health Services | Health Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31793802 | 31793802 | 14000000 | GOK | NA | 100 | 0 | 31793802 | null | 31793802 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT GARSESALA IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT GARSESALA IN MANDERA SOUTH SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera South | SALA | 3.077 | 41.083 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-17 00:00:00+00 | 10101244 | 10101244 | 10101244 | GOK | N/A | 100 | 0 | 10101244 | null | 10101244 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT GARSESALA IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT GARSESALA IN MANDERA SOUTH SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera South | SALA | 3.077 | 41.083 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-17 00:00:00+00 | 10101244 | 10101244 | 10101244 | GOK | N/A | 100 | 0 | 10101244 | null | 10101244 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF CELLED DRIFT AT DANDU HOSPITAL ACCESS ROAD IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF CELLED DRIFT AT DANDU HOSPITAL ACCESS ROAD IN MANDERA WEST SUB COUNTY | resource management | improve water security |  | Health | Mandera West | Dandu | null | null | Health Services | Health Services | Health Services | Health Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 15218040 | 15218040 | 10000000 | GOK | NA | 100 | 0 | 15218040 | null | 15218040 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
Supply, Delivery, Installation And Commissioning Of 250 Kva At Elwak Referral Hospital In Mandera South Sub-County | Supply, Delivery, Installation And Commissioning Of 250 Kva At Elwak Referral Hospital In Mandera South Sub-County | improving health and preventing diseases | healthy lifestyle |  | health | Mandera South | Elwak South | 2.808 | 40.926 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-17 00:00:00+00 | 12900000 | 12900000 | 12900000 | GOK | N/A | 100 | 0 | 12900000 | null | 12900000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Supply, Delivery And Installation Of Medical Equipment To Accident And Imergency Unit At Mandera County Refferal And Elwak Hospital | Supply, Delivery And Installation Of Medical Equipment To Accident And Imergency Unit At Mandera County Refferal And Elwak Hospital | improving health and preventing diseases | healthy lifestyle |  | health | Mandera South | Elwak South | 3.936 | 41.857 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-12 00:00:00+00 | 74008680 | 74008680 | 74008680 | GOK | N/A | 100 | 0 | 74008680 | null | 74008680 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
SUPPLY AND DELIVERY OF ICT EQUIPMENT AND SOFTWARES FOR PUBLIC WORKS | SUPPLY AND DELIVERY OF ICT EQUIPMENT AND SOFTWARES FOR PUBLIC WORKS | improve office comunication and data management | boast efficiency and productivity |  | Public Works | Mandera East | Township | null | null | Public Works | Public Works | PUBLIC WORKS | Public Works | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 10200025 | 10200025 | 10200025 | GOK | NA | 100 | 0 | 10200025 | null | 10200025 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED REPAIR AND MAINTENANCE OF ACCIDENT AND EMERGENCY CENTRES AND MATERNITY CENTRES AT MCRH AND ELWAK REFERRAL HOSPITALS IN MANDERA COUNTY | PROPOSED REPAIR AND MAINTENANCE OF ACCIDENT AND EMERGENCY CENTRES AND MATERNITY CENTRES AT MCRH AND ELWAK REFERRAL HOSPITALS IN MANDERA COUNTY | preventing harm and maintaining safe environment for both patient and hospital staff | maximizing longativity and reducing unplanned cost |  | Health | Mandera South | Township | null | null | Health Services | Health Services | Health Services | Health Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31793802 | 31793802 | 14000000 | GOK | NA | 100 | 0 | 31793802 | null | 31793802 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF DISPENSARY AT BOJI GARSE IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF DISPENSARY AT BOJI GARSE IN MANDERA SOUTH SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera South | null | 3.9459 | 41.541 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-12 00:00:00+00 | 9123415 | 9123415 | 9123415 | GOK | N/A | 100 | 0 | 9123415 | null | 9123415 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF DISPENSARY AT KAMOR ELLE IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF DISPENSARY AT KAMOR ELLE IN MANDERA EAST SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera East | Township | 3.9251 | 41.8543 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-19 00:00:00+00 | 7682400 | 7682400 | 7682400 | GOK | N/A | 100 | 0 | 7682400 | null | 7682400 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Supply and Delivery of Funiture for ECD Centres in Banisa Sub- County | Supply and Delivery of Funiture for ECD Centres in Banisa Sub- County | Equiping ECD centres for learning puporses | Facilitates availability of learning equipment | MCG/OT/87/2017-2018 | Operationalization of 13 Wards Offices (Furnitures and Solar) | Banisa | Banisa | 3.2104 | 41.1784 | Education | EDUCATION | EDUCATION | EDUCATION | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 24997140 | 24997140 | 9000000 | GOK | N/A | 100 | null | 24997140 | 24997140 | 24997140 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 30,000M3 QARSA EARTH PAN IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 30,000M3 QARSA EARTH PAN IN MANDERA WEST SUB COUNTY | food security | boast food security | null | Water Services | Mandera West | LAGSURE | null | null | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 14480000 | 14480000 | 14480000 | GOK | NA | 100 | null | 14480000 | null | 14480000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 30,000M3 QARSA EARTH PAN IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 30,000M3 QARSA EARTH PAN IN MANDERA WEST SUB COUNTY | food security | boast food security | null | Water Services | Mandera West | LAGSURE | null | null | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 14480000 | 14480000 | 14480000 | GOK | NA | 100 | null | 14480000 | null | 14480000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION 30,000 M3 EARTH PAN AT DUSE BIMA IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION 30,000 M3 EARTH PAN AT DUSE BIMA IN MANDERA WEST SUB COUNTY | water security | improve water security | null | Water Services | Mandera West | Takaba | 3.4911 | 40.1095 | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 17000000 | 17000000 | 15000000 | GOK | NA | 100 | null | 17000000 | null | 17000000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION 30,000 M3 EARTH PAN AT DUSE BIMA IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION 30,000 M3 EARTH PAN AT DUSE BIMA IN MANDERA WEST SUB COUNTY | water security | improve water security | null | Water Services | Mandera West | Takaba | 3.4911 | 40.1095 | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 17000000 | 17000000 | 15000000 | GOK | NA | 100 | null | 17000000 | null | 17000000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CHANGE OF MATERIAL LABORATORY TO PROOCOL OFFICE AND CABRO WORKS IN MANDERA EAST SUB-COUNTY | PROPOSED CHANGE OF MATERIAL LABORATORY TO PROOCOL OFFICE AND CABRO WORKS IN MANDERA EAST SUB-COUNTY | provide office space for staffs | enhance officers accessibility |  | Public Works | Mandera East | Township | null | null | Public Works | Public Works | PUBLIC WORKS | Public Works | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 8498027.4 | 8498027.4 | 8498027.4 | GOK | NA | 100 | 0 | 8498027.4 | null | 8498027.4 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED REPAIR AND MAINTENANCE OF ACCIDENT AND EMERGENCY CENTRES AND MATERNITY CENTRES AT MCRH AND ELWAK REFERRAL HOSPITALS IN MANDERA COUNTY | PROPOSED REPAIR AND MAINTENANCE OF ACCIDENT AND EMERGENCY CENTRES AND MATERNITY CENTRES AT MCRH AND ELWAK REFERRAL HOSPITALS IN MANDERA COUNTY | preventing harm and maintaining safe environment for both patient and hospital staff | maximizing longativity and reducing unplanned cost |  | Health | Mandera South | Elwak South | null | null | Health Services | Health Services | Health Services | Health Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31793802 | 31793802 | 14000000 | GOK | NA | 100 | 0 | 31793802 | null | 31793802 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF40,000M3 EARTH PAN AT BASKORME IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF40,000M3 EARTH PAN AT BASKORME IN BANISA SUB COUNTY | livelyhood enhancement | boast food security |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 19991880 | 19991880 | 19991880 | GOK | NA | 100 | 0 | 19991880 | null | 19991880 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF40,000M3 EARTH PAN AT BASKORME IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF40,000M3 EARTH PAN AT BASKORME IN BANISA SUB COUNTY | livelyhood enhancement | boast food security |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 19991880 | 19991880 | 19991880 | GOK | NA | 100 | 0 | 19991880 | null | 19991880 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF DISPENSARY AT SHIRSHIR IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF DISPENSARY AT SHIRSHIR IN MANDERA NORTH SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera North | ASHABITO | 3.7682 | 41.1336 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-27 00:00:00+00 | 7986882 | 7986882 | 7986882 | GOK | N/A | 100 | 0 | 7986882 | null | 7986882 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 60,000M3 HAR DUMAYO EARTH PAN IN BANISA SUB-COUNTY, MANDERA COUNTY. | PROPOSED CONSTRUCTION OF 60,000M3 HAR DUMAYO EARTH PAN IN BANISA SUB-COUNTY, MANDERA COUNTY. | resource management | improve water security |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 32820616.5 | 32820616.5 | 32820617 | GOK | NA | 100 | 0 | 32820617 | null | 32820617 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 60,000M3 HAR DUMAYO EARTH PAN IN BANISA SUB-COUNTY, MANDERA COUNTY. | PROPOSED CONSTRUCTION OF 60,000M3 HAR DUMAYO EARTH PAN IN BANISA SUB-COUNTY, MANDERA COUNTY. | resource management | improve water security |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 32820616.5 | 32820616.5 | 32820617 | GOK | NA | 100 | 0 | 32820617 | null | 32820617 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
Construction Of 20,000M3 Dambala Gale Earth Pan | Proposed Expansion Of Guba Heaith Centre In Banisa Sub-County. | Improve access to water |  |  |  | Mandera South | WARGADUD | 2.845 | 40.612 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-11-23 00:00:00+00 | 11500000 | 11500000 | 11500000 | GOK | N/A | null | null | 11500000 | 100 | 11500000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Construction Of 20,000M3 Dambala Gale Earth Pan | Proposed Expansion Of Guba Heaith Centre In Banisa Sub-County. | Improve access to water |  |  |  | Mandera South | WARGADUD | 2.845 | 40.612 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-11-23 00:00:00+00 | 11500000 | 11500000 | 11500000 | GOK | N/A | null | null | 11500000 | 100 | 11500000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
PROPOSED CONSTRUCTION OF GATES, CABRO AND PARKING SHADES AT NEW COUNTY HEADQUARTERS IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF GATES, CABRO AND PARKING SHADES AT NEW COUNTY HEADQUARTERS IN MANDERA EAST SUB-COUNTY | security boast | enhance security of the hospital | null | Public Works | Mandera East | Neboi | 3.9621 | 41.7703 | Public Works | Public Works | PUBLIC WORKS | Public Works | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 19991985 | 19991985 | 10000000 | GOK | NA | 100 | null | 19991985 | null | 19991985 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED REPAIR AND MAINTENANCE OF ACCIDENT AND EMERGENCY CENTRES AND MATERNITY CENTRES AT MCRH AND ELWAK REFERRAL HOSPITALS IN MANDERA COUNTY | PROPOSED REPAIR AND MAINTENANCE OF ACCIDENT AND EMERGENCY CENTRES AND MATERNITY CENTRES AT MCRH AND ELWAK REFERRAL HOSPITALS IN MANDERA COUNTY | preventing harm and maintaining safe environment for both patient and hospital staff | maximizing longativity and reducing unplanned cost |  | Health | Mandera East | Township | null | null | Health Services | Health Services | Health Services | Health Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 31793802 | 31793802 | 14000000 | GOK | NA | 100 | 0 | 31793802 | null | 31793802 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA SOUTH SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA SOUTH SUB COUNTY | accessibility and social equity |  |  | public works | Mandera South | WARGADUD | 2.845 | 40.612 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-15 00:00:00+00 | 7500305 | 7500305 | 7500305 | GOK | N/A | 100 | 0 | 7500305 | null | 7500305 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT FULALEY IN LAGSURE IN MANDERA WEST | PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT FULALEY IN LAGSURE IN MANDERA WEST | resilence to climate change | boast food security |  | Water Services | Mandera West | Takaba | null | null | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 12000000 | 12000000 | 10000000 | GOK | NA | 100 | 0 | 12000000 | null | 12000000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT FULALEY IN LAGSURE IN MANDERA WEST | PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT FULALEY IN LAGSURE IN MANDERA WEST | resilence to climate change | boast food security |  | Water Services | Mandera West | Takaba | null | null | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 12000000 | 12000000 | 10000000 | GOK | NA | 100 | 0 | 12000000 | null | 12000000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONTSRUCTION OF 100,000M3 DADACHI GABABA EARTHPAN IN BANISA SUB COUNTY | PROPOSED CONTSRUCTION OF 100,000M3 DADACHI GABABA EARTHPAN IN BANISA SUB COUNTY | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/06/2023-2024 | null | Banisa | Banisa | 2.938 | 40.339 | WATER SERVICES | Water Services | Water Services | Water Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-03-13 21:00:00+00 | 74976231 | 74976231 | 74946231 | GOK | N/A | null | null | null | null | 74946231 | null | 30000 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONTSRUCTION OF 100,000M3 DADACHI GABABA EARTHPAN IN BANISA SUB COUNTY | PROPOSED CONTSRUCTION OF 100,000M3 DADACHI GABABA EARTHPAN IN BANISA SUB COUNTY | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/06/2023-2024 | null | Banisa | Banisa | 2.938 | 40.339 | WATER SERVICES | Water Services | Water Services | Water Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-03-13 21:00:00+00 | 74976231 | 74976231 | 74946231 | GOK | N/A | null | null | null | null | 74946231 | null | 30000 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT KUBI KOYETI IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT KUBI KOYETI IN MANDERA WEST SUB COUNTY | resilence to climate change | increase climate resilence | null | Water Services | Mandera West | Gither | 3.7055 | 39.954 | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 12000000 | 12000000 | 10000000 | GOK | NA | 100 | null | 12000000 | null | 12000000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT KUBI KOYETI IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT KUBI KOYETI IN MANDERA WEST SUB COUNTY | resilence to climate change | increase climate resilence | null | Water Services | Mandera West | Gither | 3.7055 | 39.954 | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 12000000 | 12000000 | 10000000 | GOK | NA | 100 | null | 12000000 | null | 12000000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF DISPENSARY AT GARBAQOLEY IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF DISPENSARY AT GARBAQOLEY IN MANDERA EAST SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera East | Township | 3.936 | 41.8587 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-03 00:00:00+00 | 7500000 | 7500000 | 7500000 | GOK | N/A | 100 | 0 | 7500000 | null | 7500000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CHANGE OF KAMOR BORDER PETROL BASE TO KAMOR HEALTH CENTRE IN MANDERA EAST | PROPOSED CHANGE OF KAMOR BORDER PETROL BASE TO KAMOR HEALTH CENTRE IN MANDERA EAST | improving health and preventing diseases | healthy lifestyle |  | health | Mandera East | Township | 3.9251 | 41.8543 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-25 00:00:00+00 | 46000000 | 46000000 | null | GOK | N/A | 100 | 0 | 46000000 | null | 46000000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF GESREBKI DISPENSARY IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF GESREBKI DISPENSARY IN BANISA SUB COUNTY | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/022/2023-2024 | null | Banisa | Banisa | 4.0029 | 40.2308 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 19924020 | 19924020 | 5715800 | GOK | N/A | null | null | null | null | 11715800 | null | 8208220 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 40,000 CUBIC METRE EARTH PAN AT KAMOR ELLE IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF 40,000 CUBIC METRE EARTH PAN AT KAMOR ELLE IN MANDERA EAST SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera East | Township | 3.9251 | 41.8543 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-11 00:00:00+00 | 19796910 | 19796910 | 19796910 | GOK | N/A | 100 | 0 | 19796910 | null | 19796910 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 40,000 CUBIC METRE EARTH PAN AT KAMOR ELLE IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF 40,000 CUBIC METRE EARTH PAN AT KAMOR ELLE IN MANDERA EAST SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera East | Township | 3.9251 | 41.8543 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-11 00:00:00+00 | 19796910 | 19796910 | 19796910 | GOK | N/A | 100 | 0 | 19796910 | null | 19796910 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CHAINLINK FENCING AND BUSH CLEARING AT BAMBO DISPENSARY IN LAFEY SUB-COUNTY | PROPOSED CHAINLINK FENCING AND BUSH CLEARING AT BAMBO DISPENSARY IN LAFEY SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera East | Lafey | 3.5259 | 40.9754 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-11 00:00:00+00 | 6858616 | 6858616 | 6858616 | GOK | N/A | 100 | 0 | 6858616 | null | 6858616 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of Rhamu Dimtu- Argarbicha Road In Mandera North Sub-County | Proposed Construction Of Rhamu Dimtu- Argarbicha Road In Mandera North Sub-County | smooth flow of goods and services | boost trade |  | Road/public works | Mandera North | Rhamu Dimtu | 3.82 | 40.98 | Roads | ROADS | ROADS | ROADS | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-01 00:00:00+00 | 49945308 | 49945308 | null | GOK | N/A | 100 | 0 | 49945308 | null | 49945308 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED OPENING UP OF ACCESS ROADS IN NEWLY SURVEYED AREA IN MANDERA EAST | PROPOSED OPENING UP OF ACCESS ROADS IN NEWLY SURVEYED AREA IN MANDERA EAST | smooth flow of goods and services | boost trade |  | Road/public works | Mandera East | Township | 3.936 | 41.857 | Roads | ROADS | ROADS | ROADS | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-28 00:00:00+00 | 58683008 | 58683008 | null | GOK | N/A | 100 | 0 | 58683008 | null | 58683008 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF DRIFT ON LAG WARERA AT BULA MPYA IN MANDERA WEST | PROPOSED CONSTRUCTION OF DRIFT ON LAG WARERA AT BULA MPYA IN MANDERA WEST | smooth flow of goods and services | boost trade |  | Road/public works | Mandera West | Takaba | 3.939 | 41.852 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-23 00:00:00+00 | 9500500 | 9500500 | null | GOK | N/A | 100 | 0 | 9500500 | null | 9500500 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF AIRSTRIP AT TAKABA IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF AIRSTRIP AT TAKABA IN MANDERA WEST SUB COUNTY | ensure smooth flow |  |  | Road/public works | Mandera West | Takaba | 3.403 | 40.186 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-19 00:00:00+00 | 70123456 | 70123456 | 20000000 | GOK | N/A | 100 | 0 | 70123456 | null | 70123456 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION AND FENCING OF NEW DISPENSARY AT USUBEY-RHAMU DIMTU IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION AND FENCING OF NEW DISPENSARY AT USUBEY-RHAMU DIMTU IN MANDERA NORTH SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera North | Rhamu Dimtu | 3.85 | 41 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-05 00:00:00+00 | 9961500 | 9961500 | 9961500 | GOK | N/A | 100 | 0 | 9961500 | null | 9961500 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF KUTULO LEVEL IV HOSPITAL IN KUTULO SUB-COUNY | PROPOSED CONSTRUCTION OF KUTULO LEVEL IV HOSPITAL IN KUTULO SUB-COUNY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera South | Kutulo | 3.04 | 41.075 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-18 00:00:00+00 | 120412837.2 | 120412837 | 65000000 | GOK | N/A | 100 | 0 | 120412837 | null | 120412837 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED GRADING AND MURRUMING OF DAR ES SALAM - SAROHINDI ROAD MANDERA EAST | PROPOSED GRADING AND MURRUMING OF DAR ES SALAM - SAROHINDI ROAD MANDERA EAST | smooth flow of goods and services | boost trade |  | Road/public works | Mandera East | Township | 3.8756 | 41.5552 | Roads | ROADS | ROADS | ROADS | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-26 00:00:00+00 | 19829040 | 19829040 | null | GOK | N/A | 100 | 0 | 19829040 | null | 19829040 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF PUBLIC DIAS AT OLLA PUBLIC BARAZA PARK IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF PUBLIC DIAS AT OLLA PUBLIC BARAZA PARK IN MANDERA NORTH SUB-COUNTY | community welfare |  |  | Road/public works | Mandera North | ASHABITO | 3.92 | 40.85 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-03 00:00:00+00 | 5000000 | 5000000 | null | GOK | N/A | 100 | 0 | 5000000 | null | 5000000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 7NO HOUSING UNIT AND 7NO TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 7NO HOUSING UNIT AND 7NO TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA COUNTY | accessibility and social equity |  |  | public works | Mandera East | Township | 3.936 | 41.857 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-27 00:00:00+00 | 5200000 | 5200000 | 5200000 | GOK | N/A | 100 | 0 | 5200000 | null | 5200000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF DISPENSARY AT KARO IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF DISPENSARY AT KARO IN MANDERA EAST SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera East | Township | 3.8917 | 41.679 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-28 00:00:00+00 | 7600000 | 7600000 | 7600000 | GOK | N/A | 100 | 0 | 7600000 | null | 7600000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of Elwak- Kutayu Road | Proposed Construction Of Elwak- Kutayu Road | improve access | increased safety,reducd accidents |  | Road/public works | Mandera South | Elwak South | 2.808 | 40.926 | Roads | ROADS | ROADS | ROADS | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-20 00:00:00+00 | 82035954 | 82035954 | null | GOK | N/A | 100 | 0 | 82035954 | null | 82035954 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CHAINLINK FENCING AND BUSH CLEARING AT BAMBO DISPENSARY IN LAFEY SUB-COUNTY | PROPOSED CHAINLINK FENCING AND BUSH CLEARING AT BAMBO DISPENSARY IN LAFEY SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera East | Lafey | 3.5259 | 40.9754 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-01 00:00:00+00 | 6858616 | 6858616 | 6858616 | GOK | N/A | 100 | 0 | 6858616 | null | 6858616 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF DRIFT AT LAGSURE AT TAKABA IN MANDERA WEST | PROPOSED CONSTRUCTION OF DRIFT AT LAGSURE AT TAKABA IN MANDERA WEST | smooth flow of goods and services | boost trade |  | Road/public works | Mandera West | LAGSURE | 3.393 | 40.503 | Roads | ROADS | ROADS | ROADS | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-07 00:00:00+00 | 24269549 | 24269549 | null | GOK | N/A | 100 | 0 | 24269549 | null | 24269549 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF BOX CULVERT ON TAKABA - BANISA ROAD AT LAGWARERA IN MANDERA WEST | PROPOSED CONSTRUCTION OF BOX CULVERT ON TAKABA - BANISA ROAD AT LAGWARERA IN MANDERA WEST | smooth flow of goods and services | boost trade |  | Road/public works | Mandera West | Takaba | 3.4211 | 40.2628 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-12 00:00:00+00 | 41968800 | 41968800 | null | GOK | N/A | 100 | 0 | 41968800 | null | 41968800 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF PUBLIC DIAS AT RHAMU PUBLIC BARAZA PARK IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF PUBLIC DIAS AT RHAMU PUBLIC BARAZA PARK IN MANDERA NORTH SUB-COUNTY | community welfare |  |  | Road/public works | Mandera North | Rhamu | 3.935 | 41.222 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-08 00:00:00+00 | 7780000 | 7780000 | null | GOK | N/A | 100 | 0 | 7780000 | null | 7780000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF OPD AT HARSHILMI IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF OPD AT HARSHILMI IN MANDERA WEST SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera West | Dandu | 3.6 | 39.7422 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-23 00:00:00+00 | 75278449 | 75278449 | 30000000 | GOK | N/A | 100 | 0 | 75278449 | null | 75278449 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED GRADING AND BUSH CLEARING OF SHAFSHAFEY ROAD FROM B9- TO KHALALIO ROAD IN MANDERA EAST SUB COUNTY | PROPOSED GRADING AND BUSH CLEARING OF SHAFSHAFEY ROAD FROM B9- TO KHALALIO ROAD IN MANDERA EAST SUB COUNTY | smooth flow of goods and services | boost trade |  | Road/public works | Mandera East | Khalalio | 3.936 | 41.857 | Roads | ROADS | ROADS | ROADS | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-22 00:00:00+00 | 10005580 | 10005580 | null | GOK | N/A | 100 | 0 | 10005580 | null | 10005580 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED DESILTING OF KOB ADADI EARTH PAN AT MANDERA SOUTH SUB COUNTY | PROPOSED DESILTING OF KOB ADADI EARTH PAN AT MANDERA SOUTH SUB COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera South | WARGADUD | 3.19 | 40.4196 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-13 00:00:00+00 | 14153132 | 14153132 | 14153132 | GOK | N/A | 100 | 0 | 14153132 | null | 14153132 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED DESILTING OF KOB ADADI EARTH PAN AT MANDERA SOUTH SUB COUNTY | PROPOSED DESILTING OF KOB ADADI EARTH PAN AT MANDERA SOUTH SUB COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera South | WARGADUD | 3.19 | 40.4196 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-13 00:00:00+00 | 14153132 | 14153132 | 14153132 | GOK | N/A | 100 | 0 | 14153132 | null | 14153132 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF BOX CULVERT ON LAGA ALONG KHALALIO ROAD IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF BOX CULVERT ON LAGA ALONG KHALALIO ROAD IN MANDERA EAST SUB-COUNTY | smooth flow of goods and services | boost trade |  | Road/public works | Mandera East | Khalalio | 3.933 | 41.828 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-17 00:00:00+00 | 49697462 | 49697462 | null | GOK | N/A | 100 | 0 | 49697462 | null | 49697462 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN LAFEY SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN LAFEY SUB COUNTY | accessibility and social equity |  |  | public works | Mandera East | Lafey | 3.05 | 41.3 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-01 00:00:00+00 | 6308022 | 6308022 | 6308022 | GOK | N/A | 100 | 0 | 6308022 | null | 6308022 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
REPAIR AND RENOVATION OF NEBOI DISPENSARY IN MANDERA EAST | REPAIR AND RENOVATION OF NEBOI DISPENSARY IN MANDERA EAST | improving health and preventing diseases | healthy lifestyle | null | health | Mandera East | Neboi | 3.9621 | 41.7703 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-01 00:00:00+00 | 6065000 | 6065000 | 6065000 | GOK | N/A | 100 | null | 6065000 | null | 6065000 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED KUTULO(MALBE) WATER PAN FOR IRRIGATION PROJECT IN KUTULO SUB-COUNTY | PROPOSED KUTULO(MALBE) WATER PAN FOR IRRIGATION PROJECT IN KUTULO SUB-COUNTY | enhancing productivity | increasing crop yields |  | water | Mandera South | Kutulo | 2.32 | 40.72 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-30 00:00:00+00 | 253013296 | 253013296 | null | GOK | N/A | 100 | 0 | 253013296 | null | 253013296 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED KUTULO(MALBE) WATER PAN FOR IRRIGATION PROJECT IN KUTULO SUB-COUNTY | PROPOSED KUTULO(MALBE) WATER PAN FOR IRRIGATION PROJECT IN KUTULO SUB-COUNTY | enhancing productivity | increasing crop yields |  | water | Mandera South | Kutulo | 2.32 | 40.72 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-30 00:00:00+00 | 253013296 | 253013296 | null | GOK | N/A | 100 | 0 | 253013296 | null | 253013296 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of Takaba- Gither Road In Mandera West Sub-County | Proposed Construction Of Takaba- Gither Road In Mandera West Sub-County | smooth flow of goods and services | boost trade |  | Road/public works | Mandera West | Takaba | 3.154 | 40.357 | Roads | ROADS | ROADS | ROADS | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-11 00:00:00+00 | 115582400 | 115582400 | null | GOK | N/A | 100 | 0 | 115582400 | null | 115582400 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONTRUCTION OF DEPUTY GOVERNORS RESIDENCE IN MANDERA EAST | PROPOSED CONTRUCTION OF DEPUTY GOVERNORS RESIDENCE IN MANDERA EAST | infrastructure improvement and Economic Development | service delivery |  | public works | Mandera East | Township | 3.936 | 41.857 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-21 00:00:00+00 | 78983884 | 78983884 | 33000000 | GOK | N/A | 100 | 0 | 78983884 | null | 78983884 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN KUTULO SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN KUTULO SUB COUNTY | accessibility and social equity |  |  | public works | Mandera South | Kutulo | 3.04 | 41.075 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-30 00:00:00+00 | 5648167 | 5648167 | 5648167 | GOK | N/A | 100 | 0 | 5648167 | null | 5648167 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED FENCING OF HARERI HOSLE DISPENSARY, CONSTRUCTION OF NEW MATERNITY WING AND STAFF HOUSING IN MANDERA EAST SUB-COUNTY | PROPOSED FENCING OF HARERI HOSLE DISPENSARY, CONSTRUCTION OF NEW MATERNITY WING AND STAFF HOUSING IN MANDERA EAST SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | health | Mandera East | Lafey | 3.9474 | 41.4757 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-29 00:00:00+00 | 38462893 | 38462893 | null | GOK | N/A | 100 | 0 | 38462893 | null | 38462893 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED MAINTENACE AND LIGHT GRADING OF ARABIA-BAMBO 2 ROAD IN MANDERA EAST SUB-COUNTY | PROPOSED MAINTENACE AND LIGHT GRADING OF ARABIA-BAMBO 2 ROAD IN MANDERA EAST SUB-COUNTY | smooth flow of goods and services | boost trade |  | Road/public works | Mandera East | ARABIA | 3.562 | 41.499 | Roads | ROADS | ROADS | ROADS | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-22 00:00:00+00 | 9819632 | 9819632 | null | GOK | N/A | 100 | 0 | 9819632 | null | 9819632 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED MAINTENANCE AND SPOT PATCHING ON LAFEY-KABO ROAD IN LAFEY SUB-COUNTY | PROPOSED MAINTENANCE AND SPOT PATCHING ON LAFEY-KABO ROAD IN LAFEY SUB-COUNTY | smooth flow of goods and services | boost trade |  | Road/public works | Mandera East | Lafey | 3.05 | 41.3 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-05 00:00:00+00 | 9.9998 | 9999820 | 9999820 | GOK | N/A | 100 | 0 | 9999820 | null | 9999820 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF MOROTHILE-AWARA ROAD(GRAVEL STANDARD) IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF MOROTHILE-AWARA ROAD(GRAVEL STANDARD) IN MANDERA NORTH SUB-COUNTY | smooth flow of goods and services | boost trade |  | Road/public works | Mandera North | MOROTHILE | 3.9347 | 41.8561 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-29 00:00:00+00 | 43524305 | 43524305 | null | GOK | N/A | 100 | 0 | 43524305 | null | 43524305 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of Choroqo- Guba Road In Banisa Sub-County | Proposed Construction Of Choroqo- Guba Road In Banisa Sub-County | smooth flow of goods and services | boost trade |  | Road/public works | null | Guba | 3.9546 | 40.5015 | Roads | ROADS | ROADS | ROADS | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-24 00:00:00+00 | 24967538 | 24967538 | null | GOK | N/A | 100 | 0 | 24967538 | null | 24967538 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED COMPLETION OF GOVERNORS RESIDENCE IN MANDERA EAST | PROPOSED COMPLETION OF GOVERNORS RESIDENCE IN MANDERA EAST | infrastructure improvement and Economic Development | service delivery |  | public works | Mandera East | Township | 3.936 | 41.857 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-30 00:00:00+00 | 258051400 | 258051400 | 82000000 | GOK | N/A | 100 | 0 | 258051400 | null | 258051400 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 14NO.HOUSING UNIT AND 14NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA EAST SUB COUNTY | PROPOSED CONSTRUCTION OF 14NO.HOUSING UNIT AND 14NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA EAST SUB COUNTY | accessibility and social equity |  |  | public works | Mandera East | Township | 3.936 | 41.857 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-29 00:00:00+00 | 13420630 | 13420630 | 13420630 | GOK | N/A | 100 | 0 | 13420630 | null | 13420630 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Supply And Delivery Of Computers And Accessories To Mandera County | Supply And Delivery Of Computers And Accessories To Mandera County | ensure efficient and effective service delivery | qualitycontrol |  | ICT | Mandera East | Township | 3.936 | 41.857 | ICT | ICT | ICT | ICT | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-11 00:00:00+00 | 19983726 | 19983726 | 12500000 | GOK | N/A | 100 | 0 | 19983726 | null | 19983726 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF MANDERA TEACHERS TRAINING COLLEGE IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF MANDERA TEACHERS TRAINING COLLEGE IN MANDERA EAST SUB-COUNTY | promote quality education | human resources development | null | Education | Mandera East | Neboi | 3.936 | 41.857 | Education | EDUCATION | EDUCATION | EDUCATION | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-17 00:00:00+00 | 250000000 | 250000000 | 80000000 | GOK | N/A | 100 | null | 250000000 | null | 250000000 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of40,000M3 Earth Pan At Baskorme In Banisa Sub County | Proposed Construction Of40,000M3 Earth Pan At Baskorme In Banisa Sub County | Improve access to water | earth pan |  |  | null | null | 3.8867 | 40.3074 | Health Services | Health Services | Health Services | Health Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-03-27 00:00:00+00 | 19991880 | 19991880 | 19991880 | GOK | N/A | null | null | 19991880 | 100 | 19991880 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
PROPOSED UPGRADING OF BOREHOLE 11 HEALTH CENTRE | PROPOSED UPGRADING OF BOREHOLE 11 HEALTH CENTRE | improving health and preventing diseases | healthy lifestyle |  | health | Mandera South | Elwak South | 2.716 | 40.9173 | health services | Health Services | Health Services | Health Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-03 00:00:00+00 | 75135786 | 75135786 | 24000000 | GOK | N/A | 100 | 0 | 75135786 | null | 75135786 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF DRIFT BETWEEN WARANQARA AND LAFEY ROAD IN LAFEY SUB-COUNTY | PROPOSED CONSTRUCTION OF DRIFT BETWEEN WARANQARA AND LAFEY ROAD IN LAFEY SUB-COUNTY | smooth flow of goods and services | boost trade | null | Road/public works | Lafey | WARANQARA | 3.513 | 41.15 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-02 00:00:00+00 | 14937335 | 14937335 | null | GOK | N/A | 100 | null | 14937335 | null | 14937335 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED ADMINISTRATION BLOCK AT MANDERA TECHNICAL TRAINING INSTITUTE IN MANDERA EAST SUB COUNTY | PROPOSED ADMINISTRATION BLOCK AT MANDERA TECHNICAL TRAINING INSTITUTE IN MANDERA EAST SUB COUNTY | promote quality education | human resources development |  | Education | Mandera East | Township | 3.936 | 41.857 | Education | EDUCATION | EDUCATION | EDUCATION | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-21 00:00:00+00 | 69850000 | 69850000 | 40000000 | GOK | N/A | 100 | 0 | 69850000 | null | 69850000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED COMPLETION OF KUTULO MARKET IN MANDERA SOUTH SUB COUNTY | PROPOSED COMPLETION OF KUTULO MARKET IN MANDERA SOUTH SUB COUNTY | boost trade | economic development |  | public works | Mandera South | Kutulo | 3.9336 | 41.858 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-07 00:00:00+00 | 19323590 | 19323590 | 2566523 | GOK | N/A | 100 | 0 | 19323590 | null | 19323590 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Supply And Delivery Of Office Furniture For Mandera County Lot1 | Supply And Delivery Of Office Furniture For Mandera County Lot1 | ensure service delivery | effective service delivery |  | finance | Mandera East | Township | 3.936 | 41.857 | financial services | FINANCIAL SERVICES | Financial Services | FINANCIAL SERVICES | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-27 00:00:00+00 | 32006848 | 32006848 | 6000000 | GOK | N/A | 100 | 0 | 32006848 | null | 32006848 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED PAVED PARKING,DRAINAGE AND FENCING WORKS AT ELWAK SME MARKET IN MANDERA SOUTH SUB-COUNTY. | PROPOSED PAVED PARKING,DRAINAGE AND FENCING WORKS AT ELWAK SME MARKET IN MANDERA SOUTH SUB-COUNTY. | infrastructure improvement |  |  | Public works | Mandera South | Elwak South | 2.808 | 40.926 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-24 00:00:00+00 | 167355708 | 167355708 | 50000000 | GOK | N/A | 100 | 0 | 167355708 | null | 167355708 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Supply And Delivery Of Office Furniture To Office Of The Governor | Supply And Delivery Of Office Furniture To Office Of The Governor | to promotequality service delivery |  |  | finance | Mandera East | Township | 3.9358 | 41.86 | financial services | FINANCIAL SERVICES | Financial Services | FINANCIAL SERVICES | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-07-13 00:00:00+00 | 12265866 | 12265866 | 7000000 | GOK | N/A | 100 | 0 | 12265866 | null | 12265866 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
proposed construction of 20,000m3 earth pan in funanteso at banisa sub-county | proposed construction of 20,000m3 earth pan in funanteso at banisa sub-county | Providing Water for Domestic Use | increases farming nearby dams | MCG/OT/49/2017-2018 | construction of 30,000m3 at Funan Teso (mandera West) | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 14225400 | 14225400 | 15500000 | GOK | N/A | 100 | null | 14225400 | 14225400 | 14225400 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 20,000m3 earth pan in funanteso at banisa sub-county | proposed construction of 20,000m3 earth pan in funanteso at banisa sub-county | Providing Water for Domestic Use | increases farming nearby dams | MCG/OT/49/2017-2018 | construction of 30,000m3 at Funan Teso (mandera West) | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 14225400 | 14225400 | 15500000 | GOK | N/A | 100 | null | 14225400 | 14225400 | 14225400 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of kubi dispensary block in kubi | Proposed construction of kubi dispensary block in kubi subcounty | Improve Access to Primary Healthcare Services | improved heathcare access | MCG/0T/29/2017/2018 | Proposed construction of Dispensary at Kubi , Mandera North | Mandera North | MOROTHILE | 3.9272 | 41.2229 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 7401585 | 7401585 | 8000000 | GOK | N/A | 100 | null | 7401585 | 7401585 | 7401585 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 60,000M3 BARWAQO EARTHPAN IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF 60,000M3 BARWAQO EARTHPAN IN BANISA SUB COUNTY | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/04/2023-2024 | null | Banisa | Banisa | 3.9499 | 40.3457 | WATER SERVICES | Water Services | Water Services | Water Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 30671571 | 30671571 | 12000000 | GOK | N/A | null | null | null | null | null | null | 30671571 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 60,000M3 BARWAQO EARTHPAN IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF 60,000M3 BARWAQO EARTHPAN IN BANISA SUB COUNTY | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/04/2023-2024 | null | Banisa | Banisa | 3.9499 | 40.3457 | WATER SERVICES | Water Services | Water Services | Water Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 30671571 | 30671571 | 12000000 | GOK | N/A | null | null | null | null | null | null | 30671571 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED REHABILITATION OF WATER SUPPLY SYSTEM AND CONNECTION TO WATER KIOSK WITHIN KILIWEHIRI TOWN IN BANISA SUB-COUNTY | PROPOSED REHABILITATION OF WATER SUPPLY SYSTEM AND CONNECTION TO WATER KIOSK WITHIN KILIWEHIRI TOWN IN BANISA SUB-COUNTY | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/119/2023-2024 | null | Banisa | Kiliweheri | 3.9066 | 40.0091 | WATER SERVICES | Water Services | Water Services | Water Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 18488693 | 18488693 | 10000000 | GOK | N/A | null | null | null | null | null | null | 18488693 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED REHABILITATION OF WATER SUPPLY SYSTEM AND CONNECTION TO WATER KIOSK WITHIN KILIWEHIRI TOWN IN BANISA SUB-COUNTY | PROPOSED REHABILITATION OF WATER SUPPLY SYSTEM AND CONNECTION TO WATER KIOSK WITHIN KILIWEHIRI TOWN IN BANISA SUB-COUNTY | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/119/2023-2024 | null | Banisa | Kiliweheri | 3.9066 | 40.0091 | WATER SERVICES | Water Services | Water Services | Water Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 18488693 | 18488693 | 10000000 | GOK | N/A | null | null | null | null | null | null | 18488693 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED COMPLETION AND UPGRADING OF BANISA LEVEL IV HOSPITAL IN BANISA SUB COUNTY | PROPOSED COMPLETION AND UPGRADING OF BANISA LEVEL IV HOSPITAL IN BANISA SUB COUNTY | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/02/2023-2024 | Proposed Upgrading and Improvement of Level 4 Hospitals | Banisa | Banisa | 3.9403 | 40.3442 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-10-03 21:00:00+00 | 138214663 | 138214663 | 45000000 | GOK | N/A | null | null | null | null | 69000000 | null | 69214663 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Ongoing
Mcg/310/2014-2015 | Rehabilitation of Hareri water supply in Mandera east Sub-County | improve water access | water infrustructure | null | null | Mandera East | Libihiya | 3.7636 | 41.3584 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 6980000 | 6980000 | 6980000 | GOK | N/A | 100 | null | 6980000 | 6980000 | 6980000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/310/2014-2015 | Rehabilitation of Hareri water supply in Mandera east Sub-County | improve water access | water infrustructure | null | null | Mandera East | Libihiya | 3.7636 | 41.3584 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 6980000 | 6980000 | 6980000 | GOK | N/A | 100 | null | 6980000 | 6980000 | 6980000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction of 20,000m3 Earth Pan At Abba Jida In Mandera South Sub-County | Proposed Construction of 20,000m3 Earth Pan At Abba Jida In Mandera South Sub-County | Climate Resilience by enhancing the county's resilience to climate change. | increases farming nearby dams | MCG/0T/43/2017/2018 | Expansion and disilting of Abba Jida Dam | Mandera South | Kutulo | 2.5481 | 40.7047 | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 10380000 | 10380000 | 10500000 | GOK | N/A | 100 | null | 10380000 | 10380000 | 10380000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction of 20,000m3 Earth Pan At Abba Jida In Mandera South Sub-County | Proposed Construction of 20,000m3 Earth Pan At Abba Jida In Mandera South Sub-County | Climate Resilience by enhancing the county's resilience to climate change. | increases farming nearby dams | MCG/0T/43/2017/2018 | Expansion and disilting of Abba Jida Dam | Mandera South | Kutulo | 2.5481 | 40.7047 | Water Services | Water Services | Water Services | Water Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 10380000 | 10380000 | 10500000 | GOK | N/A | 100 | null | 10380000 | 10380000 | 10380000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED EXPANSION OF KUKUB EARTH PAN TO 50,000 CUBIC METRES IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF KUKUB EARTH PAN TO 50,000 CUBIC METRES IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | null | null | 3.866 | 40.2054 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-06 00:00:00+00 | 17529225 | 17529225 | 17706249 | GOK | N/A | 100 | 0 | 17529225 | null | 17529225 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED EXPANSION OF KUKUB EARTH PAN TO 50,000 CUBIC METRES IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF KUKUB EARTH PAN TO 50,000 CUBIC METRES IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | null | null | 3.866 | 40.2054 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-06 00:00:00+00 | 17529225 | 17529225 | 17706249 | GOK | N/A | 100 | 0 | 17529225 | null | 17529225 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Mcg/289/2014-2015 | Construction of 60,000m3 earth pan at Kiliweheri in banisa Sub ï¿½ County | improve water access | water infrustructure | null | null | Banisa | Kiliweheri | 3.0386 | 40.2389 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 34799845 | 34799845 | 34799845 | GOK | N/A | 100 | null | 34799845 | 34799845 | 34799845 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/289/2014-2015 | Construction of 60,000m3 earth pan at Kiliweheri in banisa Sub ï¿½ County | improve water access | water infrustructure | null | null | Banisa | Kiliweheri | 3.0386 | 40.2389 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 34799845 | 34799845 | 34799845 | GOK | N/A | 100 | null | 34799845 | 34799845 | 34799845 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Office Block For Ministry Health Services In Mandera East | Proposed Office Block For Ministry Health Services In Mandera East | Improve Access to Primary Healthcare Services | create employment opportunitie | MCG/OT/25/2017-2018 | Office block for Ministry of health at MCHR | Mandera East | Township | 3.9486 | 41.8525 | Health Services | Health Services | Health Services | Health Services | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 28980744 | 28980744 | 21000000 | GOK | N/A | 100 | null | 28980744 | 28980744 | 28980744 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Desilting And Expansion Of 30,000M3 Of Dumayo Earth Pan In Banisa, Mandera County | Proposed Desilting And Expansion Of 30,000M3 Of Dumayo Earth Pan In Banisa, Mandera County | Improve access to water | earth pan |  |  | null | null | 3.8867 | 40.3074 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-03-15 00:00:00+00 | 14999800 | 14999800 | 14999800 | GOK | N/A | null | null | 14999800 | 100 | 14999800 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Proposed Desilting And Expansion Of 30,000M3 Of Dumayo Earth Pan In Banisa, Mandera County | Proposed Desilting And Expansion Of 30,000M3 Of Dumayo Earth Pan In Banisa, Mandera County | Improve access to water | earth pan |  |  | null | null | 3.8867 | 40.3074 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-03-15 00:00:00+00 | 14999800 | 14999800 | 14999800 | GOK | N/A | null | null | 14999800 | 100 | 14999800 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Mcg/277/2014-2015 | Drilling of boreholes in Mandera South Sub ï¿½ County | improve water access | water infrustructure | null | null | Mandera South | WARGADUD | 2.9045 | 40.7289 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 14118200 | 14118200 | 14118200 | GOK | N/A | 100 | null | 14118200 | 14118200 | 14118200 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/277/2014-2015 | Drilling of boreholes in Mandera South Sub ï¿½ County | improve water access | water infrustructure | null | null | Mandera South | WARGADUD | 2.9045 | 40.7289 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 14118200 | 14118200 | 14118200 | GOK | N/A | 100 | null | 14118200 | 14118200 | 14118200 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF DIDKURO WATER SUPPLY IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF DIDKURO WATER SUPPLY IN MANDERA WEST SUB-COUNTY | ï¿½To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | MCG/OT/070/2023-2024 | null | Mandera West | Takaba | 3.4911 | 40.1095 | WATER SERVICES | Water Services | Water Services | Water Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 184682867 | 184682867 | 60000000 | GOK | N/A | null | null | null | null | 110000000 | null | 74682867 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Ongoing
PROPOSED CONSTRUCTION OF DIDKURO WATER SUPPLY IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF DIDKURO WATER SUPPLY IN MANDERA WEST SUB-COUNTY | ï¿½To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | MCG/OT/070/2023-2024 | null | Mandera West | Takaba | 3.4911 | 40.1095 | WATER SERVICES | Water Services | Water Services | Water Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 184682867 | 184682867 | 60000000 | GOK | N/A | null | null | null | null | 110000000 | null | 74682867 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Ongoing
Proposed construction of public service registry block at geneva in mandera east | Proposed construction of public service registry block at geneva in mandera east | To provide safety and proper records facility | provides good storage of files and records | null | Human Resource Registry | Mandera East | Township | 3.9486 | 41.8525 | Public Service | Public Service | Public Service | Public Service | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 29325146 | 29325146 | 12000000 | GOK | N/A | 100 | null | 29325146 | 29325146 | 29325146 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction Of Kutulo (Malbe) Water Pan Irrigation Projects | Construction Of Kutulo (Malbe) Water Pan Irrigation Projects | improve food production | irrigation infrustructure |  | 200,000M3 Earth Pan for irrigation and food production at Malbe in Kutulo Sub-County complete with Irrigation infrastructure | Mandera South | Kutulo | 2.418 | 40.6742 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-11-27 00:00:00+00 | 253013297 | 253013297 | 207092828 | GOK | N/A | null | null | 253013297 | 100 | 253013297 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Construction Of Kutulo (Malbe) Water Pan Irrigation Projects | Construction Of Kutulo (Malbe) Water Pan Irrigation Projects | improve food production | irrigation infrustructure |  | 200,000M3 Earth Pan for irrigation and food production at Malbe in Kutulo Sub-County complete with Irrigation infrastructure | Mandera South | Kutulo | 2.418 | 40.6742 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-11-27 00:00:00+00 | 253013297 | 253013297 | 207092828 | GOK | N/A | null | null | 253013297 | 100 | 253013297 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
PROPOSED DESILTING AND EXPANSION OF KOBADADI WEST EARTH PAN BY 20,000M3 IN MANDERA WEST SUB COUNTY | PROPOSED DESILTING AND EXPANSION OF KOBADADI WEST EARTH PAN BY 20,000M3 IN MANDERA WEST SUB COUNTY | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/066/2023-2024 | null | Mandera West | LAGSURE | 3.1915 | 40.4221 | WATER SERVICES | Water Services | Water Services | Water Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 14937448 | 14937448 | 7468724 | GOK | N/A | null | null | null | null | 7468724 | null | 7468724 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED DESILTING AND EXPANSION OF KOBADADI WEST EARTH PAN BY 20,000M3 IN MANDERA WEST SUB COUNTY | PROPOSED DESILTING AND EXPANSION OF KOBADADI WEST EARTH PAN BY 20,000M3 IN MANDERA WEST SUB COUNTY | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/066/2023-2024 | null | Mandera West | LAGSURE | 3.1915 | 40.4221 | WATER SERVICES | Water Services | Water Services | Water Services | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 14937448 | 14937448 | 7468724 | GOK | N/A | null | null | null | null | 7468724 | null | 7468724 | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED PAVED PARKING AT NEW FIRE STATION IN MANDERA EAST SUB COUNTY | PROPOSED PAVED PARKING AT NEW FIRE STATION IN MANDERA EAST SUB COUNTY | improved access |  |  | Road/public works | Mandera East | Township | 3.936 | 41.857 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-05 00:00:00+00 | 76288200 | 76288200 | 35000000 | GOK | N/A | 100 | 0 | 76288200 | null | 76288200 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of 32No Housing Unit And 32No Toilet For Vulnerable Persons In Lafey, Mandera North And Banisa Sub Counties In Mandera County | Proposed Construction Of 32No Housing Unit And 32No Toilet For Vulnerable Persons In Lafey, Mandera North And Banisa Sub Counties In Mandera County | improve housing |  |  | Liability for IDP Housing | null | null | 3.9387 | 41.86 | Social Services | Social Services | Social Services | Social Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-14 00:00:00+00 | 31578912 | 31578912 | 97387075 | GOK | N/A | null | null | 31578912 | 100 | 31578912 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
PROPOSED RENOCONSTRUCTION OF 60,000M3 BAAYE EARTH PAN IN BANISA SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 BAAYE EARTH PAN IN BANISA SUB-COUNTY | Water Harvesting and Storage | Increased availability of water for domestic and livestock use during dry seasons. |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-22 00:00:00+00 | 31075000 | 31075000 | 15537500 | GOK | NA | 100 | 0 | 31075000 | 100 | 31075000 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 BAAYE EARTH PAN IN BANISA SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 BAAYE EARTH PAN IN BANISA SUB-COUNTY | Water Harvesting and Storage | Increased availability of water for domestic and livestock use during dry seasons. |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-22 00:00:00+00 | 31075000 | 31075000 | 15537500 | GOK | NA | 100 | 0 | 31075000 | 100 | 31075000 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 CHAME EARTH PAN | PROPOSED RENOCONSTRUCTION OF 60,000M3 CHAME EARTH PAN | Climate Resilience | Enhanced community resilience to droughts and climate variability. |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-12 00:00:00+00 | 31877040 | 31877040 | 15938520 | GOK | NA | 100 | 0 | 31877040 | 100 | 31877040 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 CHAME EARTH PAN | PROPOSED RENOCONSTRUCTION OF 60,000M3 CHAME EARTH PAN | Climate Resilience | Enhanced community resilience to droughts and climate variability. |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-12 00:00:00+00 | 31877040 | 31877040 | 15938520 | GOK | NA | 100 | 0 | 31877040 | 100 | 31877040 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 SILKIN EARTH PAN IN BANISA SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 SILKIN EARTH PAN IN BANISA SUB-COUNTY | Long-Term Water Security | Increased availability of water for domestic and livestock use during dry seasons. |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-19 00:00:00+00 | 31277000 | 31277000 | 15638500 | GOK | NA | 100 | 0 | 31277000 | 100 | 31277000 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 SILKIN EARTH PAN IN BANISA SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 SILKIN EARTH PAN IN BANISA SUB-COUNTY | Long-Term Water Security | Increased availability of water for domestic and livestock use during dry seasons. |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-19 00:00:00+00 | 31277000 | 31277000 | 15638500 | GOK | NA | 100 | 0 | 31277000 | 100 | 31277000 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 SUKELA DERA EARTH PAN IN BANISA SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 SUKELA DERA EARTH PAN IN BANISA SUB-COUNTY | Drought Mitigation |  |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-15 00:00:00+00 | 31137000 | 31137000 | 15568500 | GOK | NA | 100 | 0 | 31137000 | 100 | 31137000 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 SUKELA DERA EARTH PAN IN BANISA SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 SUKELA DERA EARTH PAN IN BANISA SUB-COUNTY | Drought Mitigation |  |  | Water Services | Banisa | Banisa | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-15 00:00:00+00 | 31137000 | 31137000 | 15568500 | GOK | NA | 100 | 0 | 31137000 | 100 | 31137000 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 ALUNG EARTH PAN IN LAFEY SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 ALUNG EARTH PAN IN LAFEY SUB-COUNTY | Agricultural Activities | Increased availability of water for domestic and livestock use during dry seasons. |  | Water Services | Lafey | Alungu | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-30 00:00:00+00 | 32147000 | 32147000 | 16073500 | GOK | NA | 100 | 0 | 32147000 | 100 | 32147000 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 ALUNG EARTH PAN IN LAFEY SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 ALUNG EARTH PAN IN LAFEY SUB-COUNTY | Agricultural Activities | Increased availability of water for domestic and livestock use during dry seasons. |  | Water Services | Lafey | Alungu | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-30 00:00:00+00 | 32147000 | 32147000 | 16073500 | GOK | NA | 100 | 0 | 32147000 | 100 | 32147000 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 FINO EARTH PAN IN LAFEY SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 FINO EARTH PAN IN LAFEY SUB-COUNTY |  | Enhanced community resilience to droughts and climate variability. |  | Water Services | Lafey | Fino | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-11 00:00:00+00 | 31273000 | 31273000 | 15636500 | GOK | NA | 100 | 0 | 31273000 | 100 | 31273000 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOCONSTRUCTION OF 60,000M3 FINO EARTH PAN IN LAFEY SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 FINO EARTH PAN IN LAFEY SUB-COUNTY |  | Enhanced community resilience to droughts and climate variability. |  | Water Services | Lafey | Fino | null | null | Water Services | Water Services | Water Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-11 00:00:00+00 | 31273000 | 31273000 | 15636500 | GOK | NA | 100 | 0 | 31273000 | 100 | 31273000 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED CONSTRUCTION OF MARKET IN ELDANABA MANDERA WEST SUBCOUNTY | PROPOSED CONSTRUCTION OF MARKET IN ELDANABA MANDERA WEST SUBCOUNTY | social inclusion, Economic empwerment and revenue generating | Support for small-scale traders and entrepreneurs |  | Trade | Mandera West | Dandu | null | null | Trade | TRADE | Trade | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-09 00:00:00+00 | 25500524 | 25500524 | 12750262 | GOK | NA | 100 | 0 | 25500524 | 100 | 25500524 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED CONSTRUCTION OF MARKET IN ELDANABA MANDERA WEST SUBCOUNTY | PROPOSED CONSTRUCTION OF MARKET IN ELDANABA MANDERA WEST SUBCOUNTY | social inclusion, Economic empwerment and revenue generating | Support for small-scale traders and entrepreneurs |  | Trade | Mandera West | Dandu | null | null | Trade | TRADE | Trade | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-09 00:00:00+00 | 25500524 | 25500524 | 12750262 | GOK | NA | 100 | 0 | 25500524 | 100 | 25500524 | null | 0 | completed | 100 | 0 | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null |  | TRUE | risk assessments, contengency plan and resources allocation | completed
Proposed Drilling Of 3no. Borehole At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | Proposed Drilling Of 3no. Borehole At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | Ensure access to clean water | increase safer water access for communities |  | water | Mandera South | Takaba | 3.403 | 40.186 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-06 00:00:00+00 | 23280040 | 23280040 | null | GOK | N/A | 100 | 0 | 23280040 | null | 23280040 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Drilling Of 3no. Borehole At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | Proposed Drilling Of 3no. Borehole At Dadach Majani In Mandera South, Kobadadi And Takaba In Mandera West Sub-County | Ensure access to clean water | increase safer water access for communities |  | water | Mandera South | Takaba | 3.403 | 40.186 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-10-06 00:00:00+00 | 23280040 | 23280040 | null | GOK | N/A | 100 | 0 | 23280040 | null | 23280040 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED RENOVATION AND ALTERATION WORKS OF DENTAL UNIT BLOCK IN MANDERA LEVEL IV HOSPITAL MANDERA SUBCOUNTY | PROPOSED RENOVATION AND ALTERATION WORKS OF DENTAL UNIT BLOCK IN MANDERA LEVEL IV HOSPITAL MANDERA SUBCOUNTY | Ensure Compliance with Regulatory Standards | Improve Patient Comfort and Staff Working Conditions | null | Health Services | Mandera East | Neboi | 3.9621 | 41.7703 | Health Services | Health Services | Health Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-28 00:00:00+00 | 9997339.85 | 9997339.85 | 9997340 | GOK | NA | 100 | null | 9997340 | 100 | 9997340 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null | null | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED RENOVATION AND ALTERATION WORKS OF DENTAL UNIT BLOCK IN MANDERA LEVEL IV HOSPITAL MANDERA SUBCOUNTY | PROPOSED RENOVATION AND ALTERATION WORKS OF DENTAL UNIT BLOCK IN MANDERA LEVEL IV HOSPITAL MANDERA SUBCOUNTY | Ensure Compliance with Regulatory Standards | Improve Patient Comfort and Staff Working Conditions | null | Health Services | Mandera East | Neboi | 3.9621 | 41.7703 | Health Services | Health Services | Health Services | Water Services | 2022-07-01 00:00:00+00 | 2022-07-01 00:00:00+00 | 2024-06-30 23:59:59.999+00 | 2022-12-28 00:00:00+00 | 9997339.85 | 9997339.85 | 9997340 | GOK | NA | 100 | null | 9997340 | 100 | 9997340 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Competed | Implementing early warning system and developing emergency response plan | TRUE | Environmental impact assessment and social impact assesment | null | null | TRUE | risk assessments, contengency plan and resources allocation | completed
PROPOSED CONSTRUCTION OF MANDWASCO OFFICE BLOCK IN MANDERA EAST | PROPOSED CONSTRUCTION OF MANDWASCO OFFICE BLOCK IN MANDERA EAST |  |  |  | public works | Mandera East | Township | 3.936 | 41.857 | public works | Public Works | PUBLIC WORKS | Public Works | 2001-08-17 21:00:00+00 | 2018-03-10 00:00:00+00 | 2019-03-10 00:00:00+00 | 2019-01-10 00:00:00+00 | 57411648 | 57411648 | 40000000 | GOK | N/A | 100 | 0 | 57411648 | null | 57411648 | null | null | completed | null | null | N/A | N/A | null | null | null |  |  | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE
MCG/527/2014-2015 | CONSTRUCTION OF ABATTOIR IN MANDERA COUNTY | TO promotes the socio?economic development | Job creation & local economic linkages | null | Construction of World Class Abbattoir | Mandera East | Township | 3.9486 | 41.8525 | TRADE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 9000000 | 8775954 | 8775954 | GOK | N/A | 100 | null | 8775954 | 8775954 | 8775954 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/517/2014-2015 | RFP FOR ENGINEERING DESIGN AND DEVELOPMENT OF WATER SUPPLY RETICULATION, AUTOMATED LEAK DETECTION SYSTEM AND BILLING SYSTEM FOR MANDERA URBAN SUPPLY | null | null | null | Man made lakes and mega dams development Feasibility studies | Mandera East | Township | 3.9486 | 41.8525 | WATER SERVICES | Livestock | Livestock | Livestock | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 52000000 | 50887122 | 50887122 | GOK | N/A | 100 | null | 50887122 | 50887122 | 50887122 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION 60,000M3 EARTH PAN AT DADACH DHEERA IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION 60,000M3 EARTH PAN AT DADACH DHEERA IN MANDERA WEST SUB COUNTY | resource management | increase climate resilence | null | Water Services | Mandera West | Dandu | 3.4907 | 39.943 | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 30900000 | 30900000 | 30900000 | GOK | NA | 100 | null | 30900000 | null | 30900000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION 60,000M3 EARTH PAN AT DADACH DHEERA IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION 60,000M3 EARTH PAN AT DADACH DHEERA IN MANDERA WEST SUB COUNTY | resource management | increase climate resilence | null | Water Services | Mandera West | Dandu | 3.4907 | 39.943 | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 30900000 | 30900000 | 30900000 | GOK | NA | 100 | null | 30900000 | null | 30900000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
Proposed Paved Parking, Wall Finishing And Grading Of Mandera Moi Stadium In Mandera East Sub County | Proposed Paved Parking, Wall Finishing And Grading Of Mandera Moi Stadium In Mandera East Sub County | improve service delivery | paved parking |  |  | Mandera East | null | 3.9331 | 41.847 | Public Works | Public Works | PUBLIC WORKS | Public Works | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-11-21 00:00:00+00 | 9700000 | 9700000 | null | GOK | N/A | null | null | 9700000 | 100 | 9700000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Proposed Improvement Of Elwak Air Strip In Mandera West Sub County | Proposed Improvement Of Elwak Air Strip In Mandera West Sub County | impove road infrustructure | Aistrip |  |  | Mandera South | Elwak South | 2.808 | 40.926 | Roads | ROADS | ROADS | ROADS | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-02-16 00:00:00+00 | 22300179 | 22300179 | 11150090 | GOK | N/A | null | null | 22300179 | 100 | 22300179 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
MCG/59/2014-2015 | EXTENSION OF WATER FROM DANYERE TO AFAFEL | ï¿½To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | null | Rehabilitation/Construction of urban water supplies | Mandera East | Khalalio | 3.9038 | 41.6239 | WATER SERVICES | TRADE | Trade | TRADE | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 15000000 | 14404350 | 14404350 | GOK | N/A | 100 | null | 14404350 | 14404350 | 14404350 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Drilling And Civil Works At Qarsa Hama In Mandera West | Proposed Drilling And Civil Works At Qarsa Hama In Mandera West | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | Takaba | 3.4321 | 39.7898 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-10 00:00:00+00 | 27996287 | 27996287 | 25000000 | GOK | N/A | 100 | 0 | 27996287 | null | 27996287 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Drilling And Civil Works At Qarsa Hama In Mandera West | Proposed Drilling And Civil Works At Qarsa Hama In Mandera West | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | Takaba | 3.4321 | 39.7898 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-10 00:00:00+00 | 27996287 | 27996287 | 25000000 | GOK | N/A | 100 | 0 | 27996287 | null | 27996287 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of 10,000M3 Earth Pan At Girile | Proposed Construction Of 10,000M3 Earth Pan At Girile | Improve access to water | earth pan |  |  | null | null | 3.876 | 40.533 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-13 00:00:00+00 | 30930617 | 30930617 | 30930617 | GOK | N/A | null | null | 30930617 | 100 | 30930617 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Proposed Construction Of 10,000M3 Earth Pan At Girile | Proposed Construction Of 10,000M3 Earth Pan At Girile | Improve access to water | earth pan |  |  | null | null | 3.876 | 40.533 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-13 00:00:00+00 | 30930617 | 30930617 | 30930617 | GOK | N/A | null | null | 30930617 | 100 | 30930617 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
MCG/526/2014-2015 | RFP FOR FEASIBILITY STUDIES, SOCIAL ENVIRONMENTAL IMPACT ASSESSMENT AND DESIGN WORKS FOR ROAD CLASS | improve infrustructure | consultancy | null | completion of the feasibility studies | Mandera East | Township | 3.9486 | 41.8525 | ROADS | ROADS | ROADS | ROADS | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 12000000 | 11326240 | 66000000 | GOK | N/A | 100 | null | 11326240 | 11326240 | 11326240 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 20,000m3 Earth Pan At Allo Saden In Mandera West | Proposed Construction Of 20,000m3 Earth Pan At Allo Saden In Mandera West | promote sustainable water management | clean water |  | water | Mandera West | LAGSURE | 3.5445 | 39.7972 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-22 00:00:00+00 | 9989000 | 9989000 | 9989000 | GOK | N/A | 100 | 0 | 9989000 | null | 9989000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of 20,000m3 Earth Pan At Allo Saden In Mandera West | Proposed Construction Of 20,000m3 Earth Pan At Allo Saden In Mandera West | promote sustainable water management | clean water |  | water | Mandera West | LAGSURE | 3.5445 | 39.7972 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-22 00:00:00+00 | 9989000 | 9989000 | 9989000 | GOK | N/A | 100 | 0 | 9989000 | null | 9989000 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Constrcution Of 60,000M3 Har Dumayo Earth In Banisa, Mandera County | Proposed Constrcution Of 60,000M3 Har Dumayo Earth In Banisa, Mandera County | Improve access to water | earth pan |  |  | null | null | 3.8867 | 40.3074 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-01-02 00:00:00+00 | 32820617 | 32820617 | 32820617 | GOK | N/A | null | null | 32820617 | 100 | 32820617 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Proposed Constrcution Of 60,000M3 Har Dumayo Earth In Banisa, Mandera County | Proposed Constrcution Of 60,000M3 Har Dumayo Earth In Banisa, Mandera County | Improve access to water | earth pan |  |  | null | null | 3.8867 | 40.3074 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-01-02 00:00:00+00 | 32820617 | 32820617 | 32820617 | GOK | N/A | null | null | 32820617 | 100 | 32820617 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Construction of 20,000M3 Earth Pan at HarQora in Qalanqalesa | Construction of 20,000M3 Earth Pan at HarQora in Qalanqalesa | improve water access | water infrustructure | null | null | Mandera South | Shimpir Fatuma | 2.8672 | 40.555 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 97576235 | 97576235 | 59000000 | GOK | null | 100 | null | 97576235 | 97576235 | 97576235 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at HarQora in Qalanqalesa | Construction of 20,000M3 Earth Pan at HarQora in Qalanqalesa | improve water access | water infrustructure | null | null | Mandera South | Shimpir Fatuma | 2.8672 | 40.555 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 97576235 | 97576235 | 59000000 | GOK | null | 100 | null | 97576235 | 97576235 | 97576235 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 30,000m3 Earth Pan At Allo Golbo Ropi In Mandera South | Proposed Construction Of 30,000m3 Earth Pan At Allo Golbo Ropi In Mandera South | improve water quality and sanitation | sustainable water management practices |  | water | Mandera South | Elwak South | 3.5445 | 39.7972 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-21 00:00:00+00 | 19655423 | 19655423 | null | GOK | N/A | 100 | 0 | 19655423 | null | 19655423 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of 30,000m3 Earth Pan At Allo Golbo Ropi In Mandera South | Proposed Construction Of 30,000m3 Earth Pan At Allo Golbo Ropi In Mandera South | improve water quality and sanitation | sustainable water management practices |  | water | Mandera South | Elwak South | 3.5445 | 39.7972 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-08-21 00:00:00+00 | 19655423 | 19655423 | null | GOK | N/A | 100 | 0 | 19655423 | null | 19655423 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of 20,000 M3 Earth Pan At Kubi Koyeti In Mandera West Sub County | Proposed Construction Of 20,000 M3 Earth Pan At Kubi Koyeti In Mandera West Sub County | Improve access to water | earth pan |  |  | Mandera West | Gither | 3.7409 | 39.8593 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-02-12 00:00:00+00 | 12000000 | 12000000 | 12000000 | GOK | N/A | null | null | 12000000 | 100 | 12000000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Proposed Construction Of 20,000 M3 Earth Pan At Kubi Koyeti In Mandera West Sub County | Proposed Construction Of 20,000 M3 Earth Pan At Kubi Koyeti In Mandera West Sub County | Improve access to water | earth pan |  |  | Mandera West | Gither | 3.7409 | 39.8593 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-02-12 00:00:00+00 | 12000000 | 12000000 | 12000000 | GOK | N/A | null | null | 12000000 | 100 | 12000000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Kutulo water supply rehabilitation, Mandera South | Kutulo water supply rehabilitation, Mandera South | improve water access | water infrustructure | null | null | Mandera South | Kutulo | 2.5481 | 40.7047 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33434940 | 33434940 | 33434940 | GOK | null | 100 | null | 33434940 | 33434940 | 33434940 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Kutulo water supply rehabilitation, Mandera South | Kutulo water supply rehabilitation, Mandera South | improve water access | water infrustructure | null | null | Mandera South | Kutulo | 2.5481 | 40.7047 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33434940 | 33434940 | 33434940 | GOK | null | 100 | null | 33434940 | 33434940 | 33434940 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT ADALA DIMTU EARTH PAN IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT ADALA DIMTU EARTH PAN IN MANDERA WEST SUB COUNTY | food security | boast food security | null | Water Services | Mandera West | Dandu | 3.4907 | 39.943 | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 14480000 | 14480000 | 14480000 | GOK | NA | 100 | null | 14480000 | null | 14480000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT ADALA DIMTU EARTH PAN IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT ADALA DIMTU EARTH PAN IN MANDERA WEST SUB COUNTY | food security | boast food security | null | Water Services | Mandera West | Dandu | 3.4907 | 39.943 | Water Services | Water Services | Water Services | Water Services | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 14480000 | 14480000 | 14480000 | GOK | NA | 100 | null | 14480000 | null | 14480000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
Kobe earthpan | Kobe earthpan | improved water access | Kobe earth pan | MCG/OT/30/2019-2020 |  | Mandera West | Takaba | 3.403 | 40.186 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-01-04 00:00:00+00 | 10000000 | 10000000 | 10000000 |  | N/A | null | null | 10000000 | 100 | 10000000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Kobe earthpan | Kobe earthpan | improved water access | Kobe earth pan | MCG/OT/30/2019-2020 |  | Mandera West | Takaba | 3.403 | 40.186 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-01-04 00:00:00+00 | 10000000 | 10000000 | 10000000 |  | N/A | null | null | 10000000 | 100 | 10000000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Construction of khalafow water supply system in Mandera West | Construction of khalafow water supply system in Mandera West | improve access to services | water infrustructure | MCG/OT/40/2019-2020 |  | Mandera West | Gither | 3.73 | 39.92 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-24 00:00:00+00 | 19995500 | 19995500 | 19995500 |  | N/A | null | null | null | null | null | null | 19995500 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Construction of khalafow water supply system in Mandera West | Construction of khalafow water supply system in Mandera West | improve access to services | water infrustructure | MCG/OT/40/2019-2020 |  | Mandera West | Gither | 3.73 | 39.92 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-24 00:00:00+00 | 19995500 | 19995500 | 19995500 |  | N/A | null | null | null | null | null | null | 19995500 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Desilting and expansion of 20000m3 at Sukela loqo in Mandera West | Desilting and expansion of 20000m3 at Sukela loqo in Mandera West | Improve access to water | earth pan | MCG/OT/38/2019-2020 |  | Mandera West | Takaba | 3.403 | 40.186 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-02-28 00:00:00+00 | 9999265 | 9999265 | 9999265 |  | N/A | null | null | null | null | null | null | 9999265 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Desilting and expansion of 20000m3 at Sukela loqo in Mandera West | Desilting and expansion of 20000m3 at Sukela loqo in Mandera West | Improve access to water | earth pan | MCG/OT/38/2019-2020 |  | Mandera West | Takaba | 3.403 | 40.186 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-02-28 00:00:00+00 | 9999265 | 9999265 | 9999265 |  | N/A | null | null | null | null | null | null | 9999265 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
PROPOSED CIVIL WORKS AT MANDERA COUNTY PUBLIC SERVICE BOARD OFFICE IN MANDERA EAST | PROPOSED CIVIL WORKS AT MANDERA COUNTY PUBLIC SERVICE BOARD OFFICE IN MANDERA EAST | improve the functionality, safety, and working environment | Improved working environment | MCG/OT/062/2023-2024 | null | Mandera East | Neboi | 3.9621 | 41.7703 | PUBLIC WORKS | Public Works | PUBLIC WORKS | Public Works | 2023-07-01 00:00:00+00 | 2024-04-14 21:00:00+00 | 2025-04-13 21:00:00+00 | 2025-04-13 21:00:00+00 | 17965500 | 17965500 | 7000000 | GOK | N/A | null | null | null | null | 12965500 | null | 5000000 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED EXPANSION OF KOKOTO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | PROPOSED EXPANSION OF KOKOTO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera West | Takaba | 3.4031 | 40.1857 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-17 00:00:00+00 | 13248210 | 13248210 | null | GOK | N/A | 100 | 0 | 13248210 | null | 13248210 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED EXPANSION OF KOKOTO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | PROPOSED EXPANSION OF KOKOTO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera West | Takaba | 3.4031 | 40.1857 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-17 00:00:00+00 | 13248210 | 13248210 | null | GOK | N/A | 100 | 0 | 13248210 | null | 13248210 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction And Expantion Of 60,000M3 At Chuqal Earth In Mandera South Sub-County | Proposed Construction And Expantion Of 60,000M3 At Chuqal Earth In Mandera South Sub-County | Improve access to water | earth pan | null | null | Mandera South | Kutulo | 2.5481 | 40.7047 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-26 00:00:00+00 | 30992230 | 30992230 | 15496115 | GOK | N/A | null | null | 30992230 | 100 | 30992230 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Proposed Construction And Expantion Of 60,000M3 At Chuqal Earth In Mandera South Sub-County | Proposed Construction And Expantion Of 60,000M3 At Chuqal Earth In Mandera South Sub-County | Improve access to water | earth pan | null | null | Mandera South | Kutulo | 2.5481 | 40.7047 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-26 00:00:00+00 | 30992230 | 30992230 | 15496115 | GOK | N/A | null | null | 30992230 | 100 | 30992230 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Upgrading of Elben Ashabito road to gravel standard | Upgrading of Elben Ashabito road to gravel standard | improved road network | road network | MCG/OT/RMLF/06/2019-2020 |  | Mandera North | ASHABITO | 3.768 | 41.134 | Roads | ROADS | ROADS | ROADS | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-01-31 00:00:00+00 | 29907900 | 29907900 | 29907900 |  | N/A | null | null | null | null | null | null | 29907900 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Supply and Delivery of 45NO Laptop to Mandera County Governent | Supply and Delivery of 45NO Laptop to Mandera County Governent | To be used for the county activities | Improved efficiecy and time management | MCG/OT/088/2017-2018 | null | Mandera East | Township | 3.9486 | 41.8525 | ICT | ICT | ICT | ICT | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 5499000 | 5499000 | 5499000 | GOK | N/A | 100 | null | 5499000 | 5499000 | 5499000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED DESILTING AND EXPANSION OF YAQILA EARTHPAN BY 20,000 CUBIC METRE IN MANDERA NORTH SUB-COUNTY | PROPOSED DESILTING AND EXPANSION OF YAQILA EARTHPAN BY 20,000 CUBIC METRE IN MANDERA NORTH SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera North | Rhamu | 3.9483 | 41.1807 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-08 00:00:00+00 | 9999780 | 9999780 | 9999780 | GOK | N/A | 100 | 0 | 9999780 | null | 9999780 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED DESILTING AND EXPANSION OF YAQILA EARTHPAN BY 20,000 CUBIC METRE IN MANDERA NORTH SUB-COUNTY | PROPOSED DESILTING AND EXPANSION OF YAQILA EARTHPAN BY 20,000 CUBIC METRE IN MANDERA NORTH SUB-COUNTY | promote sustainable water management | clean water |  | water | Mandera North | Rhamu | 3.9483 | 41.1807 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-08 00:00:00+00 | 9999780 | 9999780 | 9999780 | GOK | N/A | 100 | 0 | 9999780 | null | 9999780 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed construction of 30,000M3 Earthpan in Hardimtu in Banisa Sub county | Proposed construction of 30,000M3 Earthpan in Hardimtu in Banisa Sub county | improve water access | water infrustructure | null | null | Banisa | Banisa | 3.7309 | 40.9879 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 15871073 | 15871073 | 15871073 | GOK | null | 100 | null | 15871073 | 15871073 | 15871073 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of 30,000M3 Earthpan in Hardimtu in Banisa Sub county | Proposed construction of 30,000M3 Earthpan in Hardimtu in Banisa Sub county | improve water access | water infrustructure | null | null | Banisa | Banisa | 3.7309 | 40.9879 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 15871073 | 15871073 | 15871073 | GOK | null | 100 | null | 15871073 | 15871073 | 15871073 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF AIR STRIP AT KARO IN MANDERA EAST SUB COUNTY | PROPOSED CONSTRUCTION OF AIR STRIP AT KARO IN MANDERA EAST SUB COUNTY | The project will deliver a fully constructed and operational airstrip including runway, drainage systems, and essential support infrastructure | Improve air transport in the region | null | Road/public works | Mandera East | Khalalio | 3.9038 | 41.6239 | public works | Public Works | PUBLIC WORKS | Public Works | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-12-31 00:00:00+00 | 144237204 | 144237204 | null | GOK | N/A | 100 | null | null | null | null | null | null | stalled | null | 100 | Resident community rejected the project | 2019 | 24 | 145000000 | null | Strengthen stakeholders engagment | null | null | null | null | null | null | null | stalled
Proposed Construction Male Hostel at Mandera ECDE college in Mandera East Sub-county | Proposed Construction Male Hostel at Mandera ECDE college in Mandera East Sub-county | To increase enrolment | Male hostel built | null | null | Mandera East | Neboi | 3.9621 | 41.7703 | Education | EDUCATION | EDUCATION | EDUCATION | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 24847200 | 24847200 | 15134864 | GOK | null | 100 | null | 24847200 | 24847200 | 24847200 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF CHAINLINK FENCING OF ISLAMIC AND SECULAR UNIVERSITY COMPOUND | PROPOSED CONSTRUCTION OF CHAINLINK FENCING OF ISLAMIC AND SECULAR UNIVERSITY COMPOUND | to avoid materials theft and restrict learners from absentesim | improve security | null | Education | Mandera East | Neboi | 3.9621 | 41.7703 | Education | EDUCATION | EDUCATION | EDUCATION | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 36000136 | 36000136 | 36000136 | GOK | NA | 100 | null | 36000136 | null | 36000136 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
Proposed Completion Of Harshilmi Mordern Primary School In Mandera West Sub County | Proposed Completion Of Harshilmi Mordern Primary School In Mandera West Sub County | improve access to education | A model ECDE |  | Balance of Harshilmi strategic boarding school | Mandera West | Gither | 3.6002 | 39.7415 | Education | EDUCATION | EDUCATION | EDUCATION | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-03-21 00:00:00+00 | 38846312 | 38846312 | 34558616 | GOK | N/A | null | null | 38846312 | 100 | 38846312 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT DADACH ROPISA IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT DADACH ROPISA IN MANDERA WEST SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | Dandu | 3.5673 | 39.8109 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-04 00:00:00+00 | 11744300 | 11744300 | 11744300 | GOK | N/A | 100 | 0 | 11744300 | null | 11744300 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT DADACH ROPISA IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT DADACH ROPISA IN MANDERA WEST SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | water | Mandera West | Dandu | 3.5673 | 39.8109 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-09-04 00:00:00+00 | 11744300 | 11744300 | 11744300 | GOK | N/A | 100 | 0 | 11744300 | null | 11744300 | null | null | completed | null | null | N/A | N/A | null | null | null |  | N/A | FALSE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Constructions of Road Takaba-Bolowle Road to all weather ï¿½murrum standard 35 KM | Proposed Constructions of Road Takaba-Bolowle Road to all weather ï¿½murrum standard 35 KM | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | null | null | Mandera West | Takaba | 3.4911 | 40.1095 | ROADS | ROADS | ROADS | ROADS | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 73982538 | 73982538 | 30000000 | GOK | null | 100 | null | 73982538 | 73982538 | 73982538 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCION OF 50NO TOILETS FOR VULNERABLE FAMILIES IN NEBOI LOCATION IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCION OF 50NO TOILETS FOR VULNERABLE FAMILIES IN NEBOI LOCATION IN MANDERA EAST SUB-COUNTY | public health protection | promote hygiene protection | null | Special programme | Mandera East | Neboi | 3.9621 | 41.7703 | special programme | special programme | special programme | special programme | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 10000000 | 10000000 | 10000000 | GOK | NA | 100 | null | 10000000 | null | 10000000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
PROPOSED CONSTRUCION OF 50NO TOILETS FOR VULNERABLE FAMILIES IN NEBOI LOCATION IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCION OF 50NO TOILETS FOR VULNERABLE FAMILIES IN NEBOI LOCATION IN MANDERA EAST SUB-COUNTY | public health protection | promote hygiene protection | null | Special programme | Mandera East | Neboi | 3.9621 | 41.7703 | special programme | special programme | special programme | SPECIAL PROGRAMME | 2021-07-01 00:00:00+00 | 2021-07-01 00:00:00+00 | 2023-06-30 23:59:59.999+00 | 2023-06-30 23:59:59.999+00 | 10000000 | 10000000 | 10000000 | GOK | NA | 100 | null | 10000000 | null | 10000000 | null | null | completed | 100 | null | NA | NA | null | null | TRUE | Compete | Implementing early warning system and developing emergency response plan | TRUE | Imlementing early warning, civic Education and Environmental Impact | TRUE | Environmental Impact asseesment | TRUE | Risk assesment & contigengy planning | Complete
Proposed Water Supply For Koromey Farms Irrigation Infrastructure | Proposed Water Supply For Koromey Farms Irrigation Infrastructure | improve food production | water infrustructure |  | Proposed Water supply for Koromey farms irrigation infrastructure | Mandera East | Township | 3.8952 | 41.7879 | Roads | ROADS | ROADS | ROADS | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-03-11 00:00:00+00 | 263364200 | 263364200 | 128000000 | GOK | N/A | null | null | 263364200 | 100 | 263364200 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | improve water access | water infrustructure | null | null | Banisa | DERKALE | 3.05 | 40.4 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10881045 | 10881045 | 10881045 | GOK | null | 100 | null | 10881045 | 10881045 | 10881045 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | improve water access | water infrustructure | null | null | Banisa | DERKALE | 3.05 | 40.4 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10881045 | 10881045 | 10881045 | GOK | null | 100 | null | 10881045 | 10881045 | 10881045 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Improvement of Hareri water supply (Tanks,Kiosks) | Improvement of Hareri water supply (Tanks,Kiosks) | improve access to water | water infrustructure | null | null | Mandera East | ARABIA | 3.7636 | 41.3584 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 5995810 | 5995810 | 5995810 | GOK | N/A | 100 | null | 5995810 | 5995810 | 5995810 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Improvement of Hareri water supply (Tanks,Kiosks) | Improvement of Hareri water supply (Tanks,Kiosks) | improve access to water | water infrustructure | null | null | Mandera East | ARABIA | 3.7636 | 41.3584 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 5995810 | 5995810 | 5995810 | GOK | N/A | 100 | null | 5995810 | 5995810 | 5995810 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Desilting and expansion of 20000m3 earthpan at Laga Goljo in Banisa | Desilting and expansion of 20000m3 earthpan at Laga Goljo in Banisa | improved water access | earth pan | MCG/OT/36/2019-2020 | null | Banisa | Malkamari | 4.0876 | 40.7342 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-29 00:00:00+00 | 11995095 | 11995095 | 11995095 | null | N/A | null | null | null | null | null | null | 11995095 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Desilting and expansion of 20000m3 earthpan at Laga Goljo in Banisa | Desilting and expansion of 20000m3 earthpan at Laga Goljo in Banisa | improved water access | earth pan | MCG/OT/36/2019-2020 | null | Banisa | Malkamari | 4.0876 | 40.7342 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-29 00:00:00+00 | 11995095 | 11995095 | 11995095 | null | N/A | null | null | null | null | null | null | 11995095 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Construction of 20,000M3 Earth Pan at Ban Qayam-Banisa | Construction of 20,000M3 Earth Pan at Ban Qayam-Banisa | improve water access | water infrustructure | null | null | Banisa | Guba | 3.9663 | 40.519 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10453590 | 10453590 | 10453590 | GOK | null | 100 | null | 10453590 | 10453590 | 10453590 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Ban Qayam-Banisa | Construction of 20,000M3 Earth Pan at Ban Qayam-Banisa | improve water access | water infrustructure | null | null | Banisa | Guba | 3.9663 | 40.519 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10453590 | 10453590 | 10453590 | GOK | null | 100 | null | 10453590 | 10453590 | 10453590 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 20,000M3 Ameyi Earth Pan | Proposed Construction Of 20,000M3 Ameyi Earth Pan | to ensure access to clean water | Ameyi Earth pan | MCG/OT/46,21/2020-2021 | Construction of 20,000 M3 Earth Pan at Ameyi in Banisa Sub-County | Banisa | Kiliweheri | 4.0378 | 40.1911 | Water Services | Water Services | Water Services | Water Services | 2020-12-07 21:00:00+00 | 2021-12-03 21:00:00+00 | 2022-04-27 21:00:00+00 | 2022-04-27 21:00:00+00 | 9653143 | 9653143 | 5000000 | GOK | NA | 100 | null | null | 100 | 44679 | null | null | completed | null | null | NA | NA | null | null | null | null | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Proposed Construction Of 20,000M3 Ameyi Earth Pan | Proposed Construction Of 20,000M3 Ameyi Earth Pan | to ensure access to clean water | Ameyi Earth pan | MCG/OT/46,21/2020-2021 | Construction of 20,000 M3 Earth Pan at Ameyi in Banisa Sub-County | Banisa | Kiliweheri | 4.0378 | 40.1911 | Water Services | Water Services | Water Services | Water Services | 2020-12-07 21:00:00+00 | 2021-12-03 21:00:00+00 | 2022-04-27 21:00:00+00 | 2022-04-27 21:00:00+00 | 9653143 | 9653143 | 5000000 | GOK | NA | 100 | null | null | 100 | 44679 | null | null | completed | null | null | NA | NA | null | null | null | null | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
construction of 3No. Wards, maternity block, laboratory block and store at Banisa level IV Hospital | construction of 3No. Wards, maternity block, laboratory block and store at Banisa level IV Hospital | improve access to health services | wards and maternities | MCG/OT/024/2019-2020 | null | Banisa | Banisa | 3.9442 | 40.3256 | Health Services | Health Services | Health Services | Health Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-02-06 00:00:00+00 | 98608385 | 98608385 | 98608385 | null | N/A | null | null | null | null | null | null | 98608385 | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
installation of open drip kits with water tank tower and supply of 5000litres plastic water tank at Alati, Mandera West | installation of open drip kits with water tank tower and supply of 5000litres plastic water tank at Alati, Mandera West | improve water access | water infrustructure | null | null | Mandera West | Dandu | 3.4907 | 39.943 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33839904 | 33839904 | 33839904 | GOK | null | 100 | null | 33839904 | 33839904 | 33839904 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
installation of open drip kits with water tank tower and supply of 5000litres plastic water tank at Alati, Mandera West | installation of open drip kits with water tank tower and supply of 5000litres plastic water tank at Alati, Mandera West | improve water access | water infrustructure | null | null | Mandera West | Dandu | 3.4907 | 39.943 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33839904 | 33839904 | 33839904 | GOK | null | 100 | null | 33839904 | 33839904 | 33839904 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT GARBI IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT GARBI IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | null | water | Banisa | Banisa | 4.1124 | 40.8695 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-27 00:00:00+00 | 9267720 | 9267720 | 9267720 | GOK | N/A | 100 | null | 9267720 | null | 9267720 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT GARBI IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT GARBI IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | null | water | Banisa | Banisa | 4.1124 | 40.8695 | Water services | Water Services | Water Services | Water Services | 2018-08-10 00:00:00+00 | 2018-12-10 00:00:00+00 | 2019-12-09 00:00:00+00 | 2019-06-27 00:00:00+00 | 9267720 | 9267720 | 9267720 | GOK | N/A | 100 | null | 9267720 | null | 9267720 | null | null | completed | null | null | N/A | N/A | null | null | null | null | N/A | null | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | null | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
Kob Adhadi Masonry water Tank 100m3 | Kob Adhadi Masonry water Tank 100m3 | improve access to water | water infrustructure | null | null | Mandera West | Gither | 3.7055 | 39.954 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 4115305 | 4115305 | 4115305 | GOK | N/A | 100 | null | 4115305 | 4115305 | 4115305 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Kob Adhadi Masonry water Tank 100m3 | Kob Adhadi Masonry water Tank 100m3 | improve access to water | water infrustructure | null | null | Mandera West | Gither | 3.7055 | 39.954 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 4115305 | 4115305 | 4115305 | GOK | N/A | 100 | null | 4115305 | 4115305 | 4115305 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Kobe lagi earth pan in Mandera West | Kobe lagi earth pan in Mandera West | improved water access | earth pan | MCG/OT/26/2019-2020 |  | Mandera West | Takaba | 3.403 | 40.186 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-01-12 00:00:00+00 | 30998001 | 30998001 | 30998001 |  | N/A | null | null | 30998001 | 100 | 30998001 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Kobe lagi earth pan in Mandera West | Kobe lagi earth pan in Mandera West | improved water access | earth pan | MCG/OT/26/2019-2020 |  | Mandera West | Takaba | 3.403 | 40.186 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-01-12 00:00:00+00 | 30998001 | 30998001 | 30998001 |  | N/A | null | null | 30998001 | 100 | 30998001 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Water supply system for Bulla Afya -Elwak | Water supply system for Bulla Afya -Elwak | improved water access | water infrustructure | MCG/OT/38/19/20 |  | Mandera South | Elwak South | 2.7977 | 40.925 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-12 00:00:00+00 | 20000000 | 20000000 | 20000000 |  | N/A | null | null | 20000000 | 100 | 20000000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Water supply system for Bulla Afya -Elwak | Water supply system for Bulla Afya -Elwak | improved water access | water infrustructure | MCG/OT/38/19/20 |  | Mandera South | Elwak South | 2.7977 | 40.925 | Water Services | Water Services | Water Services | Water Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2019-12-12 00:00:00+00 | 20000000 | 20000000 | 20000000 |  | N/A | null | null | 20000000 | 100 | 20000000 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Proposed Repair And Maintenance Of Accident And Emergency Centres And Maternity Centres At Mcrh And Elwak Referral Hospitals In Mandera County | Proposed Repair And Maintenance Of Accident And Emergency Centres And Maternity Centres At Mcrh And Elwak Referral Hospitals In Mandera County | improve access to health services | Accident and Emergency | MCG/OT/MOH/05/2019-2020 | adjustment to MCRH Accident and Emergency ICU and Ward area as well as replacement of tiles with Terrazo | Mandera East | null | 3.9425 | 41.8612 | Health Services | Health Services | Health Services | Health Services | 2019-08-05 00:00:00+00 | 2020-04-04 00:00:00+00 | 2021-04-03 00:00:00+00 | 2020-03-22 00:00:00+00 | 31793802 | 31793802 | 37000000 | GOK | N/A | null | null | 31793802 | 100 | 31793802 | null | null | completed | 100 | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | complete
Proposed Construction Of Drift On Lagsure At Kiliwehiri In Kiliwehiri Sub-County. | Proposed Construction Of Drift On Lagsure At Lagsure In Mandera West Sub-County. | improve access to roads | Lagsure drift | null | Construction of Drift at Lagsure in Lagsure ward | Mandera West | LAGSURE | 3.4068 | 40.2256 | Roads | ROADS | ROADS | ROADS | 2020-12-07 21:00:00+00 | 2021-12-03 21:00:00+00 | 2023-04-29 21:00:00+00 | 2023-04-29 21:00:00+00 | 21801620 | 21801620 | 9000000 | GOK | NA | 100 | null | null | 100 | 45046 | null | null | completed | null | null | NA | NA | null | null | null | null | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/T/31/2015-2016 | Construction of new 60,000m3 Earth Pan at Nyatalio, Mandera South | improve water access | water infrustructure | null | null | Mandera South | Kutulo | 2.5481 | 40.7047 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11688849 | 11688849 | 11688849 | GOK | N/A | 100 | null | 11688849 | 11688849 | 11688849 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/31/2015-2016 | Construction of new 60,000m3 Earth Pan at Nyatalio, Mandera South | improve water access | water infrustructure | null | null | Mandera South | Kutulo | 2.5481 | 40.7047 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11688849 | 11688849 | 11688849 | GOK | N/A | 100 | null | 11688849 | 11688849 | 11688849 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/90/2013-2014 | Masonry Tank 100m3 at Odha | improve access to water | water infrustructure | null | null | Mandera East | Arabia | 3.6404 | 41.5127 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 4139586 | 4139586 | 4139586 | GOK | N/A | 100 | null | 4139586 | 4139586 | 4139586 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/90/2013-2014 | Masonry Tank 100m3 at Odha | improve access to water | water infrustructure | null | null | Mandera East | Arabia | 3.6404 | 41.5127 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 4139586 | 4139586 | 4139586 | GOK | N/A | 100 | null | 4139586 | 4139586 | 4139586 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction 20,000M3 Earthpan in Waranqara in Lafey Sub county | Proposed construction 20,000M3 Earthpan in Waranqara in Lafey Sub county | improve water access | water infrustructure | null | null | Lafey | WARANQARA | 3.7309 | 40.9879 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11520633 | 11520633 | 11520633 | GOK | null | 100 | null | 11520633 | 11520633 | 11520633 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction 20,000M3 Earthpan in Waranqara in Lafey Sub county | Proposed construction 20,000M3 Earthpan in Waranqara in Lafey Sub county | improve water access | water infrustructure | null | null | Lafey | WARANQARA | 3.7309 | 40.9879 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11520633 | 11520633 | 11520633 | GOK | null | 100 | null | 11520633 | 11520633 | 11520633 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/05/2015-2016 | Construction of 20,000M3 Earth Pan at HarQora in Qalanqalesa | improve water access | water infrustructure | null | null | Mandera South | Shimpir Fatuma | 3.8124 | 41.3016 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 97576235 | 97576235 | 59000000 | GOK | N/A | 100 | null | 97576235 | 97576235 | 97576235 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/05/2015-2016 | Construction of 20,000M3 Earth Pan at HarQora in Qalanqalesa | improve water access | water infrustructure | null | null | Mandera South | Shimpir Fatuma | 3.8124 | 41.3016 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 97576235 | 97576235 | 59000000 | GOK | N/A | 100 | null | 97576235 | 97576235 | 97576235 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Upgrading Of Malka Punda Road To Bitumen Standard In Mandera East Sub-County. | Proposed Upgrading Of Malka Punda Road To Bitumen Standard In Mandera East Sub-County. | improve the standard and quality of roads | Tarmacked road and parking | null | Low Volume seal tarmac road to Malka Punda and Parking at River Access Point (KUSP) | Mandera East | Neboi | 3.9621 | 41.7703 | Roads | ROADS | ROADS | ROADS | 2020-12-07 21:00:00+00 | 2021-12-03 21:00:00+00 | 2022-04-29 21:00:00+00 | 2022-04-29 21:00:00+00 | 169239439 | 169239439 | 102000000 | GOK | NA | 100 | null | null | 100 | 44681 | null | null | completed | null | null | NA | NA | null | null | null | null | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed
MCG/T/53/2015-2016 | Construction of 20,000M3 Earth Pan at Danicha | improve water access | water infrustructure | null | null | Mandera West | Dandu | 3.4907 | 39.943 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10900000 | 10900000 | 10900000 | GOK | N/A | 100 | null | 10900000 | 10900000 | 10900000 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/53/2015-2016 | Construction of 20,000M3 Earth Pan at Danicha | improve water access | water infrustructure | null | null | Mandera West | Dandu | 3.4907 | 39.943 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10900000 | 10900000 | 10900000 | GOK | N/A | 100 | null | 10900000 | 10900000 | 10900000 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/233/2013-2024 | Construction Of Administration Police Housing Units, | Improve service delivery | Police unit | null | null | Mandera East | Township | 3.9486 | 41.8525 | PUBLIC SERVICE | Public Service | Public Service | Public Service | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 23000000 | 20000000 | 20000000 | GOK | N/A | 100 | null | 20000000 | 20000000 | 20000000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/44/2015-2016 | Proposed construction of 20,000m3 earth pan in Derkale | improve water access | water infrustructure | null | null | Banisa | DERKALE | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11520633 | 11520633 | 11520633 | GOK | N/A | 100 | null | 11520633 | 11520633 | 11520633 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/44/2015-2016 | Proposed construction of 20,000m3 earth pan in Derkale | improve water access | water infrustructure | null | null | Banisa | DERKALE | 3.9366 | 41.8569 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11520633 | 11520633 | 11520633 | GOK | N/A | 100 | null | 11520633 | 11520633 | 11520633 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Constructions of Gabions measuring 350m x2m x1m at Malika Kuma Mandera North Sub-County | Proposed Constructions of Gabions measuring 350m x2m x1m at Malika Kuma Mandera North Sub-County | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | Rhamu | 3.9106 | 41.2146 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11712172 | 11712172 | 9500000 | GOK |  | 100 | null | 11712172 | 11712172 | 11712172 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/79/2013-2014 | Drilling of 3 boreholes in Banisa (Kiliweheri,Hullow and Derkale ) | improve access to water | water infrustructure | null | null | Banisa | Kiliweheri | 3.0386 | 40.2389 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 15476000 | 15476000 | 15476000 | GOK | N/A | 100 | null | 15476000 | 15476000 | 15476000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/79/2013-2014 | Drilling of 3 boreholes in Banisa (Kiliweheri,Hullow and Derkale ) | improve access to water | water infrustructure | null | null | Banisa | Kiliweheri | 3.0386 | 40.2389 | WATER SERVICES | Water Services | Water Services | Water Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 15476000 | 15476000 | 15476000 | GOK | N/A | 100 | null | 15476000 | 15476000 | 15476000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
CG/T/151/2015-2016 | Proposed Constructions of Road Takaba-Bolowle Road to all weather ï¿½murrum standard 35 KM | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | null | null | Mandera West | Takaba | 3.4911 | 40.1095 | ROADS | Livestock | Livestock | Livestock | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 73982538 | 73982538 | 30000000 | GOK | N/A | 100 | null | 73982538 | 73982538 | 73982538 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan in Saikala Tainfa, Mandera North | Construction of new 60,000m3 Earth Pan in Saikala Tainfa, Mandera North | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | ASHABITO | 3.9246 | 41.2051 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32706660 | 32706660 | 25000000 | GOK |  | 100 | null | 32706660 | 32706660 | 32706660 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan in Saikala Tainfa, Mandera North | Construction of new 60,000m3 Earth Pan in Saikala Tainfa, Mandera North | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | ASHABITO | 3.9246 | 41.2051 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32706660 | 32706660 | 25000000 | GOK |  | 100 | null | 32706660 | 32706660 | 32706660 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/206/2013-2014 | Construction Medical Diagnostic center in Takaba, Mandera County | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | null | null | Mandera West | Takaba | 3.4911 | 40.1095 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 35000000 | 34490815 | 34490815 | GOK | N/A | 100 | null | 34490815 | 34490815 | 34490815 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/25/2015-2016 | Proposed construction of 500m long raised canal with distribution box, sitling basin and water control gate at Fiqoo Farm, Mandera East Sub-County | null | Raised canal | null | null | Mandera East | Khalalio | 3.9038 | 41.6239 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 8800000 | 8800000 | 8800000 | GOK | N/A | 100 | null | 8800000 | 8800000 | 8800000 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Extension of Water Supply to Morothile | Extension of Water Supply to Morothile | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | MOROTHILE | 3.9552 | 41.2451 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10301557.6 | 10301558 | 10301558 | GOK |  | 100 | null | 10301558 | 10301558 | 10301558 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Extension of Water Supply to Morothile | Extension of Water Supply to Morothile | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | MOROTHILE | 3.9552 | 41.2451 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10301557.6 | 10301558 | 10301558 | GOK |  | 100 | null | 10301558 | 10301558 | 10301558 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Purchase and delivery of computers Hardware equipment | Purchase and delivery of computers Hardware equipment | Improve ICT | computer equipment | null | null | Mandera East | Township | 3.9486 | 41.8525 | ICT | ICT | ICT | ICT | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 25000000 | 24839769 | null | GOK | N/A | 100 | null | 24839769 | 24839769 | 24839769 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/24/2015-2016 | Proposed construction of Gabions measuring 50m x4m x4m at Aresa Scheme Mandera East Sub-County | null | Gabions constructed | null | irrigation development for BP1, Gadudia, Aresa, Shantoley and Rhamu Dimtu | Mandera East | Libihiya | 3.7451 | 41.2886 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11697973 | 11697973 | 21000000 | GOK | N/A | 100 | null | 11697973 | 11697973 | 11697973 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/19/2015-2016 | Proposed Construction Male Hostel at Mandera Teachers Training College college in Mandera East Sub-county | To increase enrolment | Male hostel built | null | Construction of male hostel at MTTC | Mandera East | Neboi | 3.9621 | 41.7703 | Education | ROADS | ROADS | ROADS | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 24847200 | 24847200 | 15134864 | GOK | N/A | 100 | null | 24847200 | 24847200 | 24847200 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/196/2013-2014 | Supply & delivery of other assorted medical equipments to MCRH | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | null | null | Mandera East | Neboi | 3.9621 | 41.7703 | HEALTH SERVICES | Health Services | Health Services | Health Services | 2013-07-01 00:00:00+00 | 2014-07-01 00:00:00+00 | 2016-06-30 23:59:59.999+00 | 2016-06-30 23:59:59.999+00 | 55000000 | 54046300 | 54046300 | GOK | N/A | 100 | null | 54046300 | 54046300 | 54046300 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Constructions of Road Mandera ï¿½ Khalalio Road to all weather ï¿½murrum standard (28 KM) | Proposed Constructions of Road Mandera ï¿½ Khalalio Road to all weather ï¿½murrum standard (28 KM) | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods |  |  | Mandera East | Khalalio | 3.8 | 41.35 | Roads | ROADS | ROADS | ROADS | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 124178858.6 | 124178859 | 241888000 | GOK |  | 100 | null | 124178859 | 124178859 | 124178859 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of social Hall in Khalalio, Mandera East | Proposed construction of social Hall in Khalalio, Mandera East | improve infrustructure | Social Hall |  |  | Mandera East | Khalalio | 3.7851 | 41.3368 | Social services | Social Services | Social Services | Social Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 7999398 | 7999398 | 7999398 | GOK |  | 100 | null | 7999398 | 7999398 | 7999398 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction of Female Hostel at Mandera ECDE college in Mandera East Sub-county | Proposed Construction of Female Hostel at Mandera ECDE college in Mandera East Sub-county | null | Female Hostel built | null | null | Mandera East | Neboi | 3.9621 | 41.7703 | Education | EDUCATION | EDUCATION | EDUCATION | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 23750000 | 23750000 | 17644273 | GOK | null | 100 | null | 23750000 | 23750000 | 23750000 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of Gabions measuring 50m x4m x4m at Aresa Scheme Mandera East Sub-County | Proposed construction of Gabions measuring 50m x4m x4m at Aresa Scheme Mandera East Sub-County | null | Gabions constructed | null | null | Mandera East | Libihiya | 3.7451 | 41.2886 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11697973 | 11697973 | 21000000 | GOK | null | 100 | null | 11697973 | 11697973 | 11697973 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of 500m long raised canal with distribution box, sitling basin and water control gate at Fiqo Farm, Mandera East Sub-County | Proposed construction of 500m long raised canal with distribution box, sitling basin and water control gate at Fiqo Farm, Mandera East Sub-County | null | Raised canal | null | null | Mandera East | Khalalio | 3.9038 | 41.6239 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 8800000 | 8800000 | 8800000 | GOK | null | 100 | null | 8800000 | 8800000 | 8800000 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
onstruction of new 60,000m3 Earth Pan at Oda, Mandera East | onstruction of new 60,000m3 Earth Pan at Oda, Mandera East | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera East | ARABIA | 3.5214 | 40.8421 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33384120 | 33384120 | 33384120 | GOK |  | 100 | null | 33384120 | 33384120 | 33384120 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
onstruction of new 60,000m3 Earth Pan at Oda, Mandera East | onstruction of new 60,000m3 Earth Pan at Oda, Mandera East | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera East | ARABIA | 3.5214 | 40.8421 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33384120 | 33384120 | 33384120 | GOK |  | 100 | null | 33384120 | 33384120 | 33384120 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Domog Ashabito | Construction of 20,000M3 Earth Pan at Domog Ashabito | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | ASHABITO | 3.9196 | 41.2108 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10497217.5 | 10497218 | 10497218 | GOK |  | 100 | null | 10497218 | 10497218 | 10497218 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Domog Ashabito | Construction of 20,000M3 Earth Pan at Domog Ashabito | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | ASHABITO | 3.9196 | 41.2108 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10497217.5 | 10497218 | 10497218 | GOK |  | 100 | null | 10497218 | 10497218 | 10497218 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Water infrastructure improvement at Bulla Geneva and Tawakal , Mandera East | Water infrastructure improvement at Bulla Geneva and Tawakal , Mandera East | improve water access | water infrustructure |  |  | Mandera East | Township | 3.7159 | 41.4712 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 13028000 | 13028000 | 13028000 | GOK |  | 100 | null | 13028000 | 13028000 | 13028000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Water infrastructure improvement at Bulla Geneva and Tawakal , Mandera East | Water infrastructure improvement at Bulla Geneva and Tawakal , Mandera East | improve water access | water infrustructure |  |  | Mandera East | Township | 3.7159 | 41.4712 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 13028000 | 13028000 | 13028000 | GOK |  | 100 | null | 13028000 | 13028000 | 13028000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3HarrDimtu Earth Pan | Construction of 20,000M3HarrDimtu Earth Pan | improve water access | water infrustructure |  |  | Mandera North | Rhamu Dimtu | 3.7309 | 40.9879 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500000 | 10500000 | 10500000 | GOK |  | 100 | null | 10500000 | 10500000 | 10500000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3HarrDimtu Earth Pan | Construction of 20,000M3HarrDimtu Earth Pan | improve water access | water infrustructure |  |  | Mandera North | Rhamu Dimtu | 3.7309 | 40.9879 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500000 | 10500000 | 10500000 | GOK |  | 100 | null | 10500000 | 10500000 | 10500000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Damicha | Construction of 20,000M3 Earth Pan at Damicha | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | null | null | Banisa | Malkamari | 4.0876 | 40.7342 | WATER SERVICES | Water Services | Livestock | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500000 | 10500000 | 10500000 | GOK | null | 100 | null | 10500000 | 10500000 | 10500000 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Damicha | Construction of 20,000M3 Earth Pan at Damicha | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | null | null | Banisa | Malkamari | 4.0876 | 40.7342 | WATER SERVICES | Water Services | Livestock | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500000 | 10500000 | 10500000 | GOK | null | 100 | null | 10500000 | 10500000 | 10500000 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan at Domal, Banisa Sub-County | Construction of new 60,000m3 Earth Pan at Domal, Banisa Sub-County | improve water access | water infrustructure | null | null | Banisa | Malkamari | 4.0876 | 40.7342 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32842950 | 32842950 | 32842950 | GOK | null | 100 | null | 32842950 | 32842950 | 32842950 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan at Domal, Banisa Sub-County | Construction of new 60,000m3 Earth Pan at Domal, Banisa Sub-County | improve water access | water infrustructure | null | null | Banisa | Malkamari | 4.0876 | 40.7342 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32842950 | 32842950 | 32842950 | GOK | null | 100 | null | 32842950 | 32842950 | 32842950 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Bidale | Construction of 20,000M3 Earth Pan at Bidale | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | Guticha | 3.2984 | 40.7126 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12240424 | 12240424 | 12240424 | GOK |  | 100 | null | 12240424 | 12240424 | 12240424 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Bidale | Construction of 20,000M3 Earth Pan at Bidale | ï¿½To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water |  |  | Mandera North | Guticha | 3.2984 | 40.7126 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12240424 | 12240424 | 12240424 | GOK |  | 100 | null | 12240424 | 12240424 | 12240424 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction of Rhamu IDPs Housing Unit 25 No Lot 1 (Re-advertised) | Proposed Construction of Rhamu IDPs Housing Unit 25 No Lot 1 (Re-advertised) | Provision of shelter to displaced internally displaced people | Improveroved living standard |  |  | Mandera North | Rhamu | 3.946 | 41.238 | Social services | Social Services | Social Services | Social Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 15813750 | 15813750 | 150000000 | GOK |  | 100 | null | 15813750 | 15813750 | 15813750 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at DomogAshabito | Construction of 20,000M3 Earth Pan at DomogAshabito | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.68 | 41.1 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10497218 | 10497218 | 10497218 | GOK |  | 100 | null | 10497218 | 10497218 | 10497218 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at DomogAshabito | Construction of 20,000M3 Earth Pan at DomogAshabito | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.68 | 41.1 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10497218 | 10497218 | 10497218 | GOK |  | 100 | null | 10497218 | 10497218 | 10497218 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pam at Harshilmi, Mandera West | Construction of new 60,000m3 Earth Pam at Harshilmi, Mandera West | improve water access | water infrustructure |  |  | Mandera West | Gither | 3.6 | 39.7422 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11794000 | 11794000 | 11794000 | GOK |  | 100 | null | 11794000 | 11794000 | 11794000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pam at Harshilmi, Mandera West | Construction of new 60,000m3 Earth Pam at Harshilmi, Mandera West | improve water access | water infrustructure |  |  | Mandera West | Gither | 3.6 | 39.7422 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11794000 | 11794000 | 11794000 | GOK |  | 100 | null | 11794000 | 11794000 | 11794000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan Bambo, Lafey Sub-county | Construction of new 60,000m3 Earth Pan Bambo, Lafey Sub-county | improve water access | water infrustructure |  |  | Lafey | Lafey | 2.607 | 40.665 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 9851000 | 9851000 | 9851000 | GOK |  | 100 | null | 9851000 | 9851000 | 9851000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan Bambo, Lafey Sub-county | Construction of new 60,000m3 Earth Pan Bambo, Lafey Sub-county | improve water access | water infrustructure |  |  | Lafey | Lafey | 2.607 | 40.665 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 9851000 | 9851000 | 9851000 | GOK |  | 100 | null | 9851000 | 9851000 | 9851000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | improve water access | water infrustructure | null | null | Banisa | DERKALE | 3.05 | 40.4 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10881045 | 10881045 | 10881045 | GOK | null | 100 | null | 10881045 | 10881045 | 10881045 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | Construction of 20,000M3 Earth Pan at Dug Dera, Derkhale | improve water access | water infrustructure | null | null | Banisa | DERKALE | 3.05 | 40.4 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10881045 | 10881045 | 10881045 | GOK | null | 100 | null | 10881045 | 10881045 | 10881045 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Lying of 18km gravity main 1 from Falama hills to Bohole11 in M/South | Lying of 18km gravity main 1 from Falama hills to Bohole11 in M/South | improve water access | water infrustructure |  |  | Mandera South | Kutulo | 2.9 | 40.7 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11829500 | 11829500 | 11829500 | GOK |  | 100 | null | 11829500 | 11829500 | 11829500 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE |  |  | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Lying of 18km gravity main 1 from Falama hills to Bohole11 in M/South | Lying of 18km gravity main 1 from Falama hills to Bohole11 in M/South | improve water access | water infrustructure |  |  | Mandera South | Kutulo | 2.9 | 40.7 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11829500 | 11829500 | 11829500 | GOK |  | 100 | null | 11829500 | 11829500 | 11829500 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE |  |  | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction of Rhamu IDPs Housing Unit 25 No Lot 7 (Re-advertised) | Proposed Construction of Rhamu IDPs Housing Unit 25 No Lot 7 (Re-advertised) | Provision of shelter to displaced internally displaced people | Improveroved living standard |  |  | Mandera North | Rhamu | 3.946 | 41.238 | Social services | Social Services | Social Services | Social Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 16646000 | 16646000 | 16646000 | GOK |  | 100 | null | 16646000 | 16646000 | 16646000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Extension of Water Supply to Morothile | Extension of Water Supply to Morothile | improve water access | water infrustructure |  |  | Mandera North | MOROTHILE | 3.1 | 40.5 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10501558 | 10501558 | 10501558 | GOK |  | 100 | null | 10501558 | 10501558 | 10501558 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Extension of Water Supply to Morothile | Extension of Water Supply to Morothile | improve water access | water infrustructure |  |  | Mandera North | MOROTHILE | 3.1 | 40.5 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10501558 | 10501558 | 10501558 | GOK |  | 100 | null | 10501558 | 10501558 | 10501558 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Water infrastructure improvement in Fino | Water infrastructure improvement in Fino | improve water access | water infrustructure |  |  | Lafey | Fino | 2.7 | 40.55 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11900232 | 11900232 | 11900232 | GOK |  | 100 | null | 11900232 | 11900232 | 11900232 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Water infrastructure improvement in Fino | Water infrastructure improvement in Fino | improve water access | water infrustructure |  |  | Lafey | Fino | 2.7 | 40.55 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11900232 | 11900232 | 11900232 | GOK |  | 100 | null | 11900232 | 11900232 | 11900232 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of Gabions measuring 150m x2m x2m at Buno Farm of Shantoley, Mandera North Sub-County | Proposed construction of Gabions measuring 150m x2m x2m at Buno Farm of Shantoley, Mandera North Sub-County | improve water access | water infrustructure |  |  | Mandera North | Rhamu | 3.95 | 41.2 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 9504344 | 9504344 | 6860000 | GOK |  | 100 | null | 9504344 | 9504344 | 9504344 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 in HardaAllo, Mandera West | Construction of 20,000M3 in HardaAllo, Mandera West | improve water access | water infrustructure | null | null | Mandera West | Dandu | 3.4907 | 39.943 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 9999885 | 9999885 | 9999885 | GOK | null | 100 | null | 9999885 | 9999885 | 9999885 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 in HardaAllo, Mandera West | Construction of 20,000M3 in HardaAllo, Mandera West | improve water access | water infrustructure | null | null | Mandera West | Dandu | 3.4907 | 39.943 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 9999885 | 9999885 | 9999885 | GOK | null | 100 | null | 9999885 | 9999885 | 9999885 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Fencing of Waranqara, Bambo&Gari Boreholes | Fencing of Waranqara, Bambo&Gari Boreholes | improve water access | water infrustructure |  |  | Lafey | WARANQARA | 3.4344 | 40.9689 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500126 | 10500126 | 10500126 | GOK |  | 100 | null | 10500126 | 10500126 | 10500126 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Fencing of Waranqara, Bambo&Gari Boreholes | Fencing of Waranqara, Bambo&Gari Boreholes | improve water access | water infrustructure |  |  | Lafey | WARANQARA | 3.4344 | 40.9689 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10500126 | 10500126 | 10500126 | GOK |  | 100 | null | 10500126 | 10500126 | 10500126 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan at Oda, Mandera East | Construction of new 60,000m3 Earth Pan at Oda, Mandera East | improve water access | water infrustructure |  |  | Mandera East | ARABIA | 3.7159 | 41.4712 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33384120 | 33384120 | 28000000 | GOK |  | 100 | null | 33384120 | 33384120 | 33384120 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan at Oda, Mandera East | Construction of new 60,000m3 Earth Pan at Oda, Mandera East | improve water access | water infrustructure |  |  | Mandera East | ARABIA | 3.7159 | 41.4712 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33384120 | 33384120 | 28000000 | GOK |  | 100 | null | 33384120 | 33384120 | 33384120 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Itlale | Construction of 20,000M3 Earth Pan at Itlale | improve water access | water infrustructure |  |  | Mandera North | MOROTHILE | 3.1089 | 40.2446 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33863340 | 33863340 | 33863340 | GOK |  | 100 | null | 33863340 | 33863340 | 33863340 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Itlale | Construction of 20,000M3 Earth Pan at Itlale | improve water access | water infrustructure |  |  | Mandera North | MOROTHILE | 3.1089 | 40.2446 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 33863340 | 33863340 | 33863340 | GOK |  | 100 | null | 33863340 | 33863340 | 33863340 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 at Urile Earth Pan, Eymole | Construction of 20,000M3 at Urile Earth Pan, Eymole | improve water access | water infrustructure | null | null | Banisa | Kiliweheri | 3.9725 | 40.3414 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10558590 | 10558590 | 10558590 | GOK | null | 100 | null | 10558590 | 10558590 | 10558590 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 at Urile Earth Pan, Eymole | Construction of 20,000M3 at Urile Earth Pan, Eymole | improve water access | water infrustructure | null | null | Banisa | Kiliweheri | 3.9725 | 40.3414 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10558590 | 10558590 | 10558590 | GOK | null | 100 | null | 10558590 | 10558590 | 10558590 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Busle, Burduras | Construction of 20,000M3 Earth Pan at Busle, Burduras | improve water access | water infrustructure | null | null | Mandera West | Gither | 3.7055 | 39.954 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12240424 | 12240424 | 12240424 | GOK | null | 100 | null | 12240424 | 12240424 | 12240424 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Busle, Burduras | Construction of 20,000M3 Earth Pan at Busle, Burduras | improve water access | water infrustructure | null | null | Mandera West | Gither | 3.7055 | 39.954 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12240424 | 12240424 | 12240424 | GOK | null | 100 | null | 12240424 | 12240424 | 12240424 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction of Rhamu Dimtu Market, Mandera North | Proposed Construction of Rhamu Dimtu Market, Mandera North | Improvement to social economic of the inhabitant | Sme access to market |  |  | Mandera North | Rhamu Dimtu | 4.0183 | 41.0662 | TRADE | TRADE | Trade | TRADE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 15399410 | 15399410 | 10976000 | GOK |  | 100 | null | 15399410 | 15399410 | 15399410 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Rehabilitation ,expansion and disilting of Arabia Earth Pan, Mandera East | Rehabilitation ,expansion and disilting of Arabia Earth Pan, Mandera East | improve water access | water infrustructure |  |  | Mandera East | Township | 3.92 | 41.8 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12800000 | 12800000 | 12800000 | GOK |  | 100 | null | 12800000 | 12800000 | 12800000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Rehabilitation ,expansion and disilting of Arabia Earth Pan, Mandera East | Rehabilitation ,expansion and disilting of Arabia Earth Pan, Mandera East | improve water access | water infrustructure |  |  | Mandera East | Township | 3.92 | 41.8 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 12800000 | 12800000 | 12800000 | GOK |  | 100 | null | 12800000 | 12800000 | 12800000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan in SukelaTinfa, Mandera North | Construction of new 60,000m3 Earth Pan in SukelaTinfa, Mandera North | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.6398 | 40.6922 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32706660 | 32706660 | 32706660 | GOK |  | 100 | null | 32706660 | 32706660 | 32706660 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan in SukelaTinfa, Mandera North | Construction of new 60,000m3 Earth Pan in SukelaTinfa, Mandera North | improve water access | water infrustructure |  |  | Mandera North | ASHABITO | 3.6398 | 40.6922 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 32706660 | 32706660 | 32706660 | GOK |  | 100 | null | 32706660 | 32706660 | 32706660 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Danicha | Construction of 20,000M3 Earth Pan at Danicha | improve water access | water infrustructure |  |  | Mandera West | Dandu | 4.0189 | 40.4672 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10900000 | 10900000 | 10900000 | GOK |  | 100 | null | 10900000 | 10900000 | 10900000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 20,000M3 Earth Pan at Danicha | Construction of 20,000M3 Earth Pan at Danicha | improve water access | water infrustructure |  |  | Mandera West | Dandu | 4.0189 | 40.4672 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 10900000 | 10900000 | 10900000 | GOK |  | 100 | null | 10900000 | 10900000 | 10900000 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan at Nyatalio, Mandera South | Construction of new 60,000m3 Earth Pan at Nyatalio, Mandera South | improve water access | water infrustructure |  |  | Mandera South | Kutulo | 2.9214 | 40.8021 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11688849 | 11688849 | 11688849 | GOK |  | 100 | null | 11688849 | 11688849 | 11688849 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of new 60,000m3 Earth Pan at Nyatalio, Mandera South | Construction of new 60,000m3 Earth Pan at Nyatalio, Mandera South | improve water access | water infrustructure |  |  | Mandera South | Kutulo | 2.9214 | 40.8021 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11688849 | 11688849 | 11688849 | GOK |  | 100 | null | 11688849 | 11688849 | 11688849 | null | null | completed | 100 | 0 | NA | NA | null | null | FALSE | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Piping of Water Supply to Duduble, Mandera West | Piping of Water Supply to Duduble, Mandera West | improve water access | water infrustructure | null | null | Mandera West | Takaba | 3.4911 | 40.1095 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11219040 | 11219040 | 11219040 | GOK | null | 100 | null | 11219040 | 11219040 | 11219040 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Piping of Water Supply to Duduble, Mandera West | Piping of Water Supply to Duduble, Mandera West | improve water access | water infrustructure | null | null | Mandera West | Takaba | 3.4911 | 40.1095 | WATER SERVICES | Water Services | Water Services | Water Services | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 11219040 | 11219040 | 11219040 | GOK | null | 100 | null | 11219040 | 11219040 | 11219040 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/318/2014-2015 | Rehabilitation of Kaamorliban water supply in Mandera east Sub-County | improve water access | water infrustructure | null | null | Lafey | Lafey | 3.2104 | 41.1784 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11900000 | 11900000 | 11900000 | GOK | N/A | 100 | null | 11900000 | 11900000 | 11900000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Mcg/318/2014-2015 | Rehabilitation of Kaamorliban water supply in Mandera east Sub-County | improve water access | water infrustructure | null | null | Lafey | Lafey | 3.2104 | 41.1784 | WATER SERVICES | Water Services | Water Services | Water Services | 2014-07-01 00:00:00+00 | 2015-07-01 00:00:00+00 | 2017-06-30 23:59:59.999+00 | 2017-06-30 23:59:59.999+00 | 11900000 | 11900000 | 11900000 | GOK | N/A | 100 | null | 11900000 | 11900000 | 11900000 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 1 No. lateral concrete canals measuring 450m with water control gate at BP1, Mandera East | Construction of 1 No. lateral concrete canals measuring 450m with water control gate at BP1, Mandera East | null | Canal constructed | null | null | Mandera East | Township | 3.9486 | 41.8525 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 6493627 | 6493627 | 6493627 | GOK | null | 100 | null | 6493627 | 6493627 | 6493627 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of 1 No. lateral concrete canals measuring 450m with water control gate and supply of 3 piston engine water pump at BP1, Mandera East | Construction of 1 No. lateral concrete canals measuring 450m with water control gate and supply of 3 piston engine water pump at BP1, Mandera East | null | Canal constructed | null | null | Mandera East | Township | 3.9486 | 41.8525 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 4984566 | 4984566 | 8460000 | GOK | null | 100 | null | 4984566 | 4984566 | 4984566 | null | null | completed | 100 | null | NA | NA | null | null | null | NA | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/23/2015-2016 | Construction of 1 No. lateral concrete canals measuring 450m with water control gate at BP1, Mandera East | null | Canal constructed | null | null | Mandera East | Township | 3.9486 | 41.8525 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 6493627 | 6493627 | 6493627 | GOK | N/A | 100 | null | 6493627 | 6493627 | 6493627 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
MCG/T/22/2015-2016 | Construction of 1 No. lateral concrete canals measuring 450m with water control gate and supply of 3 piston engine water pump at BP1, Mandera East | null | Canal constructed | null | BP1 farming infrustructure | Mandera East | Township | 3.9486 | 41.8525 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE | 2015-07-01 00:00:00+00 | 2016-07-01 00:00:00+00 | 2018-06-30 23:59:59.999+00 | 2018-06-30 23:59:59.999+00 | 4984566 | 4984566 | 8460000 | GOK | N/A | 100 | null | 4984566 | 4984566 | 4984566 | null | null | completed | 100 | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed Extension of solar street lightening in Mandera Town | proposed Extension of solar street lightening in Mandera Town | enhance security and ease movement during the night | Reduced criminal activities | null | Solar street light for Mandera Town | Mandera East | Township | 3.9486 | 41.8525 | Energy | Energy | Energy | Energy | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 41203010 | 41203010 | 19524000 | GOK | N/A | 100 | null | 41203010 | 41203010 | 41203010 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed Maintenance of solar street lightening in Mandera Town | proposed Maintenance of solar street lightening in Mandera Town | enhance security and ease movement during the night | Boost business by extending business hours | MCG/OT/85/2017-2018 | null | Mandera East | Township | 3.9486 | 41.8525 | Energy | Energy | Energy | Energy | 2017-07-01 00:00:00+00 | 2018-07-01 00:00:00+00 | 2020-06-30 23:59:59.999+00 | 2020-06-30 23:59:59.999+00 | 18299980 | 18299980 | 18299980 | GOK | N/A | 100 | null | 18299980 | 18299980 | 18299980 | null | null | completed | null | null | N/A | N/A | null | null | null | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF DARKEN GABA-AWACHO ROAD IN KILIWEHIRI SUB COUNTY | PROPOSED MAINTENANCE OF KOTKOTO-QORGOWLE ROAD IN MANDERA WEST SUB COUNTY | Improve transport efficiency | Rehabilitated road |  |  | Mandera West | null | 3.329 | 40.307 | ROADS | ROADS | ROADS | ROADS | 2024-07-01 00:00:00+00 | 2024-11-24 21:00:00+00 | 2026-11-23 21:00:00+00 | null | 39364600 | 39364600 | 11000000 | GOK | N/A | null | null | null | null | null | null | null | ongoing | null | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Ongoing
PROPOSED PROTECTION WORKS AND APPROACH ROAD AT LAG DIMA IN BANISA SUB COUNTY | PROPOSED PROTECTION WORKS AND APPROACH ROAD AT WAYAM LENCHA IN MANDERA SOUTH | Reduce environmental damage and improve access | Completed protection works |  |  | Mandera South | Elwak South | 2.9214 | 40.8021 | ROADS | ROADS | ROADS | ROADS | 2025-07-01 00:00:00+00 | 2026-01-29 21:00:00+00 | 2027-10-28 21:00:00+00 | null | 15505488 | 15505488 | 15505488 | GOK | N/A | null | null | null | null | null | null | null | ongoing | null | null | N/A | N/A | null | null | TRUE | N/A | N/A | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Ongoing
Proposed Construction Of Mandera County Public Service Board Office Block At Mandera Town In Mandera East Sub-County. | Proposed Construction Of Mandera County Public Service Board Office Block At Mandera Town In Mandera East Sub-County. | improve service delivery | CPSB office block | null | Construction of County Public Service Board office | Mandera East | Neboi | 3.9621 | 41.7703 | Public Service Board | Public Service | Public Service | Public Service | 2020-12-07 21:00:00+00 | 2021-12-05 21:00:00+00 | 2022-12-05 21:00:00+00 | 2022-12-05 21:00:00+00 | 74800000 | 74800000 | 10000000 | GOK | NA | 100 | null | null | 100 | 44724 | null | null | completed | null | null | NA | NA | null | null | null | null | NA | TRUE | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | TRUE | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | TRUE | Risk assesment, Contingency planning,recource allocations and financial planning | Completed