## 17-18 Final
title | description | project_goal | project_output | project_code | budget_item_name | sub_county_id | ward_id | latitude | longitude | sector_vote_name | department_id | directorate_id | implementing_agency | date_of_approval | project_start_date | expected_completion_date | actual_completion_date | estimated_project_cost | approved_project_cost | funds_available_specific_year | project_funding_source | development_partner_name | county_government_component | development_partner_component | total_disbursed_funds | percentage_disbursed | expenditure_to_date | pending_bills | project_balance | status | percentage_completion | stalled_completion_percentage | stalled_reasons | year_project_stalled | time_to_complete_months | estimated_cost_to_complete | still_in_budget | stalled_project_recommendation | associated_risks | climate_disaster_screened | climate_mitigation_action | environmental_social_screened | environmental_mitigation_action | technical_viability_screened | viability_mitigation_action | remarks
20000m3 at Qorgowla earth pan in Banisa Sub County | 20000m3 at Qorgowla earth pan in Banisa Sub County | improved water access | earth pan | MCG/OT/34/2019-2020 |  | Banisa |  |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 11880130 | 11880130 |  |  | N/A | Full | N/A | 11880130 | 100% | 11880130 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Change of tiled floor to terrazo at Elwak Sub County Referal Hospital | Change of tiled floor to terrazo at Elwak Sub County Referal Hospital | improve access to health services | terrazo at Elwak hospital | MCG/OT/MOH/01/2019-2020 |  | Mandera South | Elwak |  |  | Health Services | Health Services | Health Services | Health Services |  |  |  |  | 35101426 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Construction Of 20,000M3 Dambala Gale Earth Pan | Proposed Expansion Of Guba Heaith Centre In Banisa Sub-County. | Improve access to water | [7 empty] | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 11500000 | 11500000 |  | GOK | N/A | Full | N/A | 11500000 | 100% | 11500000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Construction of 20000m3 at Koticha Tiyale in Mandera South | Construction of 20000m3 at Koticha Tiyale in Mandera South | Improve access to water | earth pan | MCG/OT/30/2019-2020 |  | Mandera South |  |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 10959610 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Construction of 20000m3 earth pan at Soroba in Banisa | Construction of 20000m3 earth pan at Soroba in Banisa | improved water access | Soroba earthpan | MCG/OT/39/2019-2020 |  | Banisa |  |  |  | Water Services | Water Services | Water Services | Water Services | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 10000000 | 10000000 |  |  | N/A | Full | N/A | 10000000 | 100% | 10000000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Construction of 20000m3 earth pan at Sotowes earthpan | Construction of 20000m3 earth pan at Sotowes earthpan | Improve access to water | earth pan | MCG/OT/42/2019-2020 | [5 empty] | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 9872016 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
construction of 3No. Wards, maternity block, laboratory block and store at Banisa level IV Hospital | construction of 3No. Wards, maternity block, laboratory block and store at Banisa level IV Hospital | improve access to health services | wards and maternities | MCG/OT/024/2019-2020 |  | Banisa | Banisa |  |  | Health Services | Health Services | Health Services | Health Services |  |  |  |  | 98608385 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Construction of 60000m3 earthpan at Banisa | Construction of 60000m3 earthpan at Banisa | Improve access to water | earth pan | MCG/OT/010/2019-2020 |  | Banisa | Banisa |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 61576452 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Construction of Box Culvert at Duse-A3 Road | Construction of Box Culvert at Duse-A3 Road | For drainage purposes and creating water path for the raining seasons | Reduced floodings in the roads during the raining | MCG/OT/076/2017-2018 |  | Mandera East | Neboi |  |  | Public works | Public works | Public works | Public works | 2017 | 2018-05-29 | 2019-05-31 | 2019-05-31 | 61995040 | 61995040 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of elwak sub-county headquarters | Construction of elwak sub-county headquarters | provide centralized locations for subcounty andministrations | provides closer government services |  | Sub-County Headquarter for Elwak Sub-County | Mandera south | Elwak |  |  | Devolved Unit | Devolved Unit | Devolved Unit | Devolved Unit | 2017 |  |  |  | 50172731 | 50172731 | 30000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of khalafow water supply system in Mandera West | Construction of khalafow water supply system in Mandera West | improve access to services | water infrustructure | MCG/OT/40/2019-2020 |  | Mandera West | Gither |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 19995500 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Construction Of Kutulo (Malbe) Water Pan Irrigation Projects | Proposed Construction Of 60,000M3 Qordobo Saglan Earthpan | improve food production | irrigation infrustructure |  | 200,000M3 Earth Pan for irrigation and food production at Malbe in Kutulo Sub-County complete with Irrigation infrastructure | Kutulo | kutulo | 2.418 | 40.6742 | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 253013297 | 253013297 | 207092828 | GOK | N/A | Full | N/A | 253013297 | 100% | 253013297 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Construction of kutulow sub-county headquarters | Construction of kutulow sub-county headquarters | ensuring governance and service delivery to the residents | promote tracking of new infectious disease | MCG/OT/036/2017/2018 | Sub-County Headquarter for kutulo Sub-County | kutulo | kutulo |  |  | Devolved Unit | Devolved Unit | Devolved Unit | Devolved Unit | 2017 | 2018-04-09 | 4/30/2019 | 4/30/2019 | 40000000 | 40000000 | 30000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of Takaba - Shimbir Fatuma Road | Construction of Takaba - Shimbir Fatuma Road | Ease transport in the area | Promote business locally | MCG/OT/070/2017-2018 |  | Takaba | shimbirfatuma |  |  | Roads | Roads | Roads | Roads | 2017 |  |  |  | 220141682 | 220141682 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Construction of Tarama water pan and irrigation in Banisa | Construction of Tarama water pan and irrigation in Banisa | Improve access to water | earth pan | MCG/OT/027/2019-2020 |  | Banisa | Derkale |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 29037161 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Construction Of The Regional Livestock Market | Proposed Construction Of Underground And Elevated Water Tank At New Government Offices. | improve acess to market and trade | Market in Mandera East |  | Completion of the Construction of the regional livestock Market | Mandera East | Neboi | 3.904 | 41.7686 | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 28933574 | 28933574 | 146000000 | GOK | N/A | Full | N/A | 28933574 | 100% | 28933574 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Design, construct, supply, deliver, installation and commisioning of Radiology unit at Takaba referral hospital in mandera west | Design, construct, supply, deliver, installation and commisioning of Radiology unit at Takaba referral hospital in mandera west | improving HEALTH SERVICES and preventing diseases | HEALTH SERVICESy lifestyle | MCG/OT/05/2018-19 | Complete Radiology unit at Takaba | mandera west | takaba | 3.8616 | 39.9323 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  |  | 4/16/2019 | 4/30/2020 | 29744968 | 29744968 | 29000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Desilting and expansion of 20000m3 at Sukela loqo in Mandera West | Desilting and expansion of 20000m3 at Sukela loqo in Mandera West | Improve access to water | earth pan | MCG/OT/38/2019-2020 |  | Mandera West |  |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 9999265 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Desilting and expansion of 20000m3 earthpan at Laga Goljo in Banisa | Desilting and expansion of 20000m3 earthpan at Laga Goljo in Banisa | improved water access | earth pan | MCG/OT/36/2019-2020 |  | Banisa | Banisa |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 11995095 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Expansion And Reconstruction Of Slaughter House In Elwak | Proposed Construction Of 50No Toilets Block At Neboi Ward In Mandera East Sub-County. |  |  |  |  | Mandera South | Elwak | 2.8186 | 40.9349 | Social Services | Social Services | Social Services | Social Services |  |  |  |  | 104959282 | 104959282 |  | GOK | N/A | Full | N/A | 104959282 | 100% | 104959282 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Expansion Of Digdig Earth Pan By 15,000M3 For Irrigation Program, Provide Water Pump And 5,000M3 Raised Water Tank | Proposed Construction Of 60,000M3 Earthpan At Kopi. | improve food production | earth pan |  | Expansion of Digdig Earth Pan by 15,000M3 for irrigation program, provide water pump and 5,000M3 raised water tank | Banisa | Derkale | 3.8969 | 40.2768 | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 14633357 | 14633357 | 3603815 | GOK | N/A | Full | N/A | 14633357 | 100% | 14633357 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Extension of solar street lighting in Elwak Town | Extension of solar street lighting in Elwak Town | improve access to services | solar street lights | MCG/OT/21/2019-2020 |  | Elwak |  |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 57697605 | 57697605 |  |  | N/A | Full | N/A | 57697605 | 100% | 57697605 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Installation Of Cctv Camera,Ip Pbx And Lan Cabling At New County Headquarters At Mandera Town In Mandera East Sub County. | Installation Of Cctv Camera,Ip Pbx And Lan Cabling At New County Headquarters At Mandera Town In Mandera East Sub County. | improve internet connectivity | CCTV and LAN installed at CHQ | MCG/40/75/2020-2021 | Supply, Delivery. Installation and Commission of LAN Cabling, CCTV Cameras, at the New County Headquarter, Governor's residence and County Hotel | Mandera East | Neboi |  |  | Finance | Financial Services | Financial Services | Financial Services | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 39987868 | 39987868 | 12500000 | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Kobe earthpan | Kobe earthpan | improved water access | Kobe earth pan | MCG/OT/30/2019-2020 |  | Mandera West |  |  |  | Water Services | Water Services | Water Services | Water Services | 2026-04-20 | 2026-04-20 | 2026-04-21 |  | 10000000 | 10000000 |  |  | N/A | Full | N/A | 10000000 | 100% | 10000000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Kobe lagi earth pan in Mandera West | Kobe lagi earth pan in Mandera West | improved water access | earth pan | MCG/OT/26/2019-2020 |  | Mandera West |  |  |  | Water Services | Water Services | Water Services | Water Services | 2026-04-20 | 2026-04-20 | 2026-04-21 |  | 30998001 | 30998001 |  |  | N/A | Full | N/A | 30998001 | 100% | 30998001 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Maintainance of Elwak Shimpir Fatuma road | Maintainance of Elwak Shimpir Fatuma road | improved road network | road network | MCG/OT/RMLF/07/2019-2020 |  | Mandera South | Elwak |  |  | Roads | Roads | Roads | Roads |  |  |  |  | 145194300 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Construction Of 60,000 Cubic Metre Earth Pan At Damoog Mandera North Sub-County | Proposed Construction Of Mandera County Public Service Board Office Block At Mandera Town In Mandera East Sub-County. | Improve access to water | earth pan | MCG/OT/13/2019-2020 | Construction of 60,000M3 eath pan at Damoog | mandera north | Rhamu | 3.2761 | 40.6354 | Water Services | Water Services | Water Services | Water Services | 2026-04-20 | 2026-04-20 | 2026-04-22 | 2026-04-22 | 29975820 | 29975820 | 30000000 | GOK | N/A | Full | N/A | 29975820 | 100% | 29975820 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed construction of Dandu theatre in mandera west | Proposed construction of Dandu theatre in mandera west | Reduce travel distance/time for residents, especially in remote/nomadic communities. | improved sanitation standard and good well being | MCG/22/2017-2018 | Construction of theater in Dandu | Mandera west | Dandu |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 408425 | 2019-03-31 | 2019-03-31 | 36048260 | 36048260 | 23000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed Extension of solar street lightening in Mandera Town | proposed Extension of solar street lightening in Mandera Town | enhance security and ease movement during the night | Reduced criminal activities |  | Solar street light for Mandera Town | Mandera East | Neboi |  |  | Energy | Energy | Energy | Energy | 2017 |  |  |  | 41203010 | 41203010 | 19524000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed Maintenance of solar street lightening in Mandera Town | proposed Maintenance of solar street lightening in Mandera Town | enhance security and ease movement during the night | Boost business by extending business hours | MCG/OT/85/2017-2018 |  | Mandera East | Neboi |  |  | Energy | Energy | Energy | Energy | 2017 |  |  |  | 18299980 | 18299980 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED ADMINISTRATION BLOCK AT MANDERA TECHNICAL TRAINING INSTITUTE IN MANDERA EAST SUB COUNTY | PROPOSED ADMINISTRATION BLOCK AT MANDERA TECHNICAL TRAINING INSTITUTE IN MANDERA EAST SUB COUNTY | promote quality education | human resources development | MCG/OT/99/2018-2019 | Mandera Technical Training Institute - Admin Block | mandera east | Neboi | 3.9356 | 41.792 | Education | Education | Education | Education |  |  | 4/30/2019 | 4/30/2019 | 69850000 | 69850000 | 40000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Alteration and Demolitions for Kutulo Hospital and Anciliary Works In Kutulo Sub-County | Proposed Alteration and Demolitions for Kutulo Hospital and Anciliary Works In Kutulo Sub-County | for structural modifications | promote safety and modernization of the building | MCG/OT/83/2017-2018 | Repair and Renovation of Kutulo District Hospital | Kutulo | Kutulo |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-06-19 | 2019-06-30 | 2019-06-30 | 7906525 | 7906525 | 12000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED AUTOMATION OF MANDERA COUNTY REVENUE SYSTEM | PROPOSED AUTOMATION OF MANDERA COUNTY REVENUE SYSTEM | enhance efficiency and productivity | quality service delivery | RFP/02/2018-2019 |  | Mandera east | mandera east |  | - | ICT | ICT | ICT | ICT |  |  | 4/30/2019 | 4/30/2019 | 24676416 | 24676416 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | Proposed Cadestral Survey in Kutulo, Elwak and Mandera town | For defining proper bounderies and creating cadestral map | provides proper planning | MCG/84/2017/2018 | Land Survey in Mandera Town, Elwak and Kutulo | Kutulo/Elwak/Mandera | Kutulo/Elwak/Mandera |  |  | Lands | Lands | Lands | Lands | 2017 | 2018-06-18 | 2019-06-30 | 2019-06-30 | 104000000 | 104000000 | 33848655 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CHAINLINK FENCING AND BUSH CLEARING AT BAMBO DISPENSARY IN LAFEY SUB-COUNTY | PROPOSED CHAINLINK FENCING AND BUSH CLEARING AT BAMBO DISPENSARY IN LAFEY SUB-COUNTY | improving HEALTH SERVICES and preventing diseases | HEALTH SERVICESy lifestyle | MCG/OT/126/2018-19 | construction of chainlink fencing and bush clearing at Bambo dispensery | Mandera East | lafey | 3.1536 | 41.1854 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  |  | 4/16/2018 | 4/30/2019 | 6858616 | 6858616 | 6900000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CHANGE OF KAMOR BORDER PETROL BASE TO KAMOR HEALTH CENTRE IN MANDERA EAST | PROPOSED CHANGE OF KAMOR BORDER PETROL BASE TO KAMOR HEALTH CENTRE IN MANDERA EAST | improving health and preventing diseases | healthy lifestyle | MCG/OT/087/2018-2019 |  | mandera east | mandera east | 3.9246 | 41.8542 | health services | health services | health services | health services |  |  | 4/30/2019 | 4/30/2019 | 46000000 | 46000000 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CHANGE OF MATERIAL LABORATORY TO PROOCOL OFFICE AND CABRO WORKS IN MANDERA EAST SUB-COUNTY | PROPOSED CHANGE OF MATERIAL LABORATORY TO PROOCOL OFFICE AND CABRO WORKS IN MANDERA EAST SUB-COUNTY | provide office space for staffs | enhance officers accessibility |  | Conversion of material lab to Protocol office, 4 No bathrooms and Cabro in the Parking area | Mandera East | Township | 3.9364 | 41.8615 | Public Works | Public Works | Public Works |  | 2021 | 2021-10-12 | 12/31/2022 | 12/31/2022 | 8498027.4 | 8498027.4 | 2000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Change Of Material Laboratory To Protocol Office And Cabro Works In Mandera East Sub-County | Proposed Expansion Of Rhamu Hospital In Mandera North Sub-County | improve service delivery | Protocol office |  |  | Mandera East | Neboi | 3.9364 | 41.8615 | Public Works | Public Works | Public Works | Public Works |  |  |  |  | 84,98,027.4 | 84,98,027.4 |  | GOK | N/A | Full | N/A | 84,98,027.4 | #VALUE! | 84,98,027.4 | N/A | #VALUE! | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Community Library In Elwak In Mandera South Sub-County. | Proposed Community Library In Elwak In Mandera South Sub-County. | improve access to literacy | Libraries established | MCG/0T/72/2020-2021 | Completion and operationalization of Elwak, Lafey and Rhamu Library | Mandera North |  | 2.8068 | 40.9367 | Social Services | social services | social services | social services | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 20577942 | 20577942 | 6700000 | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Community Library In Lafey In Lafey South Sub County. | Proposed Community Library In Lafey In Lafey South Sub County. | access to readin and writing materials | Libraries established | MCG/OT/73/2020-2021 | Completion and operationalization of Elwak, Lafey and Rhamu Library | Lafey | Lafey | 3.154 | 41.1858 | Water Services | water services | water services | water services |  |  |  |  | 18563753 | 18563753 | 6700000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Community Library In Rhamu In Mandera North Sub-County. | Proposed Community Library In Rhamu In Mandera North Sub-County. | access to many reading and writing materials | Libraries established | MCG/OT/74/2020-2021 | Completion and operationalization of Elwak, Lafey and Rhamu Library | Mandera North | Rhamu | 3.9292 | 41.2123 | Social Services | social services | social services | social services | 5/26/2021 | 2021-05-26 | 5/31/2023 | 5/31/2023 | 9990558 | 9990558 | 6700000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Completion Of County Guest House | Proposed Completion Of County Guest House | giving accomodations and providing lodging to visitors,offiials and travellers | provides safety,lodging and other related services | MCG/OT/059/20217-2018 |  | Mandera east | Neboi |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 | 2018-04-09 | 2019-04-30 | 2019-04-30 | 308671300 | 308671300 |  | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Completion Of County Headquarters | Proposed Completion Of County Headquarters | By provinding more spaces and ease accessibility of the county services | creates easy access to government offices | MCG/0T/58/2017-2018 | Completion of County Headquarter | Mandera east | Neboi |  |  | Devolved Unit | Devolved Unit | Devolved Unit | Devolved Unit | 2017 | 2018-04-02 | 2019-04-30 | 2019-04-30 | 455354521 | 455354521 | 40000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED COMPLETION OF ESP MARKET IN MANDERA TOWN IN MANDERA EAST | PROPOSED COMPLETION OF ESP MARKET IN MANDERA TOWN IN MANDERA EAST | boost trade | economic development | MCG/OT/038/2018-19 | Elwak SME market Park completion | Mandera east |  |  | mandera | public works | public works | public works | public works |  |  | 4/16/2019 | 4/30/2020 | 46640923 | 46640923 | 57101136 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED COMPLETION OF GOVERNORS RESIDENCE IN MANDERA EAST | PROPOSED COMPLETION OF GOVERNORS RESIDENCE IN MANDERA EAST | infrastructure improvement and Economic Development | service delivery | MCG/OT/143/2018-2019 | Completion of Governor's Residence - External works | mandera east | Neboi | 3.929 | 41.7977 | Public Works | public works | public works | public works |  |  | 4/30/2019 | 4/30/2019 | 258051400 | 258051400 | 82000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Completion Of Harshilmi Mordern Primary School In Mandera West Sub County | Proposed Opening Up Of Access Road To Kmtc And Mttc Area In Mandera East Sub-County | improve access to education | A model ECDE |  | Balance of Harshilmi strategic boarding school | Mandera West | Gither | 3.6002 | 39.7415 | Education | Education | Education | Education |  |  |  |  | 38846312 | 38846312 | 34558616 | GOK | N/A | Full | N/A | 38846312 | 100% | 38846312 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED COMPLETION OF HARSHILMI MORDERN PRIMARY SCHOOL IN MANDERA WEST SUB COUNTY | PROPOSED COMPLETION OF HARSHILMI MORDERN PRIMARY SCHOOL IN MANDERA WEST SUB COUNTY | improve access to quality education | increase enrolment and ensure universal education |  | Under Provision for Harshilmi Model School | Mandera West | Dandu |  |  | Education | Education | Education |  | 2021 |  |  |  | 38846312 | 38846312 | 1599519 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED COMPLETION OF KUTULO MARKET IN MANDERA SOUTH SUB COUNTY | PROPOSED COMPLETION OF KUTULO MARKET IN MANDERA SOUTH SUB COUNTY | boost trade | economic development | MCG/OT/03/2018-2019 |  | mandera south | kutulo |  |  | public works | public works | public works | public works |  |  | 4/30/2019 | 4/30/2019 | 19323590 | 19323590 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Completion Of Livestock Resilence Office In Mandera East | Proposed Completion Of Livestock Resilence Office In Mandera East | improving livelihoods | creating market linkages | MCG/OT/01/2018-19 | Completion of the Construction of the regional livestock Market | mandera east | Neboi | 3.9399 | 41.863124 3.939876 | Livestock | Livestock | Livestock | Livestock |  |  | 10/31/2018 | 10/31/2019 | 18570480 | 18570480 | 106000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Completion of Mirra Market in Mandera East Constituency | Proposed Completion of Mirra Market in Mandera East Constituency | Boosting mirra tradings and provinding modern market | Boost mirra business | MCG/OT/73/2017-2018 | Construction of Proposed Miraa Market In Mandera Town | #REF! | #REF! |  |  | Trade | Trade | Trade | Trade | 2017 | 2018-05-29 | 2019-05-31 | 2019-05-31 | 39032886 | 39032886 | 20161407 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Completion Of Opd At Harshilmi In Mandera West Sub County | Proposed Upgrading Of Malka Punda Road To Bitumen Standard In Mandera East Sub-County. | improve access to health services | OPD at Harshilmi |  | Completion of ODP at Harshilmi | Mandera West | Gither | 3.6005 | 39.7385 | Health Services | Health Services | Health Services | Health Services |  |  |  |  | 48360307 | 48360307 | 55278449 | GOK | N/A | Full | N/A | 48360307 | 100% | 48360307 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED COMPLETION OF OPD AT HARSHILMI IN MANDERA WEST SUB COUNTY | PROPOSED COMPLETION OF OPD AT HARSHILMI IN MANDERA WEST SUB COUNTY | provide high accessible, high quality diagonistic, curative service | improve patient flow and reduce wait times |  | Completion of ODP at Harshilmi | Mandera West | Dandu |  |  | Health Services | Health Services | Health Services |  | 2021 |  |  |  | 48360306.5 | 48360306.5 | 5000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Consruction Of 30,000M3 Garse Bor Earth Pan. | Proposed Consruction Of 30,000M3 Garse Bor Earth Pan. | to ensure access to clean water | Garse Bor earth pan | MCG/OT./23/2020-2021 | cocnstruction of 20000m3 Garse Bor earthpan |  |  |  |  | Water Services | water services | water services | water services | 4/22/2021 | 4/22/2021 | 5/28/2022 | 5/28/2022 | 14910630 | 14910630 |  | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED CONSRUCTION OF SECURITY CAMP AT THE NEW COUNTY HEAD QUARTERS IN MANDERA EAST | PROPOSED CONSRUCTION OF SECURITY CAMP AT THE NEW COUNTY HEAD QUARTERS IN MANDERA EAST | Promote security | increased safety | MCG/OT/109/2018-2019 | New County Headquarter Security Camp | mandera east | shafshafey | 3.9266 | 41.7936 | public works | public works | public works | public works |  |  | 4/30/2019 | 4/30/2019 | 43006826 | 43006826 | 35000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Constrcution Of 60,000M3 Har Dumayo Earth In Banisa, Mandera County | Supply,Delivery,Installation And Commissioning Of oxygen Plant For Mandera West,Kutulo And Mandera North Sub Counties And Supply And Delivery Of Medical Equipments. | Improve access to water | earth pan |  |  | Banisa | Kiliwehiri | 3.8867 | 40.3074 | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 32820617 | 32820617 |  | GOK | N/A | Full | N/A | 32820617 | 100% | 32820617 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Construcion Of 50No Toilets For Vulnerable Families In Neboi Location In Mandera East Sub-County | Proposed Murraming Of Road In Takaba Town In Mandera. | improve sanitation | Toilets |  |  | Mandera East | Neboi |  |  | Social Services | Social Services | Social Services | Social Services |  |  |  |  | 10000000 | 10000000 |  | GOK | N/A | Full | N/A | 10000000 | 100% | 10000000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCION OF 50NO TOILETS FOR VULNERABLE FAMILIES IN NEBOI LOCATION IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCION OF 50NO TOILETS FOR VULNERABLE FAMILIES IN NEBOI LOCATION IN MANDERA EAST SUB-COUNTY | public health protection | promote hygiene protection |  | Construction of 50 of Public Toilets in Neboi Ward | Mandera East | Neboi |  |  | special programme | special programme | special programme |  | 2021 | 2021-10-12 | 12/31/2022 | 12/31/2022 | 10000000 | 10000000 | 4000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 30,000M3 Earth Pan At Adala Dimtu Earth Pan In Mandera West Sub County | Proposed Construction Of Boundary Security Wall And Fencing Of Government Offices | Improve access to water | earth pan |  |  | Mandera West | Gither | 3.6839 | 39.9076 | Public Works | Public Works | Public Works | Public Works |  |  |  |  | 14480000 | 14480000 |  | GOK | N/A | Full | N/A | 14480000 | 100% | 14480000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT ADALA DIMTU EARTH PAN IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT ADALA DIMTU EARTH PAN IN MANDERA WEST SUB COUNTY | food security | boast food security |  | Construciton of 30,000m3 Adala Dimtu Dam @ dodishan mandera west | Mandera West | mandera west | 3.6839 | 39.9076 | Water Services | Water Services | Water Services |  | 2021 | 2/25/2022 | 2/28/2022 | 2/28/2022 | 14480000 | 14480000 | 15500000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction 0F 20,000M3 Wayam Dera Earth Pan. | Proposed Construction 0F 20,000M3 Wayam Dera Earth Pan. | to ensure access to clean water | Wayam Dera earth pan |  | Construction of 20,000 M3 Earth Pan at Wayam Dera in Mandera West Sub-County | mandera west | Takaba south | 3.2494 | 40.3838 | Water Services | water services | water services | water services |  |  |  |  | 9990183 | 9990183 |  | GOK | NA | 100% | [6 empty] | dry and request expansion | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction 30,000 M3 Earth Pan At Duse Bima In Mandera West Sub County | Proposed Fencing Of Bp1 And Kamor Cemetery In Mandera | Improve access to water | earth pan |  |  | Mandera West | Takaba | 3.4031 | 40.0989 | Public Works | Public Works | Public Works | Public Works |  |  |  |  | 17000000 | 17000000 |  | GOK | N/A | Full | N/A | 17000000 | 100% | 17000000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION 30,000 M3 EARTH PAN AT DUSE BIMA IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION 30,000 M3 EARTH PAN AT DUSE BIMA IN MANDERA WEST SUB COUNTY | water security | improve water security |  | Construciton of 30,000m3 Dam at Duse bima mandera West | mandera West | Mandera West | 3.4031 | 40.0989 | Water Services | Water Services | Water Services |  | 2021 | 2/25/2022 | 2/28/2022 | 2/28/2022 | 17000000 | 17000000 | 15000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction 60,000M3 Earth Pan At Dadach Dheera In Mandera West Sub County | Proposed Construction Of Water Infrastructure At The New County Headquarters In Mandera East Sub County. | Improve access to water | earth pan |  |  | Mandera West | Gither |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 30900000 | 30900000 |  | GOK | N/A | Full | N/A | 30900000 | 100% | 30900000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION 60,000M3 EARTH PAN AT DADACH DHEERA IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION 60,000M3 EARTH PAN AT DADACH DHEERA IN MANDERA WEST SUB COUNTY | resource management | increase climate resilence |  | Construction of 60,000m3 Dadach Dheera Dam | mandera West | mandera West |  |  | Water Services | Water Services | Water Services |  | 2021 | 2/25/2022 | 2/28/2022 | 2/28/2022 | 30900000 | 30900000 | 31000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction And Eqiping Of Radiology Centre At Rhamu Sub County Hospital In Mandera North Sub County. | Proposed Construction And Eqiping Of Radiology Centre At Rhamu Sub County Hospital In Mandera North Sub County. | affordale and available health facilities | Radiology center | MCG/OT/96/2020-2021 | proposed construction and equipping of radiology center at rhamu hospital in Manera North sub county | Mandera North | Rhamu | 3.9337 | 41.2259 | Health Services | Health services | Health services | Health services | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 30092952 | 30092952 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction And Expantion Of 60,000M3 At Abuna Dam | Proposed Desilting And Expansion Of Lehele Earth Pan In Kutulo Sub-County | Improve access to water | earth pan | [6 empty] | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 30869230 | 30869230 |  | GOK | N/A | Full | N/A | 30869230 | 100% | 30869230 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Construction And Expantion Of 60,000M3 At Chuqal Earth In Mandera South Sub-County | Proposed Construction Of 30,000M3 Bulla Madina Earth Pan | Improve access to water | earth pan |  |  | Mandera South |  |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 30992230 | 30992230 |  | GOK | N/A | Full | N/A | 30992230 | 100% | 30992230 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed construction dispensary block at towfiq in mandera north subcounty | Proposed construction dispensary block at towfiq in mandera north subcounty | Ensure essential services (maternal/child health, immunization) are available locally. | community engagement | MCG/OT/033/2017-2018 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) | Mandera North | RHAMU |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-03-28 | 2019-03-31 | 2019-03-31 | 7800000 | 7800000 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 20,000m3 earth pan at duse in banisa sub-county | proposed construction of 20,000m3 earth pan at duse in banisa sub-county | Irrigation, Supporting agricultural activities through water harvesting and storage . | Reductions of livestocks movement for water | MCG/OT/51/2017-2018 |  | Banisa |  |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-31 | 2019-05-31 | 2019-05-31 | 14165760 | 14165760 |  | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 20,000m3 earth pan in funanteso at banisa sub-county | proposed construction of 20,000m3 earth pan in funanteso at banisa sub-county | Providing Water for Domestic Use | increases farming nearby dams | MCG/OT/49/2017-2018 | construction of 30,000m3 at Funan Teso (mandera West) | Banisa |  |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-26 | 2019-03-31 | 2019-03-31 | 14225400 | 14225400 | 15500000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 60,000M3 Earthpan At Keye In Banisa | Installation Of Cctv Camera,Ip Pbx And Lan Cabling At New County Headquarters At Mandera Town In Mandera East Sub County. | Improve access to water | earth pan |  |  | Banisa |  |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 30930617 | 30930617 |  | GOK | N/A | Full | N/A | 30930617 | 100% | 30930617 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Construction Of 1 No Ward,Administration Block,Completion Of Theatre Works Gate House And Other Associated Works At Lafey Level Iv Hospital In Lafey Sub County. | Proposed Construction Of 1 No Ward,Administration Block,Completion Of Theatre Works Gate House And Other Associated Works At Lafey Level Iv Hospital In Lafey Sub County. | Improve health services and access | Expanded Lafey hospital | MCG/OT/92/2020-2021 | Proposed Construction Of 1 No Ward,Administration Block,Completion Of Theatre Works Gate House And Other Associated Works At Lafey Level Iv Hospital In Lafey Sub County. | Lafey | Lafey | 3.1512 | 41.1899 | Health Services | Health services | Health services | Health services | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 42448176 | 42448176 | 43000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of 10,000M3 Earth Pan At Girile | Proposed Community Library In Elwak In Mandera South Sub-County. | Improve access to water | earth pan | [6 empty] | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 30930617 | 30930617 |  | GOK | N/A | Full | N/A | 30930617 | 100% | 30930617 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF 14NO.HOUSING UNIT AND 14NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA EAST SUB COUNTY | PROPOSED CONSTRUCTION OF 14NO.HOUSING UNIT AND 14NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA EAST SUB COUNTY | accessibility and social equity |  | MCG/OT/098/2018-2019 | IDP Housing Programs - Liability | mandera east | mandera east |  | - | public works | public works | public works | public works |  |  | 2018-2019 | 2018-2019 | 13420630 | 13420630 | 119000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 15,000 CUBIC METRE EARTH PAN AT ELTUL IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF 15,000 CUBIC METRE EARTH PAN AT ELTUL IN MANDERA SOUTH SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | MCG/OT/065/2018-2019 | Construction of 15,000m3 earth pan at Eltul | Mandera south | Elwak North |  |  | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | - | - | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 15,000 CUBIC METRE EARTH PAN AT HARBATE IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF 15,000 CUBIC METRE EARTH PAN AT HARBATE IN MANDERA SOUTH SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/66/2018-2019 |  | Mandera south | Wargadud | 3.0001 | 40.6365 | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 9978675 | 9978675 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 15,000M3 EARTH PAN AT EL TUL IN MANDERA SOUTH(RE-ADVERTISEMENT) | PROPOSED CONSTRUCTION OF 15,000M3 EARTH PAN AT EL TUL IN MANDERA SOUTH(RE-ADVERTISEMENT) | improve water quality and sanitation | sustainable water management practices | MCG/OT/065/2018-2019 | Construction of 15,000m3 earth pan at Eltul | mandera south | elwak south |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 8823925 | 8823925 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 15,000m3 Earth Pan At Sigirso Idda In Mandera West Sub-County | Proposed Construction Of 15,000m3 Earth Pan At Sigirso Idda In Mandera West Sub-County | Climate Resilience by enhancing the county's resilience to climate change. | provides reliable source of income | MCG/OT/52/2017-2018 | Expansion of Sigirso Idda dam | Mandera west |  |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-23 | 2019-03-31 | 2019-03-31 | 12423390 | 12423390 | 12000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT BOLOWLE IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT BOLOWLE IN MANDERA WEST SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/052/2018-19 | Construction of Bolowle earthpan in takaba south ward | Mandera west | Takaba South | 3.2986 | 40.3347 | Water services | Water services | Water services | Water services |  |  | 4/16/2019 | 4/30/2020 | 11969108 | 11969108 | 12000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT DADACH ROPISA IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT DADACH ROPISA IN MANDERA WEST SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | MCG/OT/53/2018-19 | Construction of 20,000M3 earth Pan at Dadach Ropisa - Mandera West | Mandera west | Dandu |  | Dadach ROPISA | Water services | Water services | Water services | Water services |  |  | 4/16/2019 | 4/30/2020 | 11744300 | 11744300 | 12000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT GARBI IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT GARBI IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | MCG/OT/056/2018-19 | Construction of 20,000M3 Garbi earth Pan | Banisa | Kiliweheri | 4.6432 | 40.6895 | Water services | Water services | Water services | Water services |  |  | 4/16/2019 | 4/30/2020 | 9267720 | 9267720 | 9500000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT MURATHELOW IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT MURATHELOW IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  |  | Banisa | Derkale | 4.3219 | 40.6943 | Water services | Water services | Water services | Water services |  |  | 2018-2019 | 2018-2019 | 9999830 | 9999830 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT OGODE IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT OGODE IN MANDERA WEST SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | MCG/OT/059/2018/19 | Construction of 15,000M3 Earth Pan at Ogode | Mandera west | Gither | 3.7412 | 39.8523 | Water services | Water services | Water services | Water services |  |  | 4/16/2019 | 4/30/2020 | 9680475 | 9680475 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT SERMA IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000 CUBIC METRE EARTH PAN AT SERMA IN MANDERA WEST SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/61/2018-19 | Construction of 15,000M3 earthpan at Serma - Mandera West | Mandera west | Lagsure | 3.9453 | 41.8624 | Water services | Water services | Water services | Water services |  |  | 4/16/2019 | 4/30/2020 | 10055975 | 10055975 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 20,000 M3 Earth Pan At Fulaley In Lagsure In Mandera West | Proposed Construction Of 20,000M3 Earthpan At Laag Karo | Improve access to water | earth pan |  |  | Mandera West | Lagsure |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 12000000 | 12000000 |  | GOK | N/A | Full | N/A | 12000000 | 100% | 12000000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT FULALEY IN LAGSURE IN MANDERA WEST | PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT FULALEY IN LAGSURE IN MANDERA WEST | resilence to climate change | boast food security |  | Construction of 20,000 M3 Earth Pan at fulaley lagsure | mandera West | Takaba |  |  | Water Services | Water Services | Water Services |  | 2021 | 2/25/2022 | 3/28/2023 | 3/28/2023 | 12000000 | 12000000 | 10000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 20,000 M3 Earth Pan At Kubi Koyeti In Mandera West Sub County | Proposed Construction And Eqiping Of Radiology Centre At Rhamu Sub County Hospital In Mandera North Sub County. | Improve access to water | earth pan |  |  | Mandera West | Gither | 3.7409 | 39.8593 | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 12000000 | 12000000 |  | GOK | N/A | Full | N/A | 12000000 | 100% | 12000000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT KUBI KOYETI IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 20,000 M3 EARTH PAN AT KUBI KOYETI IN MANDERA WEST SUB COUNTY | resilence to climate change | increase climate resilence |  | Construction of 20,000 M3 Earth Pan at Kubi Koyeti Mandera West | Mandera West | Mandera west | 3.7409 | 39.8593 | Water Services | Water Services | Water Services |  | 2021 | 2/25/2022 | 2/28/2022 | 2/28/2022 | 12000000 | 12000000 | 10000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 20,000 Metre Cubic Qaaba Maalim Musa Earth Pan. | Proposed Construction Of 20,000 Metre Cubic Qaaba Maalim Musa Earth Pan. | to ensure access to clean water | earth pan |  | Construction of 20,000M3 earth Pan at Qaba Maalim Musa |  |  |  |  | Water Services | water services | water services | water services | 2021-12-04 | 2021-12-04 | 4/30/2022 | 4/30/2022 | 9996100 | 9996100 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
proposed construction of 20,000m3 earth pan at chiracha in banisa sub-county | proposed construction of 20,000m3 earth pan at chiracha in banisa sub-county | Providing Water for Domestic Use | Long trekking for water reduced | MCG/OT/40/2017-2018 | construction of 20,000m3 earth pan at Chiracha in Banisa -Sub county | Banisa | Banisa |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-29 | 2019-03-31 | 2019-03-31 | 9683680 | 9683680 | 10000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 20,000m3 earth pan at Gagaba in Mandera west sub-county | proposed construction of 20,000m3 earth pan at Gagaba in Mandera west sub-county | Providing Water for Domestic Use | generates revenue to the government |  | Rehabilitation of Gagaba Water pan | Mandera West | Mandera West |  |  | Water Services | Water Services | Water Services | Water Services | 2017 |  |  |  | 12873080 | 12873080 | 12000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 20,000M3 Ameyi Earth Pan | Proposed Construction Of 20,000M3 Ameyi Earth Pan | to ensure access to clean water | Ameyi Earth pan | MCG/OT/46,21/2020-2021 | Construction of 20,000 M3 Earth Pan at Ameyi in Banisa Sub-County | Banisa | Kiliwehiri |  |  | Water Services | water services | water services | water services | 4/25/2021 |  | 4/28/2022 | 4/28/2022 | 9653143 | 9653143 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction of 20,000m3 Earth Pan At Abba Jida In Mandera South Sub-County | Proposed Construction of 20,000m3 Earth Pan At Abba Jida In Mandera South Sub-County | Climate Resilience by enhancing the county's resilience to climate change. | increases farming nearby dams | MCG/0T/43/2017/2018 | Expansion and disilting of Abba Jida Dam | Mandera south | Elwak |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-29 | 2019-03-31 | 2019-03-31 | 10380000 | 10380000 | 10500000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 20,000m3 Earth Pan At Allo Saden In Mandera West | Proposed Construction Of 20,000m3 Earth Pan At Allo Saden In Mandera West | promote sustainable water management | clean water | MCG/OT/022/2018-2019 |  | Mandera west | Lagsure | 3.6902 | 39.8995 | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 9989000 | 9989000 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 20,000m3 Earth Pan At Allo Saden In Mandera West | Proposed Construction Of 20,000m3 Earth Pan At Allo Saden In Mandera West | promote sustainable water management | clean water |  |  | Mandera west | Lagsure | 3.6902 | 39.8995 | Water services | Water services | Water services | Water services |  |  | 2018-2019 | 2018-2019 | 9989000 | 9989000 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 20,000M3 Earthpan At Laag Karo | Proposed Construction Of 20,000M3 Earthpan At Laag Karo | access to water services | earth pan at Lag Karo in Lagsure |  | Construction of 20,000M3 earth Pan at Lag Karo in Lagsure Ward | Mandera East | Khalalio |  |  | Water Services | water services | water services | water services |  |  |  |  | 9996583 | 9996583 | 5000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of 20.000M3 Maari Dhanaba Earth Pan. | Proposed Construction Of 20.000M3 Maari Dhanaba Earth Pan. | to ensure access to clean water | Mari Dhanaba earth pan | MCG/OT/25/2020-2021 | Construction of 20,000M3 earth pan at Mari Dhanaba in Banisa Sub-County | Banisa | Banisa |  |  | Water Services | water services | water services | water services | 2021-12-04 |  |  |  | 9998465 | 9998465 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED CONSTRUCTION OF 25,000 CUBIC METRE EARTH PAN AT BULLA DIMTU IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 25,000 CUBIC METRE EARTH PAN AT BULLA DIMTU IN MANDERA WEST SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/067/2018/19 | Construction of 25,000M3 earth Pan at Bulla Dimtu - Mandera West | Mandera west | Dandu | 4.0178 | 41.0636 | Water services | Water services | Water services | Water services |  |  | 4/16/2019 | 4/30/2020 | 14997728 | 14997728 | 15000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT ARDA MACHI IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT ARDA MACHI IN BANISA SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/042/2018-2019 | Construction of 30,000M3 Arda machi Earth pan | Banisa | Banisa |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 15088700 | 15088700 | 15000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT AWAL BANDIRA IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT AWAL BANDIRA IN MANDERA SOUTH SUB-COUNTY | improve water quality and sanitation | sustainable water management practices |  | Construction of 20,000M3 earth Pan at Awal Bandira | Mandera south | Elwak North |  |  | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 14949375 | 14949375 | 15000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT AWAL BANDIRA IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT AWAL BANDIRA IN MANDERA SOUTH SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/043/2018/19 | Construction of 20,000M3 earth Pan at Awal Bandira | Mandera south | Elwak North | 3.1145 | 40.8767 | Water services | Water services | Water services | Water services |  |  | 4/16/2019 | 4/16/2019 | 14949375 | 14949375 | 15000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT HAIGURACH IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT HAIGURACH IN BANISA SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/045/2018-2019 | Construction of 30,000M3 EarthPan at Haigurach | Banisa | Banisa | 3.9478 | 40.343 | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 15450660 | 15450660 | 15500000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT HAIGURACH IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT HAIGURACH IN BANISA SUB-COUNTY | promote sustainable water management | clean water |  | Construction of 30,000M3 EarthPan at Haigurach | Banisa | Banisa | 3.9478 | 40.343 | Water services | Water services | Water services | Water services |  |  | 2018-2019 | 2018-2019 | 15450660 | 15450660 | 15500000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT KUBDISHAN IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT KUBDISHAN IN MANDERA WEST SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/046/2018-2019 | construction of 30,000M3 earthpan at kubdishan | Mandera west | Takaba |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 14980140 | 14980140 | 15000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT OMAR JILLAOW IN MANDERA EAST SUB-COUNTY WEST | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT OMAR JILLAOW IN MANDERA EAST SUB-COUNTY WEST | promote sustainable water management | clean water | MCG/OT/048/2018-2019 | Constructions of 30,000M3 earth pan at Omar Jilaow | Mandera East | Arabia | 3.9091 | 40.3468 | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 14929425 | 14929425 | 15500000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT SACHGODOM IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 30,000 CUBIC METRE EARTH PAN AT SACHGODOM IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/049/2018-2019 | Construction of 30,000M3 earth Pan at Sachgodom | Banisa | Banisa |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 14860440 | 14860440 | 15000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 30,000M3 Bulla Madina Earth Pan | Proposed Construction Of 30,000M3 Bulla Madina Earth Pan | to nsure access to clean water | earthpan | MCG/OT/29/2020-2021 | Construction of 30,000m3 earth Pan at Bula Madina in Mandera West | Mandera West | Gither |  |  | Water Services | water services | water services | water services | 2021-12-04 | 2021-12-04 | 4/30/2022 | 4/30/2022 | 14985579 | 14985579 | 10000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of 30,000m3 Earth Pan At Allo Golbo Ropi In Mandera South | Proposed Construction Of 30,000m3 Earth Pan At Allo Golbo Ropi In Mandera South | improve water quality and sanitation | sustainable water management practices | MCG/OT/023/2018-2019 |  | Mandera south | Ewak South |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 19655423 | 19655423 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
proposed construction of 30,000m3 earth pan at arda boji in mandera west sub-county | proposed construction of 30,000m3 earth pan at arda boji in mandera west sub-county | Improving Livelihoods, Contributing to the overall wellbeing by addressing water scarcity. | Reduces clan conflict for water | MCG/OT/44/2017-2018 | construction of 30,000M3 at ardha boji (mandera west ) | Mandera west | takaba |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-24 | 2019-03-31 | 2019-03-31 | 16844940 | 16844940 | 15000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction of 30,000m3 Earth Pan At Daka Qaresa In Banisa Sub-County | Proposed Construction of 30,000m3 Earth Pan At Daka Qaresa In Banisa Sub-County | Animal Watering , Supplying water for livestock | provides fresh water for domestic use |  | Construction of 30,000m3 earthpan at Daka Qaresa (Banisa Sub-County) | Banisa | Banisa |  |  | Water Services | Water Services | Water Services | Water Services | 2017 |  |  |  | 16500120 | 16500120 | 15000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of 30,000m3 earth pan at Didkobain in mandera west sub-county | Improving Livelihoods, by addressing water scarcity challenges. | Irrigation, Supporting agricultural activities through water harvesting and storage . | generates revenue to the government | MCG/OT/42/2017/2018 | construction of 30,000m3 at Diid Kooba (mandera West) | Mandera west | takaba |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-04-03 | 2019-04-30 | 2019-04-30 | 14900000 | 14900000 | 15500000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 30,000M3 Komor Qufa Earth Pan In Mandera West Sub-County. | Proposed Construction Of 30,000M3 Komor Qufa Earth Pan In Mandera West Sub-County. | to ensure access to clean water | Kamor Qufa earthpan | MCG/OT/30/2020-2021 | Construction of 30,000M3 earth Pan atKamor Qufa earthpan | [5 empty] | water services | water services | water services | 2021-12-04 | 2021-12-04 | 4/30/2022 | 2022-04-30 | 14985000 | 14985000 |  | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of 30,000M3 Qarsa Earth Pan In Mandera West Sub County | Proposed Expansion Of Qofole 20,000M3 Earthpan In Mandera West Sub-County. | Improve access to water | earth pan | [6 empty] | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 14999500 | 14999500 |  | GOK | N/A | Full | N/A | 14999500 | 100% | 14999500 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF 30,000M3 QARSA EARTH PAN IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 30,000M3 QARSA EARTH PAN IN MANDERA WEST SUB COUNTY | food security | boast food security |  | construction of 30000m3 dam at Qarsa | mandera West | Mandera West |  |  | Water Services | Water Services | Water Services |  | 2021 | 10//12/2021 | 12/31/2022 | 12/31/2022 | 14480000 | 14480000 | 15000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 30,000M3 QARSA EARTH PAN IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 30,000M3 QARSA EARTH PAN IN MANDERA WEST SUB COUNTY | resilence to climate change | improve water security |  | Water Services | Mandera West | Mandera West |  |  | Water Services | Water Services | Water Services |  | 2021 |  |  |  | 19991880 | 19991880 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 32No Housing Unit And 32No Toilet For Vulnerable Persons In Lafey, Mandera North And Banisa Sub Counties In Mandera County | Proposed Construction Of Box Culvert/Celled Drifts At Hareri In Arabia Sub County | improve housing |  |  | Liability for IDP Housing | Banisa | Banisa |  |  | Social Services | Social Services | Social Services | Social Services |  |  |  |  | 31578912 | 31578912 | 97387075 | GOK | N/A | Full | N/A | 31578912 | 100% | 31578912 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF 32NO HOUSING UNIT AND 32NO TOILET FOR VULNERABLE PERSONS IN LAFEY, MANDERA NORTH AND BANISA SUB COUNTIES IN MANDERA COUNTY | improve living condtion for vulnerables | disease p+E3:E24revention |  | Construction of houses for vulnerable families | countywide | countywide |  |  | special programme | special programme | special programme |  | 2021 |  |  |  | 31578912 | 31578912 | 85000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 40,000 CUBIC METRE EARTH PAN AT KAMOR ELLE IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF 40,000 CUBIC METRE EARTH PAN AT KAMOR ELLE IN MANDERA EAST SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/069/2018-2019 | Water pans for Komor Elle/Bida and Karo, | Mandera East | khalalio |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 19796910 | 19796910 | 20000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 44No Housing Unit And 44No Toilet For Vulnerable Persons In Mandera East Sub County | Proposed Construction Of Drift On Lagsure At Kiliwehiri In Kiliwehiri Sub-County. |  |  |  | Liability for IDP Housing | Mandera East | Neboi | 3.9001 | 41.7947 | Social Services | Social Services | Social Services | Social Services |  |  |  |  | 43421048 | 43421048 | 97387075 | GOK | N/A | Full | N/A | 43421048 | 100% | 43421048 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF 44NO HOUSING UNIT AND 44NO TOILET FOR VULNERABLE PERSONS IN MANDERA EAST SUB COUNTY | PROPOSED CONSTRUCTION OF 44NO HOUSING UNIT AND 44NO TOILET FOR VULNERABLE PERSONS IN MANDERA EAST SUB COUNTY | improve access to sanitation | environmental protection |  | Construction of houses for vulnerable families | Mandera East | Township & Neboi |  |  | special programme | special programme | special programme |  | 2021 |  |  |  | 43421048 | 43421048 | 85000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 50,000 CUBIC METRE EARTH PAN AT TARBE GALMSINGO IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 50,000 CUBIC METRE EARTH PAN AT TARBE GALMSINGO IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/070/2018-2019 | Construction of 50,000M3 earth Pan at Tarbe Galmsingo-Malka Mari Ward | Banisa | Banisa |  | latitude: 302 longtitude: 1012100 | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 28907550 | 28907550 | 29000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 50No Toilets Block At Neboi Ward In Mandera East Sub-County. | Proposed Construction Of 50No Toilets Block At Neboi Ward In Mandera East Sub-County. | best hygiene practices | public toilets in Neboi | MCG/OT/76/2020-2021 | Construction of 50 of Public Toilets in Neboi Ward | Mandera East | Neboi |  |  | Social Services | Social Services | Social Services | Social Services | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 9995000 | 9995000 | 10000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of 60,000m3 Earth Pan At Waranqara In Lafey Sub-County | Proposed Construction Of 60,000m3 Earth Pan At Waranqara In Lafey Sub-County | Irrigation, Supporting agricultural activities through water harvesting and storage . | Reduces clan conflict for water | MCG/OT/55/2017-2018 | construction of 60,000m3 at waranqara (lafey-sub-county) | Lafey | Waranqara |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-23 | 2019-03-31 | 2019-03-31 | 30997890 | 30997890 | 31000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of 60,000M3 Earthpan At Kopi. | Proposed Construction Of 60,000M3 Earthpan At Kopi. | improve water acess | Kopi earthpan |  | Construction of 60,000M3 earth Pan at Kopi |  |  |  |  | Water Services | water services | water services | water services | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 32686574 | 32686574 | 15000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of 60,000M3 Gagaba Earth Pan | Proposed Construction Of 60,000M3 Gagaba Earth Pan | to nsure access to clean water | Gagaba earth pan | MCG/OT/32/2020-2021 | Construction of Earth Pan at Gagaba | Mandera West | Dandu | 3.5662 | 39.7174 | Water Services | water services | water services | water services | 2021-12-04 | 2021-12-04 | 4/30/2022 | 4/30/2022 | 30741617 | 30741617 | 19300000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED CONSTRUCTION OF 60,000M3 HAR DUMAYO EARTH PAN IN BANISA SUB-COUNTY, MANDERA COUNTY. | PROPOSED CONSTRUCTION OF 60,000M3 HAR DUMAYO EARTH PAN IN BANISA SUB-COUNTY, MANDERA COUNTY. | resource management | improve water security |  | construction of 60,000M3 earth Pan at Har Dumayo Banisa | Banisa | Banisa | 3.8866 | 40.3074 | Water Services | Water Services | Water Services |  | 2021 | 10//12/2021 | 12/31/2022 | 12/31/2022 | 32820616.5 | 32820616.5 | 31000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of 60,000M3 Laaga Dosota Earth Pan | Proposed Construction Of 60,000M3 Laaga Dosota Earth Pan | to nsure access to clean water | Laaga Duusota earthpan | MCG/OT/33/2020-2021 | Construction of 60,000M3 earth pan Laaga Duusoota |  |  |  |  | Water Services | water services | water services | water services | 2021-12-04 | 2021-12-04 | 4/30/2022 | 4/30/2022 | 30984734 | 30984734 | 16000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of 60,000M3 Malaba Earth Pan. | Proposed Construction Of 60,000M3 Malaba Earth Pan. | to ensure access to clean water | Malaba earth pan | MCG/OT/34/2020/2021 | Construction of 20,000M3 earth Pan at Malaba in Gither Ward | Mandera West | Gither |  |  | Water Services | water services | water services | water services | 2021-12-04 | 2021-12-04 | 4/30/2022 | 4/30/2022 | 30000000 | 30000000 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of 60,000M3 Qordobo Saglan Earthpan | Proposed Construction Of 60,000M3 Qordobo Saglan Earthpan | improve water acess | Qorbo Saqlan earth pan |  | Construction of 60,000M3 Earth Pan at Qordobo Saglan |  |  |  |  | Water Services | water services | water services | water services |  |  |  |  | 30499460 | 30499460 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN BANISA SUB COUNTY | accessibility and social equity |  |  | IDP Housing Programs - Liability | Banisa | Banisa |  | - | Public Works | public works | public works | public works |  |  | 4/30/2019 | 4/30/2019 | 5250000 | 5250000 | 119000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN KUTULO SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN KUTULO SUB COUNTY | accessibility and social equity |  | MCG/OT/095/2018/19 | IDP Housing Programs - Liability | mandera south | kutulo | 2.4439 | 40.6475 | Roads | Roads | Roads | Roads |  |  | 4/16/2019 | 4/30/2020 | 5648167 | 5648167 | 119000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN LAFEY SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN LAFEY SUB COUNTY | accessibility and social equity |  | MCG/OT/092/2018-2019 | IDP Housing Programs - Liability | mandera east | lafey | 3.1541 | 41.1856 | Public Works | public works | public works | public works |  |  | 4/30/2019 | 4/30/2019 | 6308022 | 6308022 | 119000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA NORTH SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA NORTH SUB COUNTY | accessibility and social equity |  | MCG/OT/094/2018/19 | IDP Housing Programs - Liability | Mandera north | Guticha |  | Guticha | Roads | Roads | Roads | Roads |  |  | 4/16/2019 | 4/30/2020 | 5950000 | 5950000 | 119000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA SOUTH SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA SOUTH SUB COUNTY | accessibility and social equity |  | MCG/OT/097/2018-19 | IDP Housing Programs - Liability | mandera south | Wargadud |  | wargadud | Roads | Roads | Roads | Roads |  |  | 4/16/2019 | 4/30/2020 | 7500305 | 7500305 | 119000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF 7NO.HOUSING UNIT AND 7NO. TWIN TOILET FOR VULNERABLE PERSONS IN MANDERA WEST SUB COUNTY | accessibility and social equity |  | MCG/OT/096/2018-19 | IDP Housing Programs - Liability | mandera west | Dandu |  | Dandu | Roads | public works | public works | Roads |  |  | 4/16/2019 | 4/30/2020 | 5870702 | 5870702 | 119000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed construction of arda garabicha dispensary block in banisa subcounty | Proposed construction of arda garabicha dispensary block in banisa subcounty | Improve Access to Primary Healthcare Services | improved heathcare access | MCG/OT/20/2017-201825/03 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) | BANISA | BANISA |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-03-25 | 2019-03-31 | 2019-03-31 | 7925758 | 7925758 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of arges awara earth pan from 20,000m3 to in mandera west sub-county | proposed construction of arges awara earth pan from 20,000m3 to in mandera west sub-county | Ensuring households have access to safe drinking water | provides fresh water for domestic use | MCG/OT/47/2017-2018 | construction of 20,000m3 earth pan at Argesa Awara in mandera west-Sub county | Mandera west |  |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-29 | 2018-03-31 | 2019-03-31 | 13996080 | 13996080 | 10000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of bachile dispensary block in mandera east subcounty | Proposed construction of bachile dispensary block in mandera east subcounty | Reduce delays in seeking care (for minor ailments, emergencies). | provide deep healthcare awareness | MCG/OT/21/2017-2018 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) | Mandera east | Mandera east |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-03-24 | 2019-03-31 | 2019-03-31 | 7922162 | 7922162 | 35000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of Banisa Air Strip In Banisa Sub County(Re-Advertisement) | Proposed Disilting And Expansion Of Idd Kinisa Earth Pan In Mandera West. | impove road infrustructure | Aistrip |  |  | Banisa | Banisa | 3.899 | 40. 40.3193 | Roads | Roads | Roads | Roads |  |  |  |  | 74535197 | 74535197 |  | GOK | N/A | Full | N/A | 74535197 | 100% | 74535197 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Construction Of Boundary Security Wall And Fencing Of Government Offices | Proposed Construction Of Boundary Security Wall And Fencing Of Government Offices | improve security of government premises | Perimeter fence | MCG/OT/95/2020-2021 | Security Wall and Fencing of Government offices | Mandera East | Neboi | 3.9354 | 41.8612 | Public Works | public service | public service | public service | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 91800426 | 91800426 | 26500000 | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of Box Culvert/Celled Drifts At Hareri In Arabia Sub County | Proposed Construction Of Box Culvert/Celled Drifts At Hareri In Arabia Sub County | enhance movement of goods and services | Khalalion Road-Hareri | MCG/OT/RMLF/07/2020-2021 | Construction of Box culvert/Celled drifts on Khalalio Road at Hareri (RMLF) | Arabia | Arabia | 3.9385 | 41.4574 | Roads | Roads | Roads | Roads | 2021-12-04 | 2021-12-04 | 4/30/2023 | 4/30/2023 | 146591520 | 146591520 | 40000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of Bur John -Malka Mari Road In Banisa Sub-County. | Proposed Construction Of Bur John -Malka Mari Road In Banisa Sub-County. | enhance movement of goods and services | Bur John-Malka Mari Road |  | Construction of Bur John - Malka Mari Road - RMLF | Banisa | Malkamari | 4.2369 | 40.697 | Roads | Roads | Roads | Roads |  |  |  |  | 29773836 | 29773836 | 30000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of Celled Drift At Dandu Hospital Access Road In Mandera West Sub County | Proposed Dololo Dispensary Block In Mandera South Sub-County. | impove road infrustructure | Drift |  |  | Mandera West | Dandu |  |  | Roads | Roads | Roads | Roads |  |  |  |  | 15218040 | 15218040 |  | GOK | N/A | Full | N/A | 15218040 | 100% | 15218040 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF CELLED DRIFT AT DANDU HOSPITAL ACCESS ROAD IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF CELLED DRIFT AT DANDU HOSPITAL ACCESS ROAD IN MANDERA WEST SUB COUNTY | resource management | improve water security |  | Celled drift in Dandu Hospital access road | Mandera West | Dandu |  |  | Health Services | Health Services | Health Services |  | 2021 |  |  |  | 15218040 | 15218040 | 10000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Chain Link Fencing At Government Institution. | Proposed Construction Of Chain Link Fencing At Government Institution. | to protect Government premises | Chainlink fence | MCG/OT/50/2020-2021 | CONSTRUCTION OF CHAINLINK FENCING AT GOVERNMENT INSTITUTION | COUNTYWIDE | COUNTY WIDE |  |  | Public Works | Public works | Public works | Public works | 4/29/2021 | 4/29/2021 | 4/30/2022 | 4/30/2022 | 39001578 | 39001578 |  | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of Chainlink Fencing Of Islamic And Secular University Compound | Proposed Light Grading And Gravelling Of Road At Khalafow Village In Mandera West Sub-County | [8 empty] | Public Works | Public Works | Public Works | Public Works |  |  |  |  | 36000136 | 36000136 |  | GOK | N/A | Full | N/A | 36000136 | 100% | 36000136 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF CHAINLINK FENCING OF ISLAMIC AND SECULAR UNIVERSITY COMPOUND | PROPOSED CONSTRUCTION OF CHAINLINK FENCING OF ISLAMIC AND SECULAR UNIVERSITY COMPOUND | to avoid materials theft and restrict learners from absentesim | improve security |  | Chain Linking Fencing of Islamic and Secular University land | Mandera East | Neboi |  |  | Education | Education | Education |  | 2021 | 2021-10-12 | 12/31/2022 | 12/31/2022 | 36000136 | 36000136 | 30000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Choroqo- Guba Road In Banisa Sub-County | Proposed Construction Of Choroqo- Guba Road In Banisa Sub-County | smooth flow of goods and services | boost trade | MCG/OT/011/2018-2019 | Roads Maintenance Fuel Levy for 2018/2019 (Takaba-Gither, Rhamu - Malka Mari, Kutayu - Elwak, Elwak-Elgolicha, Awara-Morothiley & Guba-Choroqo ) | Banisa | Guba |  | - | Roads | Roads | Roads | Roads |  |  | 4/30/2019 | 4/30/2019 | 24967538 | 24967538 | 267035293 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF DISPENSARY AT BOJI GARSE IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF DISPENSARY AT BOJI GARSE IN MANDERA SOUTH SUB-COUNTY | improving health and preventing diseases | healthy lifestyle | MCG/OT/079/2018-2019 | Dispensary at Boji Garse | Mandera south | Elwak North |  | - | health services | health services | health services | health services |  |  | 4/30/2019 | 4/30/2019 | 9123415 | 9123415 | 7000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF DISPENSARY AT GARBAQOLEY IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF DISPENSARY AT GARBAQOLEY IN MANDERA EAST SUB-COUNTY | improving health and preventing diseases | healthy lifestyle | MCG/OT/080/2018-2019 | Dispensary at Garboqole, Kamor Ele (with Bida), Karro | mandera east | mandera east | 3.9031 | 41.861 | health services | health services | health services | health services |  |  | 4/30/2019 | 4/30/2019 | 7500000 | 7500000 | 18000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF DISPENSARY AT KARO IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF DISPENSARY AT KARO IN MANDERA EAST SUB-COUNTY | improving health and preventing diseases | healthy lifestyle |  | Dispensary at Garboqole, Kamor Ele (with Bida), Karro | mandera East | mandera east | 3.8916 | 41.6748 | health services | health services | health services | health services |  |  | 4/30/2019 | 4/30/2019 | 7600000 | 7600000 | 18000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF DISPENSARY AT SHIRSHIR IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF DISPENSARY AT SHIRSHIR IN MANDERA NORTH SUB-COUNTY | improving HEALTH SERVICES and preventing diseases | HEALTH SERVICESy lifestyle | MCG/OT/083/2018-19 | construction of shirshir dispensery in guticha ward | Mandera north | ashabito | 3.5367 | 40.7411 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  |  | 4/16/2019 | 4/30/2020 | 7986882 | 7986882 | 5500000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Drift At Lag Warera Between Iyan Abkula And Takaba South In Mandera West Sub County(Re-Advertisement) | Proposed Construction Of Slaughter House In Elwark Mandera South Sub-County. | impove road infrustructure | Drift |  |  | Mandera West | Takaba |  |  | Roads | Roads | Roads | Roads |  |  |  |  | 79992885 | 79992885 |  | GOK | N/A | Full | N/A | 79992885 | 100% | 79992885 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF DRIFT BETWEEN WARANQARA AND LAFEY ROAD IN LAFEY SUB-COUNTY | PROPOSED CONSTRUCTION OF DRIFT BETWEEN WARANQARA AND LAFEY ROAD IN LAFEY SUB-COUNTY | smooth flow of goods and services | boost trade | MCG/OT/125/2018-2019 | Construction of drift on Lafey Waranqara Road | mandera east | lafey | 3.3856 | 41.0361 | Roads | Roads | Roads | Roads |  |  | 4/30/2019 | 4/30/2019 | 14937335 | 14937335 | 11000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Drift On Lagsure At Kiliwehiri In Kiliwehiri Sub-County. | Proposed Construction Of Drift On Lagsure At Kiliwehiri In Kiliwehiri Sub-County. | improve access to roads | Lagsure drift |  | Construction of Drift on Lagsure at Kiliwehiri | Kiliweheri | Kiliwheri | 3.4068 | 40.2256 | Roads | Roads | Roads | Roads |  |  |  |  | 21801620 | 21801620 | 9000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed construction of Electrical workshop at MTTI | Proposed construction of Electrical workshop at MTTI | for learning purposes | productions of local electrical technicians |  | Mandera Technical Training Institutes 2 workshops | #REF! | #REF! |  |  | Education | Education | Education | Education | 2017 |  |  |  | 29064716 | 29064716 |  | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of Elwak- Kutayu Road | Proposed Construction Of Elwak- Kutayu Road | improve access | increased safety,reducd accidents | MCG/OT/010/2018- 19 | Roads Maintenance Fuel Levy for 2018/2019 (Takaba-Gither, Rhamu - Malka Mari, Kutayu - Elwak, Elwak-Elgolicha, Awara-Morothiley & Guba-Choroqo ) | mandera south | Elwak SOUTH | 2.8019 | 40.9053 | Roads | Roads | Roads | Road /Public Works |  |  | 2019-04-01 | 7/31/2019 | 82035954 | 82035954 | 267035293 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed construction of fresh water system for mandera refferal hospital in mandera east | Proposed construction of fresh water system for mandera refferal hospital in mandera east | To improve hygienity and cleaniness | improved sanitation standard and good well being | MCG/OT/31/2017-2018 | Drilling of new borehole, piping to MCRH, underground water tank, elavated metalic tank and water reticulation with MCRH | Mandera east | Neboi |  |  | Health Services | Health Services | Health Services | Health Services | 2017 |  |  |  | 29784386 | 29784386 | 30000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of Gates, Cabro And Parking Shades At New County Headquarters In Mandera East Sub-County | Proposed Sala Farms Agricultural Improvement Project At Sala In Lafey Sub-County In Mandera | improve service delivery | Gates and parking shades |  |  | Mandera Easr | Neboi | 3.9315 | 41.8011 | Public Works | Public Works | Public Works | Public Works |  |  |  |  | 19991985 | 19991985 |  | GOK | N/A | Full | N/A | 19991985 | 100% | 19991985 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF GATES, CABRO AND PARKING SHADES AT NEW COUNTY HEADQUARTERS IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF GATES, CABRO AND PARKING SHADES AT NEW COUNTY HEADQUARTERS IN MANDERA EAST SUB-COUNTY | security boast | enhance security of the hospital |  | Construction of new Gate, Cabro the Road from the gate to the new admin block and the parking area at MTTI | Mandera East | Neboi |  |  | Public Works | Public Works | Public Works |  | 2021 | 2021-10-12 | 12/31/2022 | 12/31/2022 | 19991985 | 19991985 | 20000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed construction of hardimtu dispensary block in mandera west subcounty | Proposed construction of hardimtu dispensary block in mandera west subcounty | Improve Access to Primary Healthcare Services | increased immunizat+F23+E23:K23+E2+E23:O24 | MCG/OT/23/2017-2018 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) | Mandera west | Mandera west |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-03-29 | 2019-03-31 | 2019-03-31 | 7900296 | 7900296 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of hardimtu earth pan of 20,000m3 in mandera west sub-county | proposed construction of hardimtu earth pan of 20,000m3 in mandera west sub-county | reducing the risk of waterborne diseases. | generates revenue to the government | MCG/0T/48/2017-2018 | Construction of 20,000M3 Earth Pna at Hardimtu dams | Mandera west |  |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-27 | 2019-03-31 | 2019-03-31 | 14128485 | 14128485 | 10000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of Harshilmi – Sake Road To Gravel Standard | Proposed Expansion And Desilting Of Harshilmi Earth Pan In Mandera West Sub-County. | [8 empty] | Roads | Roads | Roads | Roads |  |  |  |  | 29467000 | 29467000 |  | GOK | N/A | Full | N/A | 29467000 | 100% | 29467000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed construction of harwale dispensary block in mandera south subcounty | Proposed construction of harwale dispensary block in mandera south subcounty | Ensure essential services (maternal/child health, immunization,) are available locally. | community engagement | MCG/OT/24/2017-2018 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) | Mandera south | Mandera south |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-03-29 | 2019-03-31 | 2019-03-31 | 7851599 | 7851599 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of hullow dispensary block in banisa subcounty | Proposed construction of hullow dispensary block in banisa subcounty | Reduce delays in seeking care (for minor ailments, emergencies). | reduce disease outbreak | MCG/0T/26/2017/2018 |  | Banisa | Malkamari |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-03-22 | 2019-03-31 | 2019-03-31 | 7795200 | 7795200 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of irestino dispensary block in irestino subcounty | Proposed construction of irestino dispensary block in irestino subcounty | Reduce delays in seeking care (for minor ailments, emergencies). | lowered the number of referals | MCG/OT/28/2017-2018 | Construction of 6 new dispensaries. (Bachile, Hullow, Iresteno, Harwale, Arda Garbicha, Har dimtu and Tawfiq) |  | Irestino |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-03-26 | 2019-03-31 | 2019-03-31 | 7806162 | 7806162 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF KARO AIRPORT (RUN-WAY)IN MANDERA EAST | PROPOSED CONSTRUCTION OF KARO AIRPORT (RUN-WAY)IN MANDERA EAST | smooth flow of goods and services | boost trade | MCG/OT/115/2018/19 and MCG/OT/122/18-19 |  | mandera east |  |  | karo | Roads | Roads | Roads | Roads |  |  | 2018-2019 | 2018-2019 | 77175525 | 77175525 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF KMTC IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF KMTC IN MANDERA EAST SUB-COUNTY | promote quality education | human resources development | MCG/OT/091/2018-2019 | Construction of KMTC in partnership with Kenya Medical Training College. | mandera east | Neboi | 3.939 | 41.7892 | Education | Education | Education | Education |  |  | 4/30/2019 | 4/30/2019 | 256235085 | 256235085 | 80000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed construction of kubi dispensary block in kubi subcounty | Proposed construction of kubi dispensary block in kubi subcounty | Improve Access to Primary Healthcare Services | improved heathcare access | MCG/0T/29/2017/2018 | Proposed construction of Dispensary at Kubi , Mandera North | Ashabito | Marothiley |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-04-06 | 2019-04-30 | 2019-04-30 | 7401585 | 7401585 | 8000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF KUTULO LEVEL IV HOSPITAL IN KUTULO SUB-COUNY | PROPOSED CONSTRUCTION OF KUTULO LEVEL IV HOSPITAL IN KUTULO SUB-COUNY | improving HEALTH SERVICES and preventing diseases | HEALTH SERVICESy lifestyle | MCG/OT/090/2018-19 | Level 4 hospital at Kutulo sub-county (Outpetient dept, Male and Female Wards, Marternity Wing, Theater, Radiology, Lab, etc) | mandera south | kutulo | 2.4451 | 40.652 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  |  | 4/16/2019 | 4/30/2022 | 120,412,,837.20 | 120,412,,837.20 | 65000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Lafey Air Strip In Lafey Sub County(Re-Advertisement) | Proposed Construction Of 20,000 Metre Cubic Qaaba Maalim Musa Earth Pan. | impove road infrustructure | Aistrip |  |  | Lafey | Lafey | 3.1926 | 41.1968 | Roads | Roads | Roads | Roads |  |  |  |  | 75000000 | 75000000 |  | GOK | N/A | Full | N/A | 75000000 | 100% | 75000000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Construction Of Livestock Demo Farm | Proposed Community Library In Rhamu In Mandera North Sub-County. |  |  |  | Livestock Demo Farms - Chain-link fencing, Cattle shade and other infrastructure - On-going | Mandera East | Neboi |  |  | Social Services | Social Services | Social Services | Social Services |  |  |  |  | 50105610 | 50105610 | 30105610 | GOK | N/A | Full | N/A | 50105610 | 100% | 50105610 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF LIVESTOCK DEMONSATRATION FARM IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF LIVESTOCK DEMONSATRATION FARM IN MANDERA EAST SUB-COUNTY | enhancing productivity | increasing crop yields | MCG/OT/105/2018-2019 | Livestock Demo Farms - Chain-link fencing, Cattle shade and other infrastructure | mandera east | Neboi | 3.904 | 41.7686 | Livestock | Livestock | Livestock | Livestock |  |  | 4/30/2019 | 4/30/2019 | 50105610 | 50105610 | 20000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF LIVESTOCK DEMONSATRATION FARM IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF LIVESTOCK DEMONSATRATION FARM IN MANDERA EAST SUB-COUNTY | enhancing productivity | increasing crop yields | MCG/OT/105/2018-2019 | Livestock Demo Farms - Chain-link fencing, Cattle shade and other infrastructure | mandera east | Neboi |  | mandera town | Livestock | Livestock | Livestock | Livestock |  |  | 4/30/2019 | 4/30/2020 | 50105610 | 50105610 | 20000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Mandera County Public Service Board Office Block At Mandera Town In Mandera East Sub-County. | Proposed Construction Of Mandera County Public Service Board Office Block At Mandera Town In Mandera East Sub-County. | improve service delivery | CPSB office block |  | Construction of County Public Service Board office | Mandera East | Neboi | 3.9244 | 41.7973 | Public Service Board | public service | public service | public service |  |  |  |  | 74800000 | 74800000 | 10000000 | GOK | NA | 100% | 0 | 74800000 |  |  |  |  | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of Mandera North Sub-County Headquarters Office Block At Rhamu Town In Mandera North | Proposed Construction Of Mandera North Sub-County Headquarters Office Block At Rhamu Town In Mandera North | Ensure access to clean water | subcounty headquartes | MCG/OT/65/20202021 | Consruction of Rhamu Sub-County Headquarters | Mandera North | Rhamu | 3.9372 | 41.2238 | Public Works | Public works | Public works | Public works | 2021-12-04 | 2021-12-04 | 4/30/2022 | 4/30/2022 | 78993535 | 78993535 | 25000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED CONSTRUCTION OF MANDERA TEACHERS TRAINING COLLEGE IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF MANDERA TEACHERS TRAINING COLLEGE IN MANDERA EAST SUB-COUNTY | promote quality education | human resources development | MCG/OT/126/2018-19 | Mandera Technical Training Institutes 2 workshops | mandera east | neboi |  | mandera town green county | Education | Education | Education | Education services |  |  | 4/16/2018 | 4/30/2019 | 250000000 | 250000000 | 30000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF MARKET IN ELDANABA MANDERA WEST SUBCOUNTY | PROPOSED CONSTRUCTION OF MARKET IN ELDANABA MANDERA WEST SUBCOUNTY | social inclusion, Economic empwerment and revenue generating | Support for small-scale traders and entrepreneurs |  | Trade | Mandera West | Dandu |  |  | Trade | Trade | Trade |  | 2022 | 2022-05-09 | 9/30/2023 | 9/30/2023 | 25500524 | 25500524 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Market Stalls At Banisa In Banisa Sub County | Proposed Re-Channeling Of Lag Warera Seasonal River Gabions In Takaba In Mandera West Sub-County. |  |  |  | Market stalls operationalization across the County ( Eymole Market, Borehole 11, Ashabito, Khalalio, Youth, ) |  |  |  |  | Trade | Trade | Trade | Trade |  |  |  |  | 349,32,994 | 349,32,994 | 7000000 | GOK | N/A | Full | N/A | 349,32,994 | #VALUE! | 349,32,994 | N/A | #VALUE! | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF MARKET STALLS AT BANISA IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF MARKET STALLS AT BANISA IN BANISA SUB COUNTY | to create retail space and increase sales | low cost entry point and improve spaces for vendors |  |  | Banisa | banisa | 3.9405 | 40.3446 | trade | trade | trade |  | 2021 | 2021-10-12 | 12/31/2022 | 12/31/2022 | 349,32,994 | 349,32,994 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed construction of maternity wing at Takaba Hospital in Mandera West | Proposed construction of maternity wing at Takaba Hospital in Mandera West | Ensure essential services (maternal/child health, immunization, nutrition) are available. | increased immunization coverage |  | Construction of maternity in Takaba sub county hospital. | Mandera west | takaba |  |  | Health Services | Health Services | Health Services | Health Services | 2017 |  |  |  | 65384577 | 65384577 | 23000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of Maternity/Delivery Block, Solar Installation, Twin Toiletn At Kutayu Health Centre In Mandera South | Proposed Construction Of Maternity/Delivery Block, Solar Installation, Twin Toiletn At Kutayu Health Centre In Mandera South | Ensure essential services (maternal/child health, immunization, ) are available locally. | provide deep healthcare awareness | MCG/OT/30/2017/2018 | Construction of Kutayu Marternity wing | Mandera west | takaba |  |  | Health Services | Health Services | Health Services | Health Services | 2017 |  |  |  | 19663879 | 19663879 | 4000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed construction of mechanical workshop at MTTI | proposed construction of mechanical workshop at MTTI | for learning purposes | well trained mechanical students graduates |  | Mandera Technical Training Institutes 2 workshops | Mandera east | Neboi |  |  | Education | Education | Education | Education | 2017 |  |  |  | 29117814 | 29117814 | 60000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED CONSTRUCTION OF MODERN SLAUGHTER HOUSE IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF MODERN SLAUGHTER HOUSE IN MANDERA EAST SUB-COUNTY | enhancing productivity | increasing crop yields | MCG/OT/16/2018-2019 | Constructions of modern slaughter house in Mandera East | Mandera East | Neboi | 3.9342 | 41.8292 | Livestock | Livestock | Livestock | Livestock |  |  | 4/30/2019 | 4/30/2019 | 119752258 | 119752258 | 61291705 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF MODERN SLAUGHTER HOUSE IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF MODERN SLAUGHTER HOUSE IN MANDERA EAST SUB-COUNTY | enhancing productivity | increasing crop yields | MCG/0T/106/2018-19 | Constructions of modern slaughter house in Mandera East | Mandera East | Neboi | 3.9342 | 41.8292 | Livestock | Livestock | Livestock | agriculture,livestock development |  |  | 2018-2019 | 2018-2019 | 119752258 | 119752258 | 61291705 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Modern Slaughter House Mordern Slaughter In Mandera East Sub County | Proposed Community Library In Lafey In Lafey South Sub County. |  |  |  | External and phase II for Modern slaughter House in Mandera East | Mandera East | Neboi | 3.904 | 41.7686 | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 119752258 | 119752258 | 20000000 | GOK | N/A | Full | N/A | 119752258 | 100% | 119752258 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF MUNICIPALITY OFFICE BLOCK IN MANDERA EAST | PROPOSED CONSTRUCTION OF MUNICIPALITY OFFICE BLOCK IN MANDERA EAST | enhance public service | accessibility and social equity | MCG/OT/04/2018-19 | Construction of Municipality Office Blocks | mandera east | Neboi | 3.9308 | 41.7991 | public works | public works | public works | public works |  |  | 10/26/2018 | 10/31/2019 | 59021552 | 59021552 | 40000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of N0.Ward,Maternity Block,Mechanical Works And Associated Civil Works At Lafey Level 1V Hospital At Lafey Sub County | Proposed Expansion Of Arabia Sub County Hospital. | Improve health services and access | maternity block at Lafey | MCG/OT/23/2019-2020 | Upgrading of Lafey Hospital (KDSP) | Lafey | Lafey | 3.1508 | 41.1898 | Health Services | Health Services | Health Services | Health Services | 2026-04-20 | 2026-04-20 | 2026-04-22 | 2026-04-22 | 46774724 | 46774724 | 50000000 | GOK | N/A | Full | N/A | 46774724 | 100% | 46774724 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF OPD AT HARSHILMI IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF OPD AT HARSHILMI IN MANDERA WEST SUB-COUNTY | improving health and preventing diseases | healthy lifestyle | MCG/OT/086/18-19 | Complete ODP at Gither and Harshilmi (to re-design) | mandera west | Dandu |  | - | health services | health services | health services | health services |  |  | 4/30/2019 | 4/30/2019 | 75278449 | 75278449 | 30000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF OPD AT HARSHILMI IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF OPD AT HARSHILMI IN MANDERA WEST SUB-COUNTY | improving HEALTH SERVICES and preventing diseases | HEALTH SERVICESy lifestyle | MCG/OT/086/2018-19 | Complete ODP at Gither and Harshilmi (to re-design) | mandera west | Dandu | 3.6005 | 39.7385 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  |  | 4/16/2019 | 4/30/2020 | 75278449 | 75278449 | 30000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Opd At Maika Mari In Banisa | Proposed Construction Of Opd At Maika Mari In Banisa | to expand and improve healthcare services | Malka Mari OPD centre |  |  | Banisa | Malkamari |  |  | Health Services | Health services | Health services | Health services |  |  |  |  | 9894800 | 9894800 |  | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of Paved Parking At New County Offices In Mandera East Sub-County | Proposed Construction Of 60,000M3 Laaga Dosota Earth Pan | improveinfrustructure | Parking |  |  | Mandera Easr | Neboi | 3.9275 | 41.7936 | Public Works | Public Works | Public Works | Public Works |  |  |  |  | 95813019 | 95813019 |  | GOK | N/A | Full | N/A | 95813019 | 100% | 95813019 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Construction Of Phase Ii Of Kmtc In Mandera East Sub-County | Proposed Reticulation Of Sala Water System | Improve access to water | KMTC |  | Construction of KMTC in partnership with Kenya Medical Training College. | Mandera East | Neboi | 3.939 | 41.7892 | Health Services | Health Services | Health Services | Health Services |  |  |  |  | 78654820 | 78654820 | 60000000 | GOK | N/A | Full | N/A | 78654820 | 100% | 78654820 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF PUBLIC DIAS AT OLLA PUBLIC BARAZA PARK IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF PUBLIC DIAS AT OLLA PUBLIC BARAZA PARK IN MANDERA NORTH SUB-COUNTY | community welfare |  | MCG/OT/120/2018-2019 | construction of Baraza Park at Olla town in Guticha ward | mandera north | Guticha | 3.8967 | 40.8623 | Public Works | public works | public works | public works |  |  | 4/30/2019 | 4/30/2019 | 5000000 | 5000000 | 5000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF PUBLIC DIAS AT OLLA PUBLIC BARAZA PARK IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF PUBLIC DIAS AT OLLA PUBLIC BARAZA PARK IN MANDERA NORTH SUB-COUNTY | community welfare |  | MCG/OT/121/2018-19 | construction of Baraza Park at Olla town in Guticha ward | mandera north | Guticha | 3.8967 | 40.8623 | Roads | Roads | Roads | Roads |  |  | 4/16/2019 | 4/30/2020 | 5000000 | 5000000 | 5000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed construction of public service registry block at geneva in mandera east | Proposed construction of public service registry block at geneva in mandera east | To provide safety and proper records facility | provides good storage of files and records |  | Human Resource Registry | Mandera east | Neboi |  |  | Public service | Public service | Public service | Public service | 2017 |  |  |  | 29325146 | 29325146 | 12000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of qurahmadow dispensary block in qurahmadow in mandera north subcounty | Proposed construction of qurahmadow dispensary block in qurahmadow in mandera north subcounty | Improve Access to Primary Healthcare Services | increased immunization coverage | MCG/OT/32/2017-2018 | Construction of Dispensary at Qurahmadhow | Mandera North | Ashabito |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-03-24 | 2019-03-31 | 2019-03-31 | 7899999 | 7899999 | 6000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of Rhamu Air Strip In Mandera North Sub County(Re-Advertisement) | Proposed Construction Of Opd At Maika Mari In Banisa | impove road infrustructure | Aistrip |  |  | mandera north | Rhamu |  |  | Roads | Roads | Roads | Roads |  |  |  |  | 75420236 | 75420236 |  | GOK | N/A | Full | N/A | 75420236 | 100% | 75420236 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Construction Of Rhamu Dimtu- Argarbicha Road In Mandera North Sub-County | Proposed Construction Of Rhamu Dimtu- Argarbicha Road In Mandera North Sub-County | smooth flow of goods and services | boost trade | MCG/OT/012/2018-2019 |  | Mandera north | Rhamu dimtu |  | - | Roads | Roads | Roads | Roads |  |  | 4/30/2019 | 4/30/2019 | 49945308 | 49945308 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed construction of rhamu IDP Phase ll 25NO LOT 11 | Proposed construction of rhamu IDP Phase ll 25NO LOT 11 | roviding shelter to the poor and promoting social reintegration and self-belief | promte better neighbourhood and safety |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 18742700 | 18742700 |  | GOK | N/A | FULL | N/A | 18742700 | 100% | 18742700 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 12 | Proposed construction of rhamu IDP Phase ll 25NO LOT 12 | promoting sustainable development | Reduce crowding | MCG/OT/04/2017-2018 | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 | 2018-03-26 | 2019-03-31 | 2019-03-31 | 18483575 | 18483575 |  | GOK | N/A | FULL | N/A | 18483575 | 100% | 18483575 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 12 | Proposed construction of rhamu IDP Phase ll 25NO LOT 12 | To provide affordable housing for the vulnerable people affected by the internal conflicts | promote sustainable development |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 18701056 | 18701056 |  | GOK | N/A | FULL | N/A | 18701056 | 100% | 18701056 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 13 | Proposed construction of rhamu IDP Phase ll 25NO LOT 13 | enhancing social inclusivity and reducing inequalities within the society | enhanced the overrall well being of the beneficieries | MCG/OT/03/2017/2018 | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 | 2018-03-23 | 2019-03-31 | 2019-03-31 | 18430500 | 18430500 |  | GOK | N/A | FULL | N/A | 18430500 | 100% | 18430500 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 14 | Proposed construction of rhamu IDP Phase ll 25NO LOT 14 | To provide affordable housing for the vulnerable people affected by the internal conflicts | improve living conditions by providing shelter | MCG/0T/06/2017-2018 | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 | 2018-03-23 | 2019-03-31 | 2019-03-31 | 18464875 | 18464875 | 300000000 | GOK | N/A | FULL | N/A | 18464875 | 100% | 18464875 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 15 | Proposed construction of rhamu IDP Phase ll 25NO LOT 15 | To provide affordable housing for the vulnerable people affected by the internal conflicts | it facilitates reintegration of IDPS with other communities | MCG/OT/07/2017-2018 | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 | 2018-03-26 | 2019-03-31 | 2019-03-31 | 18435010 | 18435010 |  | GOK | N/A | FULL | N/A | 18435010 | 100% | 18435010 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 16 | Proposed construction of rhamu IDP Phase ll 25NO LOT 16 | promoting sustainable development | promote social cohesion and integrity |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 18450375 | 18450375 |  | GOK | N/A | FULL | N/A | 18450375 | 100% | 18450375 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 17 | Proposed construction of rhamu IDP Phase ll 25NO LOT 17 | enhancing social inclusivity and reducing inequalities within the society | promote sustainable development |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 18441375 | 18441375 |  | GOK | N/A | FULL | N/A | 18441375 | 100% | 18441375 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 18 | Proposed construction of rhamu IDP Phase ll 25NO LOT 18 | roviding shelter to the poor and promoting social reintegration and self-belief | enhanced the overrall well being of the beneficieries |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 18916207 | 18916207 |  | GOK | N/A | FULL | N/A | 18916207 | 100% | 18916207 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 19 | Proposed construction of rhamu IDP Phase ll 25NO LOT 19 | promoting sustainable development | promte better neighbourhood and safety |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 18519975 | 18519975 |  | GOK | N/A | FULL | N/A | 18519975 | 100% | 18519975 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 20 | Proposed construction of rhamu IDP Phase ll 25NO LOT 20 | enhancing social inclusivity and reducing inequalities within the society | it facilitates reintegration of IDPS with other communities | MCG/OT/12/2017-2018 | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 | 2018-03-21 | 2019-03-31 | 2019-03-31 | 18636879 | 18636879 |  | GOK | N/A | FULL | N/A | 18636879 | 100% | 18636879 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 21 | Proposed construction of rhamu IDP Phase ll 25NO LOT 21 | roviding shelter to the poor and promoting social reintegration and self-belief | promote social cohesion and integrity |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 18673750 | 18673750 |  | GOK | N/A | FULL | N/A | 18673750 | 100% | 18673750 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 23 | Proposed construction of rhamu IDP Phase ll 25NO LOT 23 | promoting sustainable development | it facilitates reintegration of IDPS with other communities |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 18270000 | 18270000 |  | GOK | N/A | FULL | N/A | 18270000 | 100% | 18270000 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 24 | Proposed construction of rhamu IDP Phase ll 25NO LOT 24 | enhancing social inclusivity and reducing inequalities within the society | promote social cohesion and integrity |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 18600020 | 18600020 |  | GOK | N/A | FULL | N/A | 18600020 | 100% | 18600020 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 25 | Proposed construction of rhamu IDP Phase ll 25NO LOT 25 | roviding shelter to the poor and promoting social reintegration and self-belief | promote sustainable development |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 11173671 | 11173671 |  | GOK | N/A | FULL | N/A | 11173671 | 100% | 11173671 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 26 | Proposed construction of rhamu IDP Phase ll 25NO LOT 26 | roviding shelter to the poor and promoting social reintegration and self-belief | enhanced the overrall well being of the beneficieries |  | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 |  |  |  | 11223000 | 11223000 |  | GOK | N/A | FULL | N/A | 11223000 | 100% | 11223000 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed construction of rhamu IDP Phase ll 25NO LOT 27 | Proposed construction of rhamu IDP Phase ll 25NO LOT 27 | To provide affordable housing for the vulnerable people affected by the internal conflicts | improve living conditions by providing shelter | MCG/OT/2017-2018 | IDP Housing Programs | Mandera North | RHAMU |  |  | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | SPECIAL PROGRAMME | 2017 | 2018-03-24 | 2019-03-31 | 2019-03-31 | 13705695 | 13705695 |  | GOK | N/A | FULL | N/A | 13705695 | 100% | 13705695 | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of Slaughter House In Elwark Mandera South Sub-County. | Proposed Construction Of Slaughter House In Elwark Mandera South Sub-County. | boost trade | expanded slaughter house | MCG/OT/49/2020-2021 | Expansion and reconstruction of Slaughter House in Elwak | Mandera South | elwak south | 2.8186 | 40.9349 | Trade | Trade | Trade | Trade | 4/29/2021 | 4/29/2021 | 4/30/2023 | 4/30/2023 | 104959282 | 104959282 | 15000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Construction Of Takaba- Gither Road In Mandera West Sub-County | Proposed Construction Of Takaba- Gither Road In Mandera West Sub-County | smooth flow of goods and services | boost trade | MCG/OT/013/2018-19 | Roads Maintenance Fuel Levy for 2018/2019 (Takaba-Gither, Rhamu - Malka Mari, Kutayu - Elwak, Elwak-Elgolicha, Awara-Morothiley & Guba-Choroqo ) | mandera west | takaba | 3.3553 | 40.2228 | Roads | Roads | Roads | Roads |  |  | 2019-04-01 | 7/31/2019 | 115582400 | 115582400 | 267035293 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Tarama Water Pan And Irrigation Project In Banisa Sub-County | Proposed Expansion Of Olla Heaith Centre In Mandera North Sub County. | Improve access to water | earth pan | MCG/OT/027/2019-2020 | Construction of 40,000 with Irrigation infrastructure pan at Tarama | Banisa |  |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 29031619 | 29031619 | 30000000 | GOK | N/A | Full | N/A | 29031619 | 100% | 29031619 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Construction Of Underground And Elevated Water Tank At New Government Offices. | Proposed Construction Of Underground And Elevated Water Tank At New Government Offices. | preserve water and natural resourses | water tank at new government Headquarters | MCG/OT/84/2020-2021 | Underground and elavated water tank at new Government offices. | Mandera East | NEBOI | 3.9275 | 41.7936 | Water Services | water services | water services | water services | 5/26/2021 | 5/26/2021 | 2022-05-31 | 5/31/2022 | 11951145 | 11951145 | 10000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED CONSTRUCTION OF WARD OFFICE AND RELATED WORKS AT GUBA IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WARD OFFICE AND RELATED WORKS AT GUBA IN MANDERA NORTH SUB-COUNTY | promote infrastructure development |  | MCG/OT/128/2018-2019 | Construction of Guba ward office | Mandera north | Rhamu Dimtu |  | - | Public Works | Public Works | Public Works | Public Works |  |  | 4/30/2019 | 2018-2019 | 7995000 | 7995000 | 8000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Construction Of Water Infrastructure At The New County Headquarters In Mandera East Sub County. | Proposed Construction Of Water Infrastructure At The New County Headquarters In Mandera East Sub County. | Basic needs access | water and sewerage infrastructure at the new county Headquarters |  | Provision for Construction of Water and sewerage infrastructure at the new County HQ | Mandera East | Neboi | 3.9303 | 41.8004 | Water Services | water services | water services | water services |  |  |  |  | 40000617 | 40000617 | 10000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT ALUNGU IN LAFEY SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT ALUNGU IN LAFEY SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | MCG/OT/71/2018-2019 |  | Lafey | lafey |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 9998566 | 9998566 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT FINCHARO IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT FINCHARO IN MANDERA SOUTH SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/72/2018-2019 | Piping of water from the new Fincharo Dam to the Fincharo town, Installation of genset, Gen House and Construction of 3No water troughs for livestock | mandera south | Elwak south |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 21961990 | 21961990 | 22000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT GARSE IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT GARSE IN MANDERA NORTH SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/073/2018-2019 | Construction of water Infrastructure in Garse town | Mandera north | Rhamu |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 9995029 | 9995029 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT GARSESALA IN MANDERA SOUTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT GARSESALA IN MANDERA SOUTH SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | MCG/OT/74/2018-2019 | Garse Sala Water Supply systems | Mandera south | sala |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 10101244 | 10101244 | 7000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT HAMASA IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT HAMASA IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/075/2018-19 | Water supply system at hamasa town takaba | mandera west | Takaba south |  | Hamasa | Water services | Water services | Water services | Water services |  |  | 4/16/2019 | 4/30/2020 | 10097640 | 10097640 | 8000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT KILIWEHIRI IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT KILIWEHIRI IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/076/2018/2019 | Construction of Kiliwehiri Water system | Banisa | Kiliweheri | 3.9066 | 40.0091 | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 18709801 | 18709801 | 19000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT MOROTHILE IN MANDERA NORTH SUB-COUNTY | PROPOSED CONSTRUCTION OF WATER SUPPLY SYSTEM AT MOROTHILE IN MANDERA NORTH SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | MCG/OT/77/2018-2019 |  | mandera north | Morothile |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 10692750 | 10692750 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed construction of water supply system for mandera technical training institute in mandera east | Proposed construction of water supply system for mandera technical training institute in mandera east | Giving water to the institution for various usage | enhance hygiene and clealinesss | MCG/OT/57/2017-2018 | Extension of water supply system from Neboi to Mandera TTI | Mandera east | Neboi |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-29 | 2019-03-31 | 2019-03-31 | 19985312 | 19985312 | 20000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Construction Of40,000M3 Earth Pan At Baskorme In Banisa Sub County | Proposed Construction Of 1 No Ward,Administration Block,Completion Of Theatre Works Gate House And Other Associated Works At Lafey Level Iv Hospital In Lafey Sub County. | Improve access to water | earth pan |  |  | Banisa | Banisa | 3.8867 | 40.3074 | Health Services | Health Services | Health Services | Health Services |  |  |  |  | 19991880 | 19991880 |  | GOK | N/A | Full | N/A | 19991880 | 100% | 19991880 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED CONSTRUCTION OF40,000M3 EARTH PAN AT BASKORME IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF40,000M3 EARTH PAN AT BASKORME IN BANISA SUB COUNTY | livelyhood enhancement | boast food security |  | construction of 40,000M3 earthpan at baskorme banissa subcounty | Banisa | banisa | 3.9244 | 40.6573 | Water Services | Water Services | Water Services |  | 2021 |  |  |  | 19991880 | 19991880 | 10000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED CONTRUCTION OF DEPUTY GOVERNORS RESIDENCE IN MANDERA EAST | PROPOSED CONTRUCTION OF DEPUTY GOVERNORS RESIDENCE IN MANDERA EAST | infrastructure improvement and Economic Development | service delivery | MCG/OT/142/2018-19 |  | Mandera East | Neboi | 3.9275 | 41.7936 | Roads | Roads | Roads | Roads |  |  | 4/15/2019 | 4/30/2022 | 78983884 | 78983884 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Dandu Water Reticulation Systems In Dandu. | Proposed Dandu Water Reticulation Systems In Dandu. | to ensure access to clean water | Dandu reticulated water systems | MCG/OT/35/2020-2021 | Dandu Water reticulation systems in Dandu | Mandera West | Dandu |  |  | Water Services | water services | water services | water services | 2021-12-04 | 2021-12-04 | 4/30/2022 |  | 15988676 | 15988676 | 10000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Desilting And Expansion Of 30,000M3 Of Dumayo Earth Pan In Banisa, Mandera County | Proposed Expansion And Desilting Of Qarsa Qoroma Earthpan. | Improve access to water | earth pan |  |  | Banisa | Kiliwehiri | 3.8867 | 40.3074 | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 14999800 | 14999800 |  | GOK | N/A | Full | N/A | 14999800 | 100% | 14999800 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
proposed de-silting and expansion of bachile earth pan from 20,000m3 to 50,000m3 | proposed de-silting and expansion of bachile earth pan from 20,000m3 to 50,000m3 | increase water harvestation during the raining seasons | increased the availablility of water | MCG/OT/039/2017-2018 | Expansion of the Current Bachile Dam to 50,000M3 in Mandera West | Mandera West | takaba |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-24 | 2019-03-31 | 2019-03-31 | 16886940 | 16886940 | 17000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED DESILTING AND EXPANSION OF BULLA PANGA EARTH PAN TO 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | PROPOSED DESILTING AND EXPANSION OF BULLA PANGA EARTH PAN TO 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/060/2018-19 | expansion and desilting of bulla panga earthpan in dandu ward | Mandera west | Dandu |  | Bull Panga | Water services | Water services | Water services | Water services |  |  | 4/16/2019 | 4/30/2020 | 9992955 | 9992955 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Desilting And Expansion Of Lehele Earth Pan In Kutulo Sub-County | Proposed Desilting And Expansion Of Lehele Earth Pan In Kutulo Sub-County | to nsure access to clean water | earth pan | MCG/OT/31/2020-2021 | Disilting od Lehele Earth Pan | Kutulo | Kutulo | 2.5191 | 40.5955 | Water Services | water services | water services | water services | 2021-12-04 | 2021-12-04 | 4/30/2022 | 4/30/2022 | 15003400 | 15003400 | 2000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
proposed de-silting and expansion of qarsa hama earth pan from 20,000m3 to 50,000m3 in mandera west sub-county | proposed de-silting and expansion of qarsa hama earth pan from 20,000m3 to 50,000m3 in mandera west sub-county | promoting food security and sustainable development | Long trekking for water reduced |  | Construction of 20,000m3 earthpan at Karsa Hama | Mandera west |  |  |  | Water Services | Water Services | Water Services | Water Services | 2017 |  |  |  | 14114310 | 14114310 | 10000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED DESILTING AND EXPANSION OF WACHUF EARTHPAN TO 30,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED DESILTING AND EXPANSION OF WACHUF EARTHPAN TO 30,000 CUBIC METRE IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | MCG/OT/050/2018/2019 | Disilting and Exanpansion of Wachuf Earth Pan-Banissa Ward | Banisa | Banisa |  |  | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 15100500 | 15100500 | 15000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED DESILTING AND EXPANSION OF WACHUF EARTHPAN TO 30,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED DESILTING AND EXPANSION OF WACHUF EARTHPAN TO 30,000 CUBIC METRE IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities |  | Disilting and Exanpansion of Wachuf Earth Pan-Banissa Ward | Banisa | Banisa | 3.9091 | 40.3468 | Water services | Water services | Water services | Water services |  |  | 2018-2019 | 2018-2019 | 15100500 | 15100500 | 15000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED DESILTING AND EXPANSION OF YAQILA EARTHPAN BY 20,000 CUBIC METRE IN MANDERA NORTH SUB-COUNTY | PROPOSED DESILTING AND EXPANSION OF YAQILA EARTHPAN BY 20,000 CUBIC METRE IN MANDERA NORTH SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/63/2018-19 | desilting and expansion of yaqila earthpan | Mandera north | Rhamu | 3.5036 | 40.6967 | Water services | Water services | Water services | Water services |  |  | 4/16/2019 | 4/30/2020 | 9999780 | 9999780 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Disilting And Expansion Of Idd Kinisa Earth Pan In Mandera West. | Proposed Disilting And Expansion Of Idd Kinisa Earth Pan In Mandera West. | to ensure access to clean water | desilted and expanded earthpan | MCG/OT/42/2020-2021 | Disilting and Expansion of Idd Kinisa Earth Pan | Mandera West | Gither |  |  | Water Services | water services | water services | water services |  |  |  |  | 9987190 | 9987190 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Dololo Dispensary Block In Mandera South Sub-County. | Proposed Dololo Dispensary Block In Mandera South Sub-County. | improve health services and access | Dololo dispensary |  | Construction of Dololo Dispensary | Mandera South |  | 2.8625 | 40.5012 | Health Services | Health services | Health services | Health services |  |  |  |  | 5986000 | 5986000 | 4500000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Drilling And Civil Works At Qarsa Hama In Mandera West | Proposed Drilling And Civil Works At Qarsa Hama In Mandera West | Ensure access to clean water |  | MCG/OT/017/2018-19 | Water Infrastructure in Karsa Hama (Drilling of new borehole, underground water tank, overhead tank and connection to the several water kiosk in the settlement | Mandera west | Dandu |  | Qarsa Hama | Water services | Water services | Water services | Water services |  |  | 2019-03-01 | 7/31/2019 | 27996287 | 27996287 | 25000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
proposed drilling and equiping at towfiq village in mandera north sub-county | proposed drilling and equiping at towfiq village in mandera north sub-county | providing a reliable water source during dry periods | enhances social integrations among communities | MCG/OT/54/2017-2018 | drilling and equiping of a borehole at Towfiq village in Rhamu | Mandera North | RHAMU |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-28 | 2019-03-31 | 2019-03-31 | 10088626 | 10088626 | 10111122 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Erection And Completion Of Mordern Slaughter House (Phase 2) In Mandera East Sub County | Proposed Completion Of Fm Station In Mandera East Sub-County. | improve access to services | Mandera slaughter house | MCG/OT/28/2019-2020 | Constructions of modern slaughter house in Mandera East | Mandera East | Neboi | 3.9342 | 41.8292 | Agriculture | Agriculture | Agriculture | Agriculture | 2026-04-20 | 2026-04-20 | 2026-04-22 | 2026-04-22 | 24300240 | 24300240 | 58752258 | GOK | N/A | Full | N/A | 24300240 | 100% | 24300240 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Executive Office Block At Public Works Compound In Mandera East Sub-County | Proposed Executive Office Block At Public Works Compound In Mandera East Sub-County | providing extra spaces for the executive functions | provides office spaces | MCG/OT/077/2017-2018 | Construction of office block at Works office | Mandera East | Neboi |  |  | Public Works | Public Works | Public Works | Public Works | 2017 |  |  |  | 53987058 | 53987058 | 12000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Expansion And Desilting Of Egu Furqan Earthpan In Mandera South Sub County | Proposed Expansion Of Fino Health Centre In Lafey Sub-County. | Improve access to water | earth pan |  |  | Mandera South |  |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 6394752 | 6394752 |  | GOK | N/A | Full | N/A | 6394752 | 100% | 6394752 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Expansion And Desilting Of Hardimtu Earthpan In Mandera West Sub-County. | Proposed Expansion And Desilting Of Hardimtu Earthpan In Mandera West Sub-County. | access to safe water services for domestic use | Desilted Hardimtu | MCG/OT/87/2020-2021 | Desilting of Hardimtu in Mandera west | Mandera West |  | 2.5449 | 40.799 | Water Services | water services | water services | water services | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 9998990 | 9998990 | 4140000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Expansion And Desilting Of Harshilmi Earth Pan In Mandera West Sub-County. | Proposed Expansion And Desilting Of Harshilmi Earth Pan In Mandera West Sub-County. | to nsure access to clean water | desilted and repaired inlet | MCG/OT/41/2020-2021 | Disilting and repair of inlet at Harshilmi | Mandera West |  |  |  | Water Services | water services | water services | water services | 2021-12-04 | 2021-12-04 | 4/30/2022 | 4/30/2022 | 9959208 | 9959208 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Expansion And Desilting Of Qarsa Qoroma Earthpan. | Proposed Expansion And Desilting Of Qarsa Qoroma Earthpan. | access to safe water services for domestic use | expanded and desilted Qarsa Qoroma earthpan | MCG/OT/86/2020-2021 | Expansion and Disilting of Qarsa Qoroma Earth Pan |  |  |  |  | Water Services | water services | water services | water services | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 9989650 | 9989650 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Expansion And Desilting Of Urile Earthpan In Banisa Sub County. | Proposed Expansion And Desilting Of Urile Earthpan In Banisa Sub County. | preserve water and natural resourses | expanded Urile Dam | MCG/OT/85/2020-2021 | Expansion of Urile dam | Banisa |  | 4.0412 | 40.1993 | Water Services | water services | water services | water services | 3/26/2021 | 4/29/2021 | 5/28/2022 | 5/28/2022 | 9999080 | 9999080 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Expansion Of Arabia Sub County Hospital. | Proposed Expansion Of Arabia Sub County Hospital. | Improve health services and access | expanded hospital |  | expansion of Arabia health facility | Mandera East | Arabia |  |  | Health Services | Health services | Health services | Health services |  |  |  | 0 | 9905298 | 9905298 | 5000000 | GOK | NA | 100% | 0 |  | 0% |  |  |  | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED EXPANSION OF ARDA BOJI EARTHPAN BY 60,000 CUBIC METRE IN MANDERA SOUTH SUB-COUNTY | PROPOSED EXPANSION OF ARDA BOJI EARTHPAN BY 60,000 CUBIC METRE IN MANDERA SOUTH SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/051/2018-2019 | Expansion of Arda Boji Earthpan by 60,000M3 | Mandera South | Shimpir Fatuma | 2.6853 | 40.529 | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 40004387 | 40004387 | 31000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED EXPANSION OF ARDA BOJI EARTHPAN BY 60,000 CUBIC METRE IN MANDERA SOUTH SUB-COUNTY | PROPOSED EXPANSION OF ARDA BOJI EARTHPAN BY 60,000 CUBIC METRE IN MANDERA SOUTH SUB-COUNTY | promote sustainable water management | clean water |  | Expansion of Arda Boji Earthpan by 60,000M3 | Mandera South | Shimpir Fatuma | 2.6853 | 40.529 | Water services | Water services | Water services | Water services |  |  | 2018-2019 | 2018-2019 | 40004387 | 40004387 | 31000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED EXPANSION OF DHARKEN SADEN EARTH PAN BY 15,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF DHARKEN SADEN EARTH PAN BY 15,000 CUBIC METRE IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/64/2018-2019 | Construction of 15,000M3 earth Pan at Darken Saden - Banisa sub County | Banisa | Banisa |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 9991275 | 9991275 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Expansion Of Duse Dam In Kutulo | Proposed Expansion And Desilting Of Urile Earthpan In Banisa Sub County. | Improve access to water | earth pan |  |  | Mandera South | kutulo | 2.5719 | 40.6659 | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 30976930 | 30976930 |  | GOK | N/A | Full | N/A | 30976930 | 100% | 30976930 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Expansion Of Fino Health Centre In Lafey Sub-County. | Proposed Expansion Of Fino Health Centre In Lafey Sub-County. | improve health services and access | Fino Health centre |  | expansion of Fino health facility | Lafey | Fino |  |  | Health Services | Health services | Health services | Health services |  |  |  |  | 9850039 | 9850039 | 5000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Expansion Of Guba Heaith Centre In Banisa Sub-County. | Proposed Expansion Of Guba Heaith Centre In Banisa Sub-County. | improve health services and access | Guba Health centre | MCG/OT1/02/2020-2021 | expansion of Guba health facility | Banisa | Guba | 3.9502 | 40.3331 | Health Services | Health services | Health services | Health services | 2021-11-06 | 2021-11-06 | 2022-11-06 | 2022-11-06 | 9534805 | 9534805 | 5000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED EXPANSION OF HARBUYO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | PROPOSED EXPANSION OF HARBUYO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/54/2018-2019 | Expansion of Har Buyo Dams to 30,000M3 | Mandera west | Takaba south |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 9999570 | 9999570 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED EXPANSION OF HARCHINI EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF HARCHINI EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | improve water quality and sanitation | sustainable water management practices | MCG/OT/55/2018-2019 | expansion to 30,000,000M3 and desilting of Harchini earthpan banisa subcounty | Banisa | Banisa |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 9991800 | 9991800 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED EXPANSION OF KOKOTO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | PROPOSED EXPANSION OF KOKOTO EARTHPAN BY 20,000 CUBIC METRE IN MANDERA WEST SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/057/2018-2019 | Construction of 30,000m3 earth pan at kotkoto | Mandera west | Takaba South |  | - | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 13248210 | 13248210 | 169402 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED EXPANSION OF KUKUB EARTH PAN TO 50,000 CUBIC METRES IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF KUKUB EARTH PAN TO 50,000 CUBIC METRES IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | MCG/OT/047/2018-19 | Expansion of Kukub Earthpan to 50,000M3 | Banisa | Banisa | 3.8538 | 40.2208 | Water services | Water services | Water services | Water services |  |  | 4/16/2019 |  | 17529225 | 17529225 | 17706249 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Expansion Of Olla Heaith Centre In Mandera North Sub County. | Proposed Expansion Of Olla Heaith Centre In Mandera North Sub County. | improve health services and access | Olla Health centre | MCG/OT/03/2020-2021 | expansion of Olla health facility | Mandera North |  | 3.8941 | 40.8672 | Health Services | Health services | Health services | Health services | 2021-12-06 | 2021-12-06 | 2022-12-06 | 2022-12-06 | 9888895 | 9888895 | 5000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Expansion Of Qofole 20,000M3 Earthpan In Mandera West Sub-County. | Proposed Expansion Of Qofole 20,000M3 Earthpan In Mandera West Sub-County. | preserve water and natural resourses | expanded Qofole dam | MCG/89/2020-2021 | Expansion of Qofole dam 20,000m3 | Mandera West | Lagsure |  |  | Water Services | water services | water services | water services |  |  |  |  | 9689837 | 9689837 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Expansion Of Rhamu Hospital In Mandera North Sub-County | Proposed Expansion Of Rhamu Hospital In Mandera North Sub-County | to reduce infectious diseases and improve health | Expanded Rhamu hospital | MCG/OT/62/2020-2021 | Expansion of Rhamu Hospital | Mandera North | Rhamu | 3.9337 | 41.2253 | Health Services | Health services | Health services | Health services | 4/26/2021 | 4/26/2021 | 4/30/2022 | 4/30/2022 | 73061138 | 73061138 | 30000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED EXPANSION OF WAKO DADACHA EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | PROPOSED EXPANSION OF WAKO DADACHA EARTHPAN BY 20,000 CUBIC METRE IN BANISA SUB-COUNTY | Ensure access to clean water | increase safer water access for communities | MCG/OT/067/2018-2019 | expansion of wako Dadacha Dam in Banisa by 30,000m3 | Banisa | Banisa | 3.8432 | 40.3409 | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 9686625 | 9686625 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
proposed extension of distribution main for water supply in mandera south sub - county | proposed extension of distribution main for water supply in mandera south sub - county | Animal Watering , Supplying water for livestock. | Reduces clan conflict for water | MCG/OT/50/2017-2018 | construction of 20,000m3 earth pan at Duse in Kutulo-Sub county | Mandera south | Kutulo |  |  | Water Services | Water Services | Water Services | Water Services | 2017 |  |  |  | 19703640 | 19703640 | 10000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED FENCING AND SELVING OF SALA MARKET IN LAFEY SUB-COUNTY | PROPOSED FENCING AND SELVING OF SALA MARKET IN LAFEY SUB-COUNTY | boost trade | economic development | MCG/OT/139/2018-19 |  | mandera east | lafey | 3.9312 | 41.2801 | public works | public works | public works | public works |  |  | 4/16/2019 | 4/30/2020 | 9095850 | 9095850 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Fencing Of Bp1 And Kamor Cemetery In Mandera | Proposed Fencing Of Bp1 And Kamor Cemetery In Mandera | protect amenities | Chainlink fence | MCG/OT/93/2020-2021 | Fencing Of Bp1 And Kamor Cemetery In Mandera | Mandera East | Township | 3.9162 | 41.8478 | Public Works | public service | public service | public service | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 19744700 | 19744700 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED FENCING OF HARERI HOSLE DISPENSARY, CONSTRUCTION OF NEW MATERNITY WING AND STAFF HOUSING IN MANDERA EAST SUB-COUNTY | PROPOSED FENCING OF HARERI HOSLE DISPENSARY, CONSTRUCTION OF NEW MATERNITY WING AND STAFF HOUSING IN MANDERA EAST SUB-COUNTY | improving health and preventing diseases | healthy lifestyle | MCG/OT/089/2018-2019 | Harer Hosle Dispensary fencing,adding Marternity wing, and staff Housing | Mandera East | lafey |  | - | health services | health services | health services | health services |  |  | 4/30/2019 | 4/30/2019 | 38462893 | 38462893 | 9000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED GRADING AND MURRUMING OF DAR ES SALAM - SAROHINDI ROAD MANDERA EAST | PROPOSED GRADING AND MURRUMING OF DAR ES SALAM - SAROHINDI ROAD MANDERA EAST | smooth flow of goods and services | boost trade | MCG/OT/111/2018-19 | Grading and murruming of Dar es salam - Sarohindi Road | Mandera East |  | 3.8335 | 41.5102 | Roads | Roads | Roads | Roads |  |  | 4/16/2019 | 4/30/2020 | 19829040 | 19829040 | 20000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Improvement Of Elwak Air Strip In Mandera West Sub County | Proposed Dandu Water Reticulation Systems In Dandu. | impove road infrustructure | Aistrip |  |  | Mandera South | Elwak |  |  | Roads | Roads | Roads | Roads |  |  |  |  | 22300179 | 22300179 |  | GOK | N/A | Full | N/A | 22300179 | 100% | 22300179 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Proposed Improvement Of Takaba Air Strip In Mandera West Sub County(Re-Advertisement) | Proposed Construction Of Mandera North Sub-County Headquarters Office Block At Rhamu Town In Mandera North | impove road infrustructure | Aistrip |  | Proposed Constructions of runway and fencing of Takaba Airstrip | Mandera West | Lagsure |  |  | Roads | Roads | Roads | Roads |  |  |  |  | 16539939 | 16539939 | 50000000 | GOK | N/A | Full | N/A | 16539939 | 100% | 16539939 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED KOROMEY IRRIGATION PROJECT IN MANDERA EAST SUB-COUNTY | PROPOSED KOROMEY IRRIGATION PROJECT IN MANDERA EAST SUB-COUNTY | enhancing productivity | increasing crop yields | MCG/OT/103/2018-2019 | Proposed Water supply for Koromey farms irrigation infrastructure | mandera east | mandera east | 3.8952 | 41.7879 | Agriculture | Agriculture | Agriculture | Agriculture |  |  | 4/30/2019 | 4/30/2019 | 263564200 | 263564200 | 50000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED KUTULO(MALBE) WATER PAN FOR IRRIGATION PROJECT IN KUTULO SUB-COUNTY | PROPOSED KUTULO(MALBE) WATER PAN FOR IRRIGATION PROJECT IN KUTULO SUB-COUNTY | enhancing productivity | increasing crop yields | MCG/OT/104/2018-2019 |  | mandera south | kutulo | 2.418 | 40.6742 | Water services | Water services | Water services | Water services |  |  | 4/16/2018 | 4/30/2019 | 253013296 | 253013296 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Land Registry Block At Elwak Town In Mandera South Constituency | Proposed Land Registry Block At Elwak Town In Mandera South Constituency | providing storage for land registry | facilitates well stored books and files | MCG/OT/74/2017-2018 |  | Mandera south | Elwak |  |  | Lands | Lands | Lands | Lands | 2017 | 2018-05-29 | 2019-05-31 | 2019-05-31 | 20500000 | 20500000 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Light Grading And Gravelling Of Road At Khalafow Village In Mandera West Sub-County | Proposed Light Grading And Gravelling Of Road At Khalafow Village In Mandera West Sub-County | improve quality and accessibility | Gravelled Roads at Khalafow |  | Light Grading and Gravelling of Road at Khalafow Village | Mandera west | Takaba |  |  | Roads | Roads | Roads | Roads |  |  |  |  | 79978520 | 79978520 | 39320000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED MAINTENACE AND LIGHT GRADING OF ARABIA-BAMBO 2 ROAD IN MANDERA EAST SUB-COUNTY | PROPOSED MAINTENACE AND LIGHT GRADING OF ARABIA-BAMBO 2 ROAD IN MANDERA EAST SUB-COUNTY | smooth flow of goods and services | boost trade | MCG/OT/110/2018-2019 | Arabia to bambo 2 light grading | Mandera East | Arabia | 3.5765 | 41.4813 | Roads | Roads | Roads | Roads |  |  | 4/30/2019 | 4/30/2019 | 9819632 | 9819632 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED MAINTENANCE AND GRADING OF LIBEHIA-AFGOYE ROAD IN MANDERA EAST SUB-COUNY | PROPOSED MAINTENANCE AND GRADING OF LIBEHIA-AFGOYE ROAD IN MANDERA EAST SUB-COUNY | smooth flow of goods and services | boost trade | MCG/OT/117/2018-2019 | Maintenance and grading of road (afgoye to labehia center ) | Mandera East | Libehia | 3.8293 | 41.5211 | Roads | Roads | Roads | Roads |  |  | 4/30/2019 | 4/30/2019 | 9.998,040 | 9.998,040 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED MAINTENANCE AND SPOT PATCHING ON LAFEY-KABO ROAD IN LAFEY SUB-COUNTY | PROPOSED MAINTENANCE AND SPOT PATCHING ON LAFEY-KABO ROAD IN LAFEY SUB-COUNTY | smooth flow of goods and services | boost trade | MCG/OT/116/2018-2019 | Maintainence & spot patching Lafey-Kabo Road | Lafey | lafey |  | - | Roads | Roads | Roads | Roads |  |  | 4/30/2019 | 4/30/2019 | 9.999,820.62 | 9.999,820.62 | 10000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Mandera Disability Source Centre In Mandera East County | Proposed Mandera Disability Source Centre In Mandera East County | Empowering persons with disabilities and promotig inclusive development | promote social cohesion and integrity | MCG/0T/71/2017-2018 | Persons with disabilities' resource centre | #REF! | #REF! |  |  | Social services | Social services | Social services | Social services | 2017 | 2018-05-30 | 2019-05-31 | 2019-05-31 | 24998580 | 24998580 | 12000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed mandera KMTC ( former rest house) boundary wall in mandera east | Proposed mandera KMTC ( former rest house) boundary wall in mandera east | To enhance security of the learners and the entire institution | promote tracking of new infectious disease | MCG/OT/27/2017-2018 | Proposed fencing of Mandera Rest House( Enforcement Office block) | Mandera east | Neboi |  |  | Health Services | Health Services | Health Services | Health Services | 2017 |  |  |  | 25913646 | 25913646 | 15000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
proposed Mandera nature park current mirra market boundary wall | proposed Mandera nature park current mirra market boundary wall | To prevent intruders, encroachment and enhancing security | Reduced encroachmen+F38+E38:K39+E38:M39+E38:M38 | MCG/OT/38/2017-2018 |  | Mandera east | Neboi |  |  | Trade | Trade | Trade | Trade | 2017 | 2018-03-29 | 2019-03-31 | 2019-03-31 | 15000000 | 15000000 |  | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Mandera Rehabilitation Centre in Mandera East Constituency | Proposed Mandera Rehabilitation Centre in Mandera East Constituency | providing person centered care by providing rehab interventions to each individals needs | Reduced meltal health problems |  |  | #REF! | #REF! |  |  | Social services | Social services | Social services | Social services | 2017 |  |  |  | 44582615 | 44582615 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Murraming Of Road In Takaba Town In Mandera. | Proposed Murraming Of Road In Takaba Town In Mandera. | improve quality | Murrum Roads -Takaba Town |  | Marruming of Roads in Takaba town | Mandera est | Takaba |  |  | Roads | Roads | Roads | Roads |  |  |  |  | 9812440 | 9812440 | 6750000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED MUSEUM HALL AT MANDERA EAST SUB COUNTY | PROPOSED MUSEUM HALL AT MANDERA EAST SUB COUNTY | promote heritage and culture | promote investment | MCH/OT/136/2018-2018 |  | mandera east | mandera east |  | - | Heritage and culture | Heritage and culture | Heritage and culture | Heritage and culture |  |  | 4/30/2019 | 4/30/2019 | 6000000 | 6000000 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed of Fire station in Mnadera East Sub county | Proposed of Fire station in Mnadera East Sub county | Providing quick and standby services for fire emergency | quick fire extinguish services and available personel |  | Construction of Fire station | Mandera east | Township |  |  | Public works | Public works | Public works | Public works | 2017 |  |  |  | 24359576 | 24359576 | 15000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Office Block For Ministry Health Services In Mandera East | Proposed Office Block For Ministry Health Services In Mandera East | Improve Access to Primary Healthcare Services | create employment opportunitie | MCG/OT/25/2017-2018 | Office block for Ministry of health at MCHR | Mandera east | Mandera east |  |  | Health Services | Health Services | Health Services | Health Services | 2017 | 2018-03-24 | 2019-03-31 | 2019-03-31 | 28980744 | 28980744 | 21000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Opening Up Access Road For Koromey Farms In Mandera East Sub-County. | Proposed Opening Up Access Road For Koromey Farms In Mandera East Sub-County. | to aid in smooth flow of goods and services | Koromey farms access Roads |  | Access Roads for Koromey farms | Mandera East | Township | 3.9004 | 41.7944 | Roads | Roads | Roads | Roads |  |  |  |  | 15265020 | 15265020 | 6000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Opening Up And Light Grading Of Mandera Bypass Road In Mandera East Sub County. | Proposed Opening Up And Light Grading Of Mandera Bypass Road In Mandera East Sub County. | smooth flow of goods andd services | Mandera bypass road | MCG/OT/19/2020-2021 | Opening up and light grading of Mandera bypass road | Mandera East | Township | 3.917 | 41.8287 | Roads | Roads | Roads | Roads | 2021-12-04 | 2021-12-04 | 4/30/2022 | 4/30/2022 | 99976485 | 99976485 | 9000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Opening Up Of Access Road To Kmtc And Mttc Area In Mandera East Sub-County | Proposed Opening Up Of Access Road To Kmtc And Mttc Area In Mandera East Sub-County | improve the standard and quality of roads | Access Roads KMTC and MTTC | MCG/OT/18/2020-2021 | Opening Up Access Roads to KMTC and MTTC Area | Mandera East | Neboi | 3.9361 | 41.7923 | Roads | Roads | Roads | Roads | 2021-12-04 | 2021-12-04 | 4/30/2023 | 4/30/2023 | 96682520 | 96682520 | 6300000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED PAVED PARKING AT NEW FIRE STATION IN MANDERA EAST SUB COUNTY | PROPOSED PAVED PARKING AT NEW FIRE STATION IN MANDERA EAST SUB COUNTY | improved access |  | MCG/OT/107/2018-19 | proposed paved parking at new fire station in mandera east sub county | mandera east | Neboi | 3.9343 | 41.8619 | public works | public works | public works | Road /Public Works |  |  | 4/16/2019 | 4/30/2020 | 76288200 | 76288200 | 35000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Paved Parking, Wall Finishing And Grading Of Mandera Moi Stadium In Mandera East Sub County | Proposed Opening Up And Light Grading Of Mandera Bypass Road In Mandera East Sub County. | improve service delivery | paved parking |  |  | Mandera East | Neboi | 3.9331 | 41.847 | Public Works | Public Works | Public Works | Public Works |  |  |  |  | 9700000 | 9700000 |  | GOK | N/A | Full | N/A | 9700000 | 100% | 9700000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED PAVED PARKING, WALL FINISHING AND GRADING OF MANDERA MOI STADIUM IN MANDERA EAST SUB COUNTY | PROPOSED PAVED PARKING, WALL FINISHING AND GRADING OF MANDERA MOI STADIUM IN MANDERA EAST SUB COUNTY | providing safe and covienent storage to support economic development | reduce vehicles jam and enhance economic |  | Roads and Public Works | Mandera East | Neboi |  |  | Roads and Public Works | Public Works | Public Works |  | 2021 | 2021-10-12 | 12/31/2022 | 12/31/2022 | 9700000 | 9700000 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED PAVED PARKING,DRAINAGE AND FENCING WORKS AT ELWAK SME MARKET IN MANDERA SOUTH SUB-COUNTY. | PROPOSED PAVED PARKING,DRAINAGE AND FENCING WORKS AT ELWAK SME MARKET IN MANDERA SOUTH SUB-COUNTY. | infrastructure improvement |  | MCG/OT/036/2018-19 | proposed paved parking and drainage system at Elwak SME market Park | mandera south | Elwak south |  | Elwak | public works | public works | public works | public works |  |  | 2019-11-02 | 2/28/2021 | 167355708 | 167355708 | 50000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
PROPOSED PROVISION OF ASSET TAGGING SOLUTIONS TO MANDERA COUNTY GOVERNMENT | PROPOSED PROVISION OF ASSET TAGGING SOLUTIONS TO MANDERA COUNTY GOVERNMENT | proper management of assets/tracking of assets | reduced theft | MCG/OT/RFP/01/18-19 |  | Mandera east |  |  | mandera | financial services | financial services | financial services | financial services |  |  | 4/16/2019 | 4/30/2020 | 11100000 | 11100000 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Re-Channeling Of Lag Warera Seasonal River Gabions In Takaba In Mandera West Sub-County. | Proposed Light Grading And Gravelling Of Road At Khalafow Village In Mandera West Sub-County | improve quality maintenance | Gabions Takaba Town |  | re-channelling of Lag Warera seasonal River, Gabions in Takaba | Mandera west | Takaba |  |  | Roads | Roads | Roads | Roads |  |  |  |  | 19994920 | 19994920 | 15000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Rehabilitation And Expansion Of Sake Earth Pan From 25,000m3 To 60,000m3 In Mandera West Sub-County | Proposed Rehabilitation And Expansion Of Sake Earth Pan From 25,000m3 To 60,000m3 In Mandera West Sub-County | Improving Livelihoods, by addressing water scarcity challenges. | boost business locally |  | Expansion of the current Sake dam to 60,000M3 (mandera West) | Mandera West | Takaba |  |  | Water Services | Water Services | Water Services | Water Services | 2017 |  |  |  | 16755990 | 16755990 | 15000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED REHABILITATION OF KHALALIO WATER SUPPLY IN MANDERA EAST SUB-COUNTY | PROPOSED REHABILITATION OF KHALALIO WATER SUPPLY IN MANDERA EAST SUB-COUNTY | promote sustainable water management | clean water | MCG/OT/078/2018-2019 |  | Mandera East | khalalio | 3.9655 | 41.6173 | Water services | Water services | Water services | Water services |  |  | 4/30/2019 | 4/30/2019 | 6241484 | 6241484 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed rehabilitation of qolfole earth pan from 30,000m3 to 60,000m3 in mandera west | Proposed rehabilitation of qolfole earth pan from 30,000m3 to 60,000m3 in mandera west | providing a reliable water source during dry periods | increased the availablility of water | MCG/OT/45/2017-2018 | Expansion of the current Qofole Dam to 60,000M3 (mandera West) | Mandera west |  |  |  | Water Services | Water Services | Water Services | Water Services | 2017 | 2018-03-24 | 2019-03-31 | 2019-03-31 | 16542960 | 16542960 | 15000000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED RENOCONSTRUCTION OF 60,000M3 ALUNG EARTH PAN IN LAFEY SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 ALUNG EARTH PAN IN LAFEY SUB-COUNTY | Agricultural Activities | Increased availability of water for domestic and livestock use during dry seasons. |  | Water Services | Lafey | Alungu |  |  | Water Services | Water Services | Water Services |  | 2022 | 2022-05-09 | 9/30/2023 | 9/30/2023 | 32147000 | 32147000 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED RENOCONSTRUCTION OF 60,000M3 BAAYE EARTH PAN IN BANISA SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 BAAYE EARTH PAN IN BANISA SUB-COUNTY | Water Harvesting and Storage | Increased availability of water for domestic and livestock use during dry seasons. |  | Water Services | Banisa | Banisa |  |  | Water Services | Water Services | Water Services |  | 2022 | 2022-05-09 | 9/30/2023 | 9/30/2023 | 31075000 | 31075000 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED RENOCONSTRUCTION OF 60,000M3 CHAME EARTH PAN | PROPOSED RENOCONSTRUCTION OF 60,000M3 CHAME EARTH PAN | Climate Resilience | Enhanced community resilience to droughts and climate variability. |  | Water Services | Banisa | Banisa |  |  | Water Services | Water Services | Water Services |  | 2022 | 2022-05-09 | 9/30/2023 | 9/30/2023 | 31877040 | 31877040 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED RENOCONSTRUCTION OF 60,000M3 FINO EARTH PAN IN LAFEY SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 FINO EARTH PAN IN LAFEY SUB-COUNTY |  | Enhanced community resilience to droughts and climate variability. |  | Water Services | Lafey | Fino |  |  | Water Services | Water Services | Water Services |  | 2022 | 2022-05-09 | 9/30/2023 | 9/30/2023 | 31273000 | 31273000 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED RENOCONSTRUCTION OF 60,000M3 SILKIN EARTH PAN IN BANISA SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 SILKIN EARTH PAN IN BANISA SUB-COUNTY | Long-Term Water Security | Increased availability of water for domestic and livestock use during dry seasons. |  | Water Services | Banisa | Banisa |  |  | Water Services | Water Services | Water Services |  | 2022 | 2022-05-09 | 9/30/2023 | 9/30/2023 | 31277000 | 31277000 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED RENOCONSTRUCTION OF 60,000M3 SUKELA DERA EARTH PAN IN BANISA SUB-COUNTY | PROPOSED RENOCONSTRUCTION OF 60,000M3 SUKELA DERA EARTH PAN IN BANISA SUB-COUNTY | Drought Mitigation |  |  | Water Services | Banisa | Banisa |  |  | Water Services | Water Services | Water Services |  | 2022 | 2022-05-09 | 9/30/2023 | 9/30/2023 | 31137000 | 31137000 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
PROPOSED RENOVATION AND ALTERATION WORKS OF DETAL UNIT BLOCK IN MANDERA LEVEL IV HOSPITAL MANDERA SUBCOUNTY | PROPOSED RENOVATION AND ALTERATION WORKS OF DETAL UNIT BLOCK IN MANDERA LEVEL IV HOSPITAL MANDERA SUBCOUNTY | Ensure Compliance with Regulatory Standards | Improve Patient Comfort and Staff Working Conditions |  | Health | Mandera West | Neboi | 3.9423 | 41.861 | Health Services | Health Services | Health Services |  | 2022 | 2022-05-09 | 9/30/2023 | 9/30/2023 | 9997339.85 | 9997339.85 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Renovation Of Theatre, Construction Of Admin Block, Staff House Covered Walkway, Cabro And Main Gate At Banisa Hospital | Proposed Construction Of 20,000M3 Ameyi Earth Pan | improve access to health services | Theatre, Admin block,etc |  | Under Provison for Proposed fencing and Cabro work for Elwak sub-county headquarter | Banisa | Banisa | 3.94 | 40.334 | Health Services | Health Services | Health Services | Health Services |  |  |  |  | 59336906 | 59336906 | 18579050 | GOK | N/A | Full | N/A | 59336906 | 100% | 59336906 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED RENOVATION WORKS AT ESP RHAMU MARKET STALLS, KITCHEN AND TOILET BLOCK IN MANDERA NORTH SUB-COUNTY. | PROPOSED RENOVATION WORKS AT ESP RHAMU MARKET STALLS, KITCHEN AND TOILET BLOCK IN MANDERA NORTH SUB-COUNTY. | boost trade | economic development | MCG/OT/134/2018/19 | Proposed Construction of Kutulo Market | mandera north | Rhamu | 3.9375 | 41.2203 | public works | public works | public works | public works |  |  | 4/16/2019 | 4/30/2020 | 6005951 | 6005951 | 2566523 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Repair And Maintenance Of Accident And Emergency Centres And Maternity Centres At Mcrh And Elwak Referral Hospitals In Mandera County | Proposed Construction Of Chain Link Fencing At Government Institution. | improve access to health services | Accident and Emergency | MCG/OT/MOH/05/2019-2020 | adjustment to MCRH Accident and Emergency ICU and Ward area as well as replacement of tiles with Terrazo | Mandera East | Neboi | 3.9425 | 41.8612 | Health Services | Health Services | Health Services | Health Services | 2026-04-19 | 2026-04-19 | 2026-08-20 | 2026-08-20 | 31793802 | 31793802 | 37000000 | GOK | N/A | Full | N/A | 31793802 | 100% | 31793802 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED REPAIR AND MAINTENANCE OF ACCIDENT AND EMERGENCY CENTRES AND MATERNITY CENTRES AT MCRH AND ELWAK REFERRAL HOSPITALS IN MANDERA COUNTY | PROPOSED REPAIR AND MAINTENANCE OF ACCIDENT AND EMERGENCY CENTRES AND MATERNITY CENTRES AT MCRH AND ELWAK REFERRAL HOSPITALS IN MANDERA COUNTY | preventing harm and maintaining safe environment for both patient and hospital staff | maximizing longativity and reducing unplanned cost |  | Repair and maintenance of A and E Mandera | Mandera East & South | mandera East &south |  |  | Health Services | Health Services | Health Services |  | 2021 | 2021-10-12 | 12/31/2022 | 12/31/2022 | 31793802 | 31793802 | 14000000 | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Proposed Reticulation Of Sala Water System | Proposed Reticulation Of Sala Water System | to nsure access to clean water | Reticulated water systems |  | Retculation of Sala Water Sytem | Lafey | Sala | 3.9306 | 41.2811 | Water Services | water services | water services | water services |  |  |  |  | 9982350 | 9982350 | 5000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Routine Maintenance of Warqadud Qoqaqaye Road | Proposed Routine Maintenance of Warqadud Qoqaqaye Road | For easy movement of the residents | Reduced long travelling hours |  | Qoqaye - Wargadud Road | Mandera south | Elwak |  |  | Roads | Roads | Roads | Roads | 2017 |  |  |  | 19930499 | 19930499 | 2590000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Proposed Sala Farms Agricultural Improvement Project At Sala In Lafey Sub-County In Mandera | Proposed Sala Farms Agricultural Improvement Project At Sala In Lafey Sub-County In Mandera | to increase agricultural produce | agricultural improvements |  | Sala Farms Agricultural improvement | Lafey | Sala | 3.9326 | 41.2737 | Agriculture | Agriculture | Agriculture | Agriculture |  |  |  |  | 16997712 | 16997712 | 12000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
PROPOSED SOLAR STREET LIGHTING AT KUTULO TOWN | PROPOSED SOLAR STREET LIGHTING AT KUTULO TOWN | improve water quality and sanitation | sustainable water management practices | MCG/OT/040/18-19 | Solar street light (Kutulo) | Mandera south | Kutulo | 2.4447 | 40.6504 | Energy | Energy | Energy | Energy services |  |  | 4/16/2019 | 4/16/2019 | 44541689 | 44541689 | 37000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Takaba Water Supply In Mandera West Sub-County | Proposed Takaba Water Supply In Mandera West Sub-County | providing tap water to each households | provides treated water to households |  |  | Mandera West | Takaba |  |  | Water Services | Water Services | Water Services | Water Services | 2017 |  |  |  | Cancelled | Cancelled |  | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
PROPOSED UPGRADE OF HARSHILMI PRIMARY SCHOOL IN MANDERA WEST SUB COUNTY | PROPOSED UPGRADE OF HARSHILMI PRIMARY SCHOOL IN MANDERA WEST SUB COUNTY | promote quality education | human resources development | MCG/OT/131/2018-2019 |  | mandera west | Dandu | 3.6002 | 39.7415 | Education | Education | Education | Education |  |  | 4/30/2019 | 4/30/2019 | 48758616 | 48758616 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Proposed Upgrading Of Malka Punda Road To Bitumen Standard In Mandera East Sub-County. | Proposed Upgrading Of Malka Punda Road To Bitumen Standard In Mandera East Sub-County. | improve the standard and quality of roads | Tarmacked road and parking |  | Low Volume seal tarmac road to Malka Punda and Parking at River Access Point (KUSP) | Mandera East | Neboi | 3.9416 | 41.8529 | Roads | Roads | Roads | Roads |  |  |  |  | 169239439 | 169239439 | 102000000 | GOK | NA | 100% | [6 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
Proposed Water Supply For Koromey Farms Irrigation Infrastructure | Proposed Construction Of Bur John -Malka Mari Road In Banisa Sub-County. | improve food production | water infrustructure |  | Proposed Water supply for Koromey farms irrigation infrastructure | Mandera East | Township | 3.8952 | 41.7879 | Roads | Roads | Roads | Roads |  |  |  |  | 263364200 | 263364200 | 128000000 | GOK | N/A | Full | N/A | 263364200 | 100% | 263364200 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Purchase of motor vehicle | Purchase of motor vehicle | To comply with laws, risk managements and financial protections | enhanced well maintained vehicles in the county |  | Purchase of motor Vehicle | #REF! | #REF! |  |  | Public service | Public service | Public service | Public service | 2017 |  |  |  | 10700000 | 10700000 | 18670831 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Renovation and alteration works, cabro works and external works at Ministry of Finance offices in Mandera East | Renovation and alteration works, cabro works and external works at Ministry of Finance offices in Mandera East | improve service delivery | Cabro at Finance offices | MCG/OT/2019-2020 |  | Mandera East | Neboi |  |  | Financial Services | Financial Services | Financial Services | Financial Services | 2026-04-20 | 2026-04-20 | 2026-04-21 | 2026-04-21 | 19746216 | 19746216 |  | GOK | N/A | Full | N/A | 19746216 | 100% | 19746216 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
supply and delivery and installation of 40No solar street light 60w in Darwed | supply and delivery and installation of 40No solar street light 60w in Darwed | improve access to services | solar street lights | MCG/OT/22/2019-2020 |  | Mandera | Lagsure |  |  | Water Services | Water Services | Water Services | Water Services | [8 empty] | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Supply and Delivery installation testing and commissioning of oxygen plant in at Elwak Refferral Hospital | Supply and Delivery installation testing and commissioning of oxygen plant in at Elwak Refferral Hospital | provision of emergency services by providing suffient oxygen in the hospital | provides available oxygen supply |  | Oxygen plant at Elwak | Mandera south | Elwak |  |  | Health Services | Health Services | Health Services | Health Services | 2017 |  |  |  | 24269470 | 24269470 | 8650000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply and Delivery of 45NO Laptop to Mandera County Governent | Supply and Delivery of 45NO Laptop to Mandera County Governent | To be used for the county activities | Improved efficiecy and time management | MCG/OT/088/2017-2018 |  | Mandera East | Neboi |  |  | Financial Services | Financial Services | Financial Services | Financial Services | 2017 | 2018-07-11 | 2018-12-31 | 2018-12-31 | 5499000 | 5499000 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply And Delivery Of Computers And Accessories To Mandera County | Supply And Delivery Of Computers And Accessories To Mandera County | ensure efficient and effective service delivery | qualitycontrol | MCG/OT/021/2018-2019 |  | mandera east | mandera east |  | - | ICT | ICT | ICT | ICT |  |  | 4/30/2019 | 4/30/2019 | 19983726 | 19983726 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Supply and Delivery of Enforcement Equipment | Supply and Delivery of Enforcement Equipment | helps enforcements officers to enforce county laws | Helps enforcement officers to performed their duties | MCG/OT/82/2017-2018 | enforcement band equipment | Mandera East | Neboi |  |  | Devolved Unit | Devolved Unit | Devolved Unit | Devolved Unit | 2017 | 2018-06-20 | 2019-12-31 | 2019-12-31 | 22809776 | 22809776 | 2458347 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply and Delivery of Funiture for ECD Centres in Banisa and Lafey Sub- County | Supply and Delivery of Funiture for ECD Centres in Banisa and Lafey Sub- County | Equiping ECD centres for learning puporses | Facilitates availability of learning equipment | MCG/OT/87/2017-2018 | Operationalization of 13 Wards Offices (Furnitures and Solar) | Banisa and Lafey | Banisa`/ Lafey |  |  | Education | Education | Education | Education | 2017 |  |  |  | 24997140 | 24997140 | 9000000 | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply And Delivery Of Ict Equipment And Softwares For Public Works | Proposed Opening Up Access Road For Koromey Farms In Mandera East Sub-County. | improve internet connectivity | Softwares and Equipment |  |  | Mandera East | Neboi |  |  | ICT | ICT | ICT | ICT |  |  |  |  | 10200025 | 10200025 |  | GOK | N/A | Full | N/A | 10200025 | 100% | 10200025 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
SUPPLY AND DELIVERY OF ICT EQUIPMENT AND SOFTWARES FOR PUBLIC WORKS | SUPPLY AND DELIVERY OF ICT EQUIPMENT AND SOFTWARES FOR PUBLIC WORKS | improve office comunication and data management | boast efficiency and productivity |  | Public Works | Mandera East | Township |  |  | Public Works | Public Works | Public Works |  | 2021 | 2021-08-12 | 5/31/2022 | 5/31/2022 | 10200025 | 10200025 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | 100% | NA | NA | NA | NA | NA | NO | Compete | Implementing early warning system and developing emergency response plan | Yes | N/A | YES | N/A | YES | N/A
Supply And Delivery Of Office Furniture For Mandera County Lot1 | Supply And Delivery Of Office Furniture For Mandera County Lot1 | ensure service delivery | effective service delivery | MCG/OT/020/2018-2019 |  | mandera east | mandera east |  | - | financial services | financial services | financial services | financial services |  |  | 4/30/2019 | 4/30/2019 | 32006848 | 32006848 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Supply And Delivery Of Office Furniture For Mandera County Lot2 | Supply And Delivery Of Office Furniture For Mandera County Lot2 | ensure service delivery | effective service delivery | MCG/0T/020/2018-2019 |  | mandera east | mandera east |  | - | financial services | financial services | financial services | financial services |  |  | 4/30/2019 | 4/30/2019 | 14853800 | 14853800 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Supply Delivery Installation Commissioning Of 115kva Generating Set For Kutulo Level 4 Hospital | Supply Delivery Installation Commissioning Of 115kva Generating Set For Kutulo Level 4 Hospital | improving health and preventing diseases | healthy lifestyle | MCG/OT/26/2018-2019 |  | mandera south | Kutulo | 2.4455 | 40.6516 | health services | health services | health services | health services |  |  | 4/30/2019 | 4/30/2019 | 9860000 | 9860000 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Supply, Delivery And Installation Of Medical Equipment To Accident And Imergency Unit At Mandera County Refferal And Elwak Hospital | Supply, Delivery And Installation Of Medical Equipment To Accident And Imergency Unit At Mandera County Refferal And Elwak Hospital | improving HEALTH SERVICES and preventing diseases | HEALTH SERVICESy lifestyle | MCG/OT/09/2018-19 | procurement/Equipment Leasing (A $ E and Maternity at Elwak and MCRH) | mandera south,Mandera east | Elwak SOUTH | 3.9424 | 41.861 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  |  | 2018-2019 | 2018-2019 | 74008680 | 74008680 | 75000000 | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Supply, Delivery installation of solar streets lights in Morrothile Town in Mandera North Sub-county | Supply, Delivery installation of solar streets lights in Morrothile Town in Mandera North Sub-county | enhance security and ease movement during the night | Promote security during the night | MCG/OT/79/2017-2018 |  | Mandera North | Marothiley |  |  | Energy | Energy | Energy | Energy | 2017 | 2018-06-18 | 2019-06-30 | 2019-06-30 | 19781097 | 19781097 |  | GOK | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply, Delivery installation testing and commissioning of oxygen plant in at Mandera Refferral Hospital | Supply, Delivery installation testing and commissioning of oxygen plant in at Mandera Refferral Hospital | ensuring consistent supply of oxygen in the hospital | Reduced demands for oxygen from neighbouring counties |  | Oxygen at Mandera County Referral Hospitak | Mandera east | Neboi |  |  | Health Services | Health Services | Health Services | Health Services | 2017 |  |  |  | 23995000 | 23995000 | 8650000 | Gok | N/A | FULL | N/A |  |  |  | N/A | - | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | complete | N/A | Yes | Implementing early warning systems,incorporating climate resilient design,developing emergency response plan,promoting climate smart agriculcure and enhancing community resilience has been developed to reduce the risk of demages | YES | Environmental impact assessment,social impact assessment, occupational health and safety plan,gender action, stakeholders engagement and monitoring evaluation has been taken for effective metigation strategies | YES | Risk assesment, Contingency planning,recource allocations and financial planning | Complete
Supply,Delivery,Installation And Commissioning Of oxygen Plant For Mandera West,Kutulo And Mandera North Sub Counties And Supply And Delivery Of Medical Equipments. | Supply,Delivery,Installation And Commissioning Of oxygen Plant For Mandera West,Kutulo And Mandera North Sub Counties And Supply And Delivery Of Medical Equipments. | improve health services and access | oxygen plant and medical eguipments | MCG/OT/97/2020-2021 | supply, Delivery. Installation and Commission of oxygen plant and medical eguipments in mandera west,Kutulo and Mandera south | Mandera West |  |  |  | Health Services | Health services | Health services | Health services | 5/26/2021 | 5/26/2021 | 5/31/2022 | 5/31/2022 | 119949404 | 119949404 |  | GOK | NA | 100% | 0 | [5 empty] | Completed | NA | NA | NA | NA | NA | NA | NO |  | NA | Yes | N/A | YES | N/A | YES | N/A | Completed
TENDER FOR SUPPLY AND DELIVERY OF ECDE DESKS TO ALL SCHOOLS IN SHIMBIR FATUMA WARD IN MANDERA SOUTH SUB-COUNTY | TENDER FOR SUPPLY AND DELIVERY OF ECDE DESKS TO ALL SCHOOLS IN SHIMBIR FATUMA WARD IN MANDERA SOUTH SUB-COUNTY | promote quality education | human resources development | MCG/OT/101/2018-2019 |  | mandera south | Shimpir Fatuma | 3.1912 | 40.4221 | Education | Education | Education | Education |  |  | 4/30/2019 | 4/30/2019 | 9938880 | 9938880 |  | GOK | N/A | [7 empty] | completed | N/A | N/A | N/A | N/A | N/A | N/A | NO |  | N/A | Yes | N/A | YES | N/A | YES | N/A
Upgrading of Elben Ashabito road to gravel standard | Upgrading of Elben Ashabito road to gravel standard | improved road network | road network | MCG/OT/RMLF/06/2019-2020 |  | Mandera North | Ashabito |  |  | Roads | Roads | Roads | Roads |  |  |  |  | 29907900 |  |  |  | N/A | Full | N/A |  |  |  | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
Water supply system for Bulla Afya -Elwak | Water supply system for Bulla Afya -Elwak | improved water access | water infrustructure | MCG/OT/38/19/20 |  | Elwak |  |  |  | Water Services | Water Services | Water Services | Water Services |  |  |  |  | 20000000 | 20000000 |  |  | N/A | Full | N/A | 20000000 | 100% | 20000000 | N/A | - | Complete | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | Yes | N/A | YES | N/A | YES | N/A | complete
PROPOSED COMPLETION AND UPGRADING OF BANISA LEVEL IV HOSPITAL IN BANISA SUB COUNTY | PROPOSED COMPLETION AND UPGRADING OF BANISA LEVEL IV HOSPITAL IN BANISA SUB COUNTY | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/02/2023-2024 | Proposed Upgrading and Improvement of Level 4 Hospitals | BANISA | BANISA | 3.9403 | 40.3442 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 138214663 | 138214663 | 45000000 | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED DESILTING AND EXPANSION OF 60,000M3 HARDAWA EARTH PAN IN BANISA SUB COUNTY AT HARDAWA | PROPOSED DESILTING AND EXPANSION OF 60,000M3 HARDAWA EARTH PAN IN BANISA SUB COUNTY AT HARDAWA | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/03/2023-2024 |  | BANISA | BANISA | 4.2357 | 40.6946 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 31003056 | 31003056 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 60,000M3 BARWAQO EARTHPAN IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF 60,000M3 BARWAQO EARTHPAN IN BANISA SUB COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/04/2023-2024 |  | BANISA | BANISA | 3.9499 | 40.3457 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 30671571 | 30671571 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
SUPPLY, DELIVERY AND INSTALLATION AND COMMISSIONING OF ABEM TERRAMETER LS2 ADVANCED 4/82 AND ACCESSORIES | SUPPLY, DELIVERY AND INSTALLATION AND COMMISSIONING OF ABEM TERRAMETER LS2 ADVANCED 4/82 AND ACCESSORIES | To ehance reliable identification of ground water resources | Provides reliable, safe, and adequate clean water | MCG/OT/05/2023-2024 | Purchase of hight tech survey equipment and design software | MANDERA EAST | Township |  |  | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 26809625 | 26809625 | 15000000 | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONTSRUCTION OF 100,000M3 DADACHI GABABA EARTHPAN IN BANISA SUB COUNTY | PROPOSED CONTSRUCTION OF 100,000M3 DADACHI GABABA EARTHPAN IN BANISA SUB COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/06/2023-2024 |  | BANISA | BANISA |  |  | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 74976231 | 74976231 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 20,000M3 HAR DIMU EARTH PAN IN KUTULO SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000M3 HAR DIMU EARTH PAN IN KUTULO SUB-COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/08/2023-2024 |  | KUTULO | KUTULO | 2.5449 | 40.799 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 9928150 | 9928150 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 30,000M3 EARTH PANS AT AMASA IN MANDERA WEST | PROPOSED CONSTRUCTION OF 30,000M3 EARTH PANS AT AMASA IN MANDERA WEST | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/09/2023-2024 |  | MANDERA WEST | TAKABA |  |  | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 14950792 | 14950792 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED DESILTING AND EXPANSION OF BAMBO EARTH PAN BY 30,000M3 IN LAFEY SUB COUNTY | PROPOSED DESILTING AND EXPANSION OF BAMBO EARTH PAN BY 30,000M3 IN LAFEY SUB COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/010/2023-2024 |  | LAFEY | Waranqara | 3.5257 | 40.9754 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 14725211 | 14725211 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT IRES SUKI NI MANDERA SOUTH | PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT IRES SUKI NI MANDERA SOUTH | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/011/2023-2024 |  | MANDERA SOUTH | Wargudud | 2.9652 | 40.9098 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 14542500 | 14542500 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT MIKOREB IN MANDERA WEST | PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT MIKOREB IN MANDERA WEST | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/012/2023-2024 |  | MANDERA WEST |  |  |  | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 15104445 | 15104445 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT SARMAN IN MANDERA NORTH SUB COUNTY | PROPOSED CONSTRUCTION OF 30,000M3 EARTH PAN AT SARMAN IN MANDERA NORTH SUB COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/013/2023-2024 |  | MANDERA NORTH | GUBA | 2.5303 | 39.9604 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 14132520 | 14132520 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 60,000M3 BURDURAS GOBOGALA EARTH PAN IN MANDERA WEST SUB- COUNTY AT BURDURAS CENTER | PROPOSED CONSTRUCTION OF 60,000M3 BURDURAS GOBOGALA EARTH PAN IN MANDERA WEST SUB- COUNTY AT BURDURAS CENTER | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/014/2023-2024 |  | MANDERA WEST | Gither | 3.844 | 39.8823 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 38382120 | 38382120 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED AUGMENTATION AND UPGRADING OF BANISA WATER SUPPLY AT BANISA TOWN IN BANISA SUB COUNTY | PROPOSED AUGMENTATION AND UPGRADING OF BANISA WATER SUPPLY AT BANISA TOWN IN BANISA SUB COUNTY | To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | MCG/OT/015/2023-2024 | Construction of Proposed Water Supply Projects | BANISA | Banisa | 3.9434 | 40.3462 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 220434636 | 220434636 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED AUGMENTATION AND UPGRADING OF ASHABITO WATER SUPPLY PROJECT PHASE 1 AT ASHABITO | PROPOSED AUGMENTATION AND UPGRADING OF ASHABITO WATER SUPPLY PROJECT PHASE 1 AT ASHABITO | To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | MCG/OT/016/2023-2024 | Construction of Proposed Water Supply Projects | ASHABITO | Ashabito | 3.5524 | 40.8705 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 81459147 | 81459147 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED AUGMENTATION AND UPGRADING OF KHALALIO WATER SUPPLY PROJECT AT KHALALIO TOWN IN MANDERA EAST SUB COUNTY | PROPOSED AUGMENTATION AND UPGRADING OF KHALALIO WATER SUPPLY PROJECT AT KHALALIO TOWN IN MANDERA EAST SUB COUNTY | To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | MCG/OT/017/2023-2024 | Construction of Proposed Water Supply Projects | MANDERA EAST | Khalalio | 3.9633 | 41.6186 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 66227207 | 66227207 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED AUGMENTATION AND UPGRADING OF LAFEY WATER SUPPLY PROJECT AT LAFEY TOWN IN LAFEY SUB COUNTY. | PROPOSED AUGMENTATION AND UPGRADING OF LAFEY WATER SUPPLY PROJECT AT LAFEY TOWN IN LAFEY SUB COUNTY. | To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | MCG/OT/018/2023-2024 | Construction of Proposed Water Supply Projects | LAFEY | Lafey | 3.1541 | 41.1845 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 128388015 | 128388015 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF DANDU WATER SUPPLY PROJECT AT DANDU TOWN IN DANDU SUB COUNTY | PROPOSED CONSTRUCTION OF DANDU WATER SUPPLY PROJECT AT DANDU TOWN IN DANDU SUB COUNTY | To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | MCG/OT/019/2023-2024 | Construction of Proposed Water Supply Projects | DANDU | Dandu | 3.4249 | 39.8775 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 117910821 | 117910821 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED AUGMENTATION AND UPGRADING OF RHAMU WATER SUPPLY PROJECT (PHASE 1) IN MANDERA NORTH SUB COUNTY | PROPOSED AUGMENTATION AND UPGRADING OF RHAMU WATER SUPPLY PROJECT (PHASE 1) IN MANDERA NORTH SUB COUNTY | To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | MCG/OT/020/2023-2024 | Construction of Proposed Water Supply Projects | MANDERA NORTH | RHAMU | 3.9341 | 41.2161 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 208818953 | 208818953 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED FENCING OF GITHER EARTH PAN IN MANDERA WEST SUB COUNTY | PROPOSED FENCING OF GITHER EARTH PAN IN MANDERA WEST SUB COUNTY | To protect the earthpan | Provides reliable, safe, and adequate clean water | MCG/OT/021/2023-2024 |  | MANDERA WEST | Gither | 3.6787 | 39.9214 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 9954700 | 9954700 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF GESREBKI DISPENSARY IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF GESREBKI DISPENSARY IN BANISA SUB COUNTY | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/022/2023-2024 |  | BANISA | KILIWEHERI | 4.0029 | 40.2308 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 19924020 | 19924020 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED FACILITY IMPROVEMENT AT ELWAK HOSPITAL IN MANDERA SOUTH SUB COUNTY | PROPOSED FACILITY IMPROVEMENT AT ELWAK HOSPITAL IN MANDERA SOUTH SUB COUNTY | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/023/2023-2024 | Operationalization and Improvement of all level 4 subcounty hospitals | MANDERA NORTH | ELWAK | 2.8105 | 40.9344 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 42976100 | 42976100 | 70000000 | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPSED UPGRADING RHAMU HOSPITAL IN MANDERA NORTH SUB COUNTY | PROPSED UPGRADING RHAMU HOSPITAL IN MANDERA NORTH SUB COUNTY | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/024/2023-2024 | Operationalization and Improvement of all level 4 subcounty hospitals | MANDERA SOUTH | RHAMU | 3.9338 | 41.2254 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 75671221 | 75671221 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED UPGRADING OF LAFEY HOSPITAL IN LAFEY SUB COUNTY | PROPOSED UPGRADING OF LAFEY HOSPITAL IN LAFEY SUB COUNTY | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/025/2023-2024 | Operationalization and Improvement of all level 4 subcounty hospitals | LAFEY | LAFEY | 3.1514 | 41.1898 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 68251897 | 68251897 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED UPGRADING OF KUTULO HOSPITAL IN KUTULO SUB COUNTY | PROPOSED UPGRADING OF KUTULO HOSPITAL IN KUTULO SUB COUNTY | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/026/2023-2024 | Operationalization and Improvement of all level 4 subcounty hospitals | KUTULO | KUTULO | 2.4448 | 40.6514 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 73810730 | 73810730 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED RENOVATION AND ALTERATION WORKS TO SPECIALIST CLINICS AT MCRH IN MANDERA EAST | PROPOSED RENOVATION AND ALTERATION WORKS TO SPECIALIST CLINICS AT MCRH IN MANDERA EAST | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/027/2023-2024 |  | MANDERA EAST | Neboi | 3.9414 | 41.8612 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 7799156 | 7799156 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF RENAL UNITS ATMANDERA COUNTY REFERRAL HOSPITAL IN MANDERA EAST | PROPOSED CONSTRUCTION OF RENAL UNITS ATMANDERA COUNTY REFERRAL HOSPITAL IN MANDERA EAST | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/028/2023-2024 | Proposed Construction Of Renal Units at Mandera County Referral Hospital In Mandera East | MANDERA EAST | Neboi | 3.9414 | 41.8612 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 12416812 | 12416812 | 5000000 | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF RENAL UNITS AT ELWAK SUB COUNTY HOSPITAL IN MANDERA SOUTH | PROPOSED CONSTRUCTION OF RENAL UNITS AT ELWAK SUB COUNTY HOSPITAL IN MANDERA SOUTH | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/029/2023-2024 | Proposed Construction Of Renal Units at Elwak Sub County Hospital In Mandera South | MANDERA SOUTH | ELWAK | 2.8105 | 40.9344 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 12416812 | 12416812 | 5000000 | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
SUPPLY AND DELIVERY OF DENTAL EQUIPMENT FOR MANDERA COUNTY GOVERNMENT | SUPPLY AND DELIVERY OF DENTAL EQUIPMENT FOR MANDERA COUNTY GOVERNMENT | Improve the quality, accessibility, and efficiency of healthcare services | Providing comprehensive and efficient healthcare services to the community | MCG/OT/031/2023-2024 | Procurement of Dental/ ENT and Eyes equipment | MANDERA EAST | Neboi | 3.9414 | 41.8612 | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES | HEALTH SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 17075853 | 17075853 | 10000000 | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF CIVIL WORKS AND SUPPLY OF 350KV STANDBY GENERATOR AT THE COUNTY HEADQUARTERS IN MANDERA EAST | PROPOSED CONSTRUCTION OF CIVIL WORKS AND SUPPLY OF 350KV STANDBY GENERATOR AT THE COUNTY HEADQUARTERS IN MANDERA EAST | Enhance supply of electricty | Back supply of electricity | MCG/OT/032/2023-2024 |  | MANDERA EAST | Neboi | 3.9416 | 41.8658 | PUBLIC WORKS | PUBLIC WORKS | PUBLIC WORKS | PUBLIC WORKS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 24869959 | 24869959 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED MAINTENANCE OF TAKABA-GITHER ROAD IN MANDERA WEST SUB COUNTY | PROPOSED MAINTENANCE OF TAKABA-GITHER ROAD IN MANDERA WEST SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/033/2023-2024 |  | MANDERA WEST | Takaba | 3.3553 | 40.2228 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 22242496 | 22242496 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED MAINTENANCE OF GITHER-BURDURAS ROAD IN MANDERA WEST SUB COUNTY | PROPOSED MAINTENANCE OF GITHER-BURDURAS ROAD IN MANDERA WEST SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/034/2023-2024 |  | MANDERA WEST | Gither | 3.6787 | 39.9214 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 14860760 | 14860760 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED MAINTENANCE OF KILIWEHIRI-BURDURAS ROAD IN KILIWEHIRI SUB COUNTY | PROPOSED MAINTENANCE OF KILIWEHIRI-BURDURAS ROAD IN KILIWEHIRI SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/035/2023-2024 |  | KILIWEHERI | Kiliwehiri | 3.8602 | 40.2472 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 35052938 | 35052938 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED MAINTENANCE OF TAKABA-DANDU ROAD IN MANDERA WEST SUB COUNTY | PROPOSED MAINTENANCE OF TAKABA-DANDU ROAD IN MANDERA WEST SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/036/2023-2024 |  | MANDERA WEST | TAKABA | 3.4213 | 39.8827 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 39759524 | 39759524 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED MAINTENANCE OF ELWAK-SHIMPIR FATUMA ROAD IN MANDERA SOUTH SUB COUNTY | PROPOSED MAINTENANCE OF ELWAK-SHIMPIR FATUMA ROAD IN MANDERA SOUTH SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/037/2023-2024 |  | MANDERA SOUTH | SHIMPIR FATUMA | 3.0082 | 40512294 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 39932768 | 39932768 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED MAINTENANCE OF SHIMPIR FATUMA- TAKABA ROAD IN MANDERA WEST SUB COUNTY | PROPOSED MAINTENANCE OF SHIMPIR FATUMA- TAKABA ROAD IN MANDERA WEST SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/038/2023-2024 |  | MANDERA SOUTH | SHIMPIR FATUMA | 3.0362 | 40.5065 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 35475959 | 35475959 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED MAINTENANCE OF LAFEY-WARANQARA ROAD IN LAFEY SUB COUNTY | PROPOSED MAINTENANCE OF LAFEY-WARANQARA ROAD IN LAFEY SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/039/2023-2024 |  | LAFEY | Waranqara | 3.3856 | 41.0361 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 40186321 | 40186321 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF MALKAMARI- MURUTHO ROAD IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF MALKAMARI- MURUTHO ROAD IN BANISA SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/040/2023-2024 |  | BANISA | Malkamari | 3.8647 | 39.9208 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 34579600 | 34579600 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED OPENING UP OF DOMAL-ANDARAK ROAD IN BANISA SUB COUNTY | PROPOSED OPENING UP OF DOMAL-ANDARAK ROAD IN BANISA SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/041/2023-2024 |  | BANISA | Malkamari | 3.9489 | 40.353 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 8236000 | 8236000 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF SHIRSHIR-GOFA ROAD IN MANDERA NORTH SUB COUNTY | PROPOSED CONSTRUCTION OF SHIRSHIR-GOFA ROAD IN MANDERA NORTH SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/042/2023-2024 |  | MANDERA NORTH | SHIRSHIR | 3.5022 | 40.6976 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 28449452 | 28449452 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF ELWAK-KUTAYU ROAD IN MANDERA SOUTH SUB COUNTY | PROPOSED CONSTRUCTION OF ELWAK-KUTAYU ROAD IN MANDERA SOUTH SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/043/2023-2024 |  | MANDERA SOUTH | ELWAK | 2.8019 | 40.9053 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 30862264 | 30862264 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF SHIMPIR FATUMA-BURMAYO ROAD IN MANDERA SOUTH SUB COUNTY | PROPOSED CONSTRUCTION OF SHIMPIR FATUMA-BURMAYO ROAD IN MANDERA SOUTH SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/044/2023-2024 |  | MANDERA SOUTH | SHIMPIR FATUMA | 3.0294 | 40.5022 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 32405180 | 32405180 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF CHOROQO-BANISA ROAD IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF CHOROQO-BANISA ROAD IN BANISA SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/045/2023-2024 |  | BANISA | Guba |  |  | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 15821793 | 15821793 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF LAGSURE-WANGAI DAHAN ROAD IN MANDERA WEST SUB COUNTY | PROPOSED CONSTRUCTION OF LAGSURE-WANGAI DAHAN ROAD IN MANDERA WEST SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/046/2023-2024 |  | MANDERA WEST | LAGSURE | 3.4219 | 40.2637 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 11689900 | 11689900 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF LIBEHIYA-ODHA ROAD IN MANDERA EAST SUB COUNTY | PROPOSED CONSTRUCTION OF LIBEHIYA-ODHA ROAD IN MANDERA EAST SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/047/2023-2024 |  | MANDERA EAST | Libehia | 3.8293 | 41.5211 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 28629160 | 28629160 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED STORM WATER PROTECTION WORKS AT RHAMU DIMTU IN MANDERA NORTH SUB COUNTY | PROPOSED STORM WATER PROTECTION WORKS AT RHAMU DIMTU IN MANDERA NORTH SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/048/2023-2024 |  | MANDERA NORTH | RHAMU DIMTU | 4.0187 | 41.0635 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 34088856 | 34088856 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED STORM WATER PROTECTION WORKS AT RHAMU DIMTU IN MANDERA NORTH SUB COUNTY | PROPOSED STORM WATER PROTECTION WORKS AT RHAMU DIMTU IN MANDERA NORTH SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/049/2023-2024 |  | MANDERA NORTH | RHAMU DIMTU | 4.0187 | 41.0635 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 7863640 | 7863640 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED EXTENTION OF LAGSURE DRIFT IN MANDERA WEST SUB COUNTY | PROPOSED EXTENTION OF LAGSURE DRIFT IN MANDERA WEST SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/050/2023-2024 |  | MANDERA WEST | LAGSURE | 3.4219 | 40.2637 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 6926789 | 6926789 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF DRIFT AT LAG BORAR IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF DRIFT AT LAG BORAR IN BANISA SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/051/2023-2024 |  | BANISA | Derkale | 3.8592 | 40.1807 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 9998098 | 9998098 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF LAG DIMA DRIFT AT DERKHALE IN BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF LAG DIMA DRIFT AT DERKHALE IN BANISA SUB COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/052/2023-2024 |  | BANISA | Derkale | 3.8238 | 40.274 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 9987530 | 9987530 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
SUPPLY AND DELIVERY OF MOTORVEHICLE AND MOTORBIKES FOR MANDERA COUNTY GOVERNMENT | SUPPLY AND DELIVERY OF MOTORVEHICLE AND MOTORBIKES FOR MANDERA COUNTY GOVERNMENT | enhance mobility, operational efficiency, and service delivery | Enhanced operation effeciency | MCG/OT/053/2023-2024 |  | MANDERA EAST | N/A |  | N/A | TRANSPORT | TRANSPORT | TRANSPORT | TRANSPORT |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 191200000 | 191200000 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF HOUSING UNITS AND TWIN TOILETS FOR THE VULNERABLE IN THE SOCIETY IN MANDERA COUNTY | PROPOSED CONSTRUCTION OF HOUSING UNITS AND TWIN TOILETS FOR THE VULNERABLE IN THE SOCIETY IN MANDERA COUNTY | To provide shelter to low income societies | Low income societies with shelter | MCG/OT/055/2023-2024 |  | COUNTY WIDE | NA |  | N/A | Social Services | Social Services | Social Services | Social Services |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 199999879 | 199999879 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF BOUNDARY WALL AT ELWAK LIBRARY IN MANDERA SOUTH | PROPOSED CONSTRUCTION OF BOUNDARY WALL AT ELWAK LIBRARY IN MANDERA SOUTH | To enhance the security, safety, and preservation of public property | Ehanced security of the property | MCG/OT/056/2023-2024 |  | MANDERA SOUTH | ELWAK | 2.8068 | 40.9368 | Social Services | Social Services | Social Services | Social Services |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 9957179 | 9957179 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF BOUNDARY WALL AT LAFEY LIBRARY IN LAEFY SUB COUNTY | PROPOSED CONSTRUCTION OF BOUNDARY WALL AT LAFEY LIBRARY IN LAEFY SUB COUNTY | To enhance the security, safety, and preservation of public property | Ehanced security of the property | MCG/OT/057/2023-2024 |  | LAFEY | Lafey | 3.154 | 41.1859 | Social Services | Social Services | Social Services | Social Services |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 9530699 | 9530699 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED REHABILITATION OF FARMLAND AT BENI FARMS IN RHAMU DIMTU WARD, MANDERA NORTH SUB COUNTY | PROPOSED REHABILITATION OF FARMLAND AT BENI FARMS IN RHAMU DIMTU WARD, MANDERA NORTH SUB COUNTY | To enahance prodcutivity of the farmland | Increased agricltural out put | MCG/OT/058/2023-2024 |  | MANDERA NORTH | RHAMU DIMTU | 4.0187 | 41.0635 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 9976200 | 9976200 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED INSTALLATION OF IRRIGATION INFRASTRUCTURE AT YABICHO A FARMS IRRIGATION PROJECT IN RHAMU WARD, MANDERA NORTH SUB COUNTY | PROPOSED INSTALLATION OF IRRIGATION INFRASTRUCTURE AT YABICHO A FARMS IRRIGATION PROJECT IN RHAMU WARD, MANDERA NORTH SUB COUNTY | To Improve Agricultural prodcutivity | Increased agricltural out put | MCG/OT/059/2023-2024 |  | MANDERA NORTH | RHAMU | 3.9292 | 41.2123 | AGRICULTURE | AGRICULTURE | AGRICULTURE | AGRICULTURE |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 36736409 | 36736409 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF CHAIN LINK FENCING OF SENIOR CHIEF ABDULLAHI GIRLS SECONDARY SCHOOL IN KILIWEHIRI SUB COUNTY | PROPOSED CONSTRUCTION OF CHAIN LINK FENCING OF SENIOR CHIEF ABDULLAHI GIRLS SECONDARY SCHOOL IN KILIWEHIRI SUB COUNTY | To enhance the security, safety, and preservation of public property | Ehanced security of the property | MCG/OT/060/2023-2024 |  | KILIWEHERI | KILIWEHERI | 3.9251 | 40.0231 | EDUCATION | EDUCATION | EDUCATION | EDUCATION |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 28643648 | 28643648 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CIVIL WORKS AT MANDERA COUNTY PUBLIC SERVICE BOARD OFFICE IN MANDERA EAST | PROPOSED CIVIL WORKS AT MANDERA COUNTY PUBLIC SERVICE BOARD OFFICE IN MANDERA EAST | improve the functionality, safety, and working environment | Improved working environment | MCG/OT/062/2023-2024 |  | MANDERA EAST | Neboi | 3.9244 | 41.7973 | PUBLIC WORKS | PUBLIC WORKS | PUBLIC WORKS | PUBLIC WORKS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 17965500 | 17965500 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 18,000M3 TURAR EARTH PAN AT BANISA SUB COUNTY | PROPOSED CONSTRUCTION OF 18,000M3 TURAR EARTH PAN AT BANISA SUB COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/063/2023-2024 |  | BANISA | Banisa | 3.8606 | 40.1781 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 8912699 | 8912699 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 20,000M3 ELRAM EARTH PAN IN KUTULO SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000M3 ELRAM EARTH PAN IN KUTULO SUB-COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/064/2023-2024 |  | KUTULO | KUTULO | 2.3316 | 40.8909 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 9869213 | 9869213 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 20,000M3 GUBATU EARTH PAN IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000M3 GUBATU EARTH PAN IN MANDERA WEST SUB-COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/065/2023-2024 |  | MANDERA WEST |  |  |  | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 9702319 | 9702319 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED DESILTING AND EXPANSION OF KOBADADI WEST EARTH PAN BY 20,000M3 IN MANDERA WEST SUB COUNTY | PROPOSED DESILTING AND EXPANSION OF KOBADADI WEST EARTH PAN BY 20,000M3 IN MANDERA WEST SUB COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/066/2023-2024 |  | MANDERA WEST | TAKABA SOUTH | 3.1915 | 40.4221 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 14937448 | 14937448 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 20,000M3 EARTH PAN AT KUBI HALLO IN DANDU SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000M3 EARTH PAN AT KUBI HALLO IN DANDU SUB-COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/067/2023-2024 |  | DANDU | Dandu |  |  | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 10289475 | 10289475 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF 20,000M3 LULIS EARTH PAN IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF 20,000M3 LULIS EARTH PAN IN BANISA SUB-COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/068/2023-2024 |  | BANISA | Banisa | 4.0247 | 40.3322 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 14987140 | 14987140 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF DIDKURO WATER SUPPLY IN MANDERA WEST SUB-COUNTY | PROPOSED CONSTRUCTION OF DIDKURO WATER SUPPLY IN MANDERA WEST SUB-COUNTY | To increase sustainable access to water in the region | Provides reliable, safe, and adequate clean water | MCG/OT/070/2023-2024 |  | MANDERA WEST | Takaba South | 3.2719 | 40.1043 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 184682867 | 184682867 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF TARAMA-KUKUB ROAD IN BANISA SUB-COUNTY | PROPOSED CONSTRUCTION OF TARAMA-KUKUB ROAD IN BANISA SUB-COUNTY | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/071/2023-2024 |  | BANISA | Derkale | 3.8642 | 40.4269 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 39935204 | 39935204 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF BOREHOLE ll –FALAMA ROAD IN KUTULO SUB-COUNTY. | PROPOSED CONSTRUCTION OF BOREHOLE ll –FALAMA ROAD IN KUTULO SUB-COUNTY. | To rovide a reliable and efficient transportation network | An improved road network that enhances connectivity, reduces travel time, and facilitates efficient movement of people and goods | MCG/OT/072/2023-2024 |  | KUTULO | KUTULO | 2.6955 | 40.9213 | ROADS | ROADS | ROADS | ROADS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 36052220 | 36052220 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
CONSULTANCY SERVICES FOR PREPARATION OF VALUATION ROLL FOR MANDERA AND ELWAK MUNICIPALITIES IN MANDERA COUNTY | CONSULTANCY SERVICES FOR PREPARATION OF VALUATION ROLL FOR MANDERA AND ELWAK MUNICIPALITIES IN MANDERA COUNTY | prepare an updated and comprehensive valuation roll | Updated valuation roll | MCG/RFP/01/2023-2024 |  | MANDERA EAST/ELWAK | N/A |  |  | LANDS | LANDS | LANDS | LANDS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 54184800 | 54184800 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
CONSULTANCY SERVICE FOR THE PROVISION OF GEODATIC CONTROLS IN 60 MARKET CENTERS IN MANDERA COUNTY | CONSULTANCY SERVICE FOR THE PROVISION OF GEODATIC CONTROLS IN 60 MARKET CENTERS IN MANDERA COUNTY | establish accurate and reliable geodetic control points | Accurate records of geodatric | MCG/RFP/02/2023-2024 |  | COUNTY WIDE | N/A |  |  | LANDS | LANDS | LANDS | LANDS |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 49550560 | 49550560 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED REHABILITATION OF WATER SUPPLY SYSTEM AND CONNECTION TO WATER KIOSK WITHIN KILIWEHIRI TOWN IN BANISA SUB-COUNTY | PROPOSED REHABILITATION OF WATER SUPPLY SYSTEM AND CONNECTION TO WATER KIOSK WITHIN KILIWEHIRI TOWN IN BANISA SUB-COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/119/2023-2024 |  | BANISA | KILIWEHERI | 3.9066 | 40.0091 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 18488693 | 18488693 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES
PROPOSED CONSTRUCTION OF OVERHEAD/ELAVATED WATER TANK AND WATER SUPPLY PIPING TO WATER KIOSKS AT LIBEHIYA IN MANDERA EAST SUB-COUNTY | PROPOSED CONSTRUCTION OF OVERHEAD/ELAVATED WATER TANK AND WATER SUPPLY PIPING TO WATER KIOSKS AT LIBEHIYA IN MANDERA EAST SUB-COUNTY | To increase sustainable access to groundwater in the region | Provides reliable, safe, and adequate clean water | MCG/OT/120/2023-2024 |  | MANDERA EAST | LIBIHIYA | 3.8293 | 41.5211 | WATER SERVICES | WATER SERVICES | WATER SERVICES | WATER SERVICES |  | 4/15/2024 | 4/14/2024 | 4/14/2024 | 30000000 | 30000000 |  | GOK | N/A | Full | N/A | [5 empty] | COMPLETED | 100% | N/A | N/A | N/A | N/A | N/A | NO | N/A | N/A | YES |  | YES |  | YES